## Slide 1: CUSTOMER DATA PLATFORM : MVP1
National Grid
Weekly Update
Week Ending 10/22/2021

## Slide 2: Agenda
One Page - Status, Risks and Issues

## Slide 3
Key Highlights | Review of Comms Channels completed, gaps identified and plan in place to eliminate communication gaps
Last One Weeks Accomplished Tasks
Grid home template draft complete Change impact validation plan in place Communication channel gap assessment complete and updated plan in place
Next One Weeks Planned Tasks
Review of communication channels and gap assessment Development of Grid:home page template Presentation for Customer Business Review Meeting (BRM) 10/19/21)
Change Management | Lead : Lauren Montgomery |  | 
Main Objectives: Share program communications with key stakeholders and impacted employees |  |  | Overall Status Green
Upcoming Milestones | Planned Start Date | Planned End Date | Revised End Date | Status / Comments
Grid:home page launch | 10/7/2021 | 11/3/2021 |  | On track
Customer Change Network Presentation | 10/7/2021 | 10/22/2021 |  | On track
Major Dependencies | Target Date | Status
Change Impact Tracking to allow for validation and communications | 10/22/2021 | 
Resources | Date | Status
Change Management integration with other business areas needed | 10/29/2021 | 
ZBR efforts picking up and will require time and effort from Lauren Montgomery | 10/29/2021 | 
Top issues | Mitigation Plan | Target Date
Top Risks | Mitigation Plan | Target Date
Unable to validate and share changes if none are entered into tracker | All squads review and submit change impacts weekly | Ongoing

## Slide 4
Key Highlights | Reltio DEV environment is available to use SSO with NG Azure AD is completed Initial MDM roles are configured in Azure AD and Reltio Connectivity with Matillion is completed that will allow connectivity with Customer source systems – CRIS and CSS New MDM resources are onboarded Reltio professional service team should be joining from 11/01/2021 Reltio TEST and PROD environments setups are in progress MDM data mapping and analysis are in progress
Last One Weeks Accomplished Tasks
Few steps of Reltio and Snowflake connectivity are completed New Resources are onboarded Data Mapping and analysis of few data elements are completed
Next One Weeks Planned Tasks
Complete Snowflake-Reltio connectivity Continue working on MDM specific data mapping and analysis Complete few steps of TEST and PROD environments
Master Data Management | Lead : Nishit Ajwaliya |  | 
Main Objectives: Create curated, Customer Golden master record with Unique enterprise persistent customer Id in Reltio MDM and sync data with Snowflake for the downstream use. |  |  | Overall Status Green
Upcoming Milestones | Planned Start Date | Planned End Date | Revised End Date | Status / Comments
Connectivity with Snowflake | 10/7/2021 | 10/29/2021 |  | On track
MDM Specific data mapping | 10/11/2021 | 11/19/2021 |  | On track
Reltio TEST and PROD environment setup | 10/21/2021 | 11/30/021 |  | On track
Onboard Reltio professional service team | 11/01/2021 | 11/10/2021 |  | On track
Major Dependencies | Target Date | Status
Logical Data Model of MVP1 scope elements | TBD | 
Resources | Date | Status
Reltio Professional Service | 11/1/2021 | Green
Top issues | Mitigation Plan | Target Date
Top Risks | Mitigation Plan | Target Date

## Slide 5
Key Highlights | Raymond is now the Product Manager Information architects, DG and customer team provided direction on EDC as being next key deliverable Approved 4 DG & MDM resources to join and begun onboarding On target for current DG sprint deliverables
Last One Weeks Accomplished Tasks
EDC Demonstration within DG team CDT and WDD glossary terms and related attributes captured Agreed with EAI the work done building the Axon glossary can happen in parallel with EDC integration Meet and Greet of Reltio MDM Analyst Onboarding Resources Created 12 additional stories to cover unplanned activities Enterprise Risks (Parallel MVPs w/o foundational work in place)
Next One Weeks Planned Tasks
Build DG MVP1 to provide glossary management Review Vishal’s stories EDC deliverable for the discussion with Maria on EDC/Axon Integration Onboarding of New Hires / Reltio MDM Analyst to Meet with Nishit & MDM Team, Review Reltio Documentation etc. Sprint Planning Defining Scope for EDC Integration Enterprise Risk Examples
Squad Name – Data Governance | Lead : Diane LoPreste |  | 
Main Objectives: Creating data capability pillars by deploying a data management and governance enterprise solution framework & approach using Customer as the first MVP that provides a Data Catalog, Data Glossary, Data Quality, Critical Data and Authority & Control |  |  | Overall Status Green
Major Dependencies | Target Date | Status
Clarity on “training approach” and “route to production” from project team​ |  | Raised as JIRA stories to track progress
The governance tools require documenting outside of any temporary project structure provide future teams such as support an enduring record of what has been built, how it works, what the enterprise tool delivers etc. At present there is no “system owner“ to take on this responsibility |  | Roles first raised as an issue 29th July 2021
Newly appointed product manager needs time to determine product roadmap and pipeline requirements |  | 
Resources | Date | Status
John Followell – Data Governance & Management Lead |  | Onboarded
Gavin Marshall – Informatica User Operating Model Lead |  | Onboarded
Morgan Reynolds – Data Governance & Management Analyst |  | Onboarded
Maryam Moshrefi – Reltio MDM Analyst |  | Onboarded
Apurba Sarkar – Reltio MDM Lead | 10/14 | Onboarded
Nishal Doctor - Informatica Business Systems Analyst (US) |  | Onboarding / System Access / Laptop
Ramesh Govindan - Data Governance & Management Lead |  | Onboarding / System Access / Laptop
Informatica Business Systems Analyst (UK) |  | Onboarding
MDM Principal Business Analyst |  | Open / Interviewing
Top issues | Mitigation Plan | Target Date
Informatica Tool Precedence Axon vs. EDC | AI Working Group / Informatica | ~10/12/2021
The ‘Ops Model’ covering topics such as DGC ToRs has multiple, parallel teams working in isolation, e.g.,. CDT DG lead, DG team, Accenture on WDD | Customer Product Team / DG Team to discuss and determine plan | WDD & Customer - Green / Other - Orange
Top Risks | Mitigation Plan | Target Date
Axon/EDC – CDQ Interface | Integration Team/ Informatica | 
Informatica Implementation Expertise |  | 
Upcoming Milestones | Planned Date | Revised Date | Status / Comments
EDC Demonstration to broader team members | 11/5 |  | Planned
Notes: Ongoing discussion on how much EDC can we fit in and what are the requirements (tool experience would be useful here) 3, 4, 2 done, 5 done, 6 done
Identify any glossary related attributes required by CDT or WDD so it can be factored into the starter glossary in Informatica Axon, i.e., the need to capture data criticality​
Work with Enterprise Information Architect to determine if "Axon first" is the right approach, or if there is greater value in starting with EDC​
Build the DG MVP1 to provide glossary management functionality​
Review Vishal's stories and re-work into what makes sense knowing what we now know​
Create additional user stories to cover unplanned activities, meetings, etc.​
Establish project support process for system issues​
Continue to source for Resources

## Slide 6: Action Log (Open Items)
Sl No | Area | Date | RAID | Description | Owner | Target End Date | Status | Remarks