## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | Customer Data Platform | 89 days? | September 8, 2021 8:00 AM | January 10, 2022 5:00 PM |  | 1
2 | Yes | Auto Scheduled | CDP release1 (Dec 2021) | 89 days? | September 8, 2021 8:00 AM | January 10, 2022 5:00 PM |  | 2
3 | Yes | Auto Scheduled | Dependencies | 4 days? | October 27, 2021 8:00 AM | November 1, 2021 5:00 PM |  | 3
4 | Yes | Auto Scheduled | Bitbucket readiness | 1 day? | November 1, 2021 8:00 AM | November 1, 2021 5:00 PM |  | 4
5 | Yes | Auto Scheduled | Mattillion Dev box | 1 day | October 28, 2021 8:00 AM | October 28, 2021 5:00 PM |  | 4
6 | Yes | Auto Scheduled | Unix server Readiness | 1 day? | October 27, 2021 8:00 AM | October 27, 2021 5:00 PM |  | 4
7 | Yes | Auto Scheduled | Access to the Unix Server | 3 days | October 28, 2021 8:00 AM | November 1, 2021 5:00 PM | 6 | 4
8 | Yes | Manually Scheduled | ZBR Team and DBA for data details | 1 day | October 27, 2021 8:00 AM | October 27, 2021 5:00 PM |  | 4 | No dates available now.
9 | Yes | Manually Scheduled | Milestones |  |  |  |  | 3
10 | Yes | Auto Scheduled | Data Integration | 15.5 days? | October 21, 2021 8:00 AM | November 11, 2021 12:00 PM |  | 3
11 | Yes | Auto Scheduled | Dev environment | 15.5 days? | October 21, 2021 8:00 AM | November 11, 2021 12:00 PM |  | 4
12 | Yes | Auto Scheduled | CSS-CDC | 15.5 days? | October 21, 2021 8:00 AM | November 11, 2021 12:00 PM |  | 5
13 | Yes | Auto Scheduled | Create Table Scripts (15 tables) | 46 hrs | October 21, 2021 8:00 AM | October 28, 2021 3:00 PM |  | 6
14 | Yes | Auto Scheduled | Create Table Scripts (remaining tables 26) | 3 days? | November 5, 2021 8:00 AM | November 9, 2021 5:00 PM |  | 6
15 | Yes | Auto Scheduled | Adding to VS /Deployment Script | 10 hrs | November 2, 2021 8:00 AM | November 3, 2021 10:00 AM | 13,4,5 | 6
16 | Yes | Auto Scheduled | Configuring Framework Tables | 10 hrs | November 3, 2021 10:00 AM | November 4, 2021 12:00 PM | 15 | 6
17 | Yes | Auto Scheduled | Matillion Pipeline | 40 hrs | November 4, 2021 1:00 PM | November 11, 2021 12:00 PM | 16 | 6
18 | Yes | Auto Scheduled | QA- to check with Shohreh | 60 hrs | October 26, 2021 8:00 AM | November 4, 2021 12:00 PM |  | 6
19 | Yes | Auto Scheduled | CRIS-RAW | 11.25 days | October 26, 2021 8:00 AM | November 10, 2021 10:00 AM |  | 5
20 | Yes | Auto Scheduled | Create Table Scripts | 46 hrs | October 27, 2021 8:00 AM | November 3, 2021 3:00 PM |  | 6
21 | Yes | Auto Scheduled | Adding to VS /Deployment Script | 10 hrs | November 3, 2021 3:00 PM | November 4, 2021 5:00 PM | 20,4,5 | 6
22 | Yes | Auto Scheduled | Configuring Framework Tables | 10 hrs | November 5, 2021 8:00 AM | November 8, 2021 10:00 AM | 21 | 6
23 | Yes | Auto Scheduled | Matillion Pipeline | 16 hrs | November 8, 2021 10:00 AM | November 10, 2021 10:00 AM | 16,22 | 6
24 | Yes | Auto Scheduled | QA- to check with Shohreh | 60 hrs | October 26, 2021 8:00 AM | November 4, 2021 12:00 PM |  | 6
25 | Yes | Auto Scheduled | CSS-RAW | 1.88 days | October 26, 2021 8:00 AM | October 27, 2021 4:00 PM |  | 5 | Cant start unless business clarification. cant plan without having the clarification.
26 | Yes | Auto Scheduled | Create Table Scripts | 11.5 hrs | October 26, 2021 8:00 AM | October 27, 2021 11:30 AM |  | 6
27 | Yes | Auto Scheduled | Adding to VS /Deployment Script | 11.5 hrs | October 26, 2021 8:00 AM | October 27, 2021 11:30 AM |  | 6
28 | Yes | Auto Scheduled | Configuring Framework Tables | 2.5 hrs | October 26, 2021 8:00 AM | October 26, 2021 10:30 AM |  | 6
29 | Yes | Auto Scheduled | Matillion Pipeline | 8 hrs | October 26, 2021 8:00 AM | October 26, 2021 5:00 PM |  | 6
30 | Yes | Auto Scheduled | QA- to check with Shohreh | 15 hrs | October 26, 2021 8:00 AM | October 27, 2021 4:00 PM |  | 6
31 | Yes | Auto Scheduled | CSS/CRIS Code | 8.06 days | October 26, 2021 8:00 AM | November 5, 2021 8:30 AM |  | 5
32 | Yes | Auto Scheduled | Create Table Scripts | 11.5 hrs | November 2, 2021 8:00 AM | November 3, 2021 11:30 AM | 7 | 6
33 | Yes | Auto Scheduled | Adding to VS /Deployment Script | 2.5 hrs | November 3, 2021 11:30 AM | November 3, 2021 3:00 PM | 32 | 6
34 | Yes | Auto Scheduled | Configuring Framework Tables | 2.5 hrs | November 3, 2021 3:00 PM | November 4, 2021 8:30 AM | 33 | 6
35 | Yes | Auto Scheduled | Matillion Pipeline | 8 hrs | November 4, 2021 8:30 AM | November 5, 2021 8:30 AM | 34 | 6
36 | Yes | Auto Scheduled | QA- to check with Shohreh | 15 hrs | October 26, 2021 8:00 AM | October 27, 2021 4:00 PM |  | 6
37 | Yes | Auto Scheduled | UCCE | 1.34 days | October 28, 2021 8:00 AM | October 29, 2021 10:45 AM | 8 | 5 | Cant start without task 8 which is unknown.
38 | Yes | Auto Scheduled | Create Table Scripts | 10.75 hrs | October 28, 2021 8:00 AM | October 29, 2021 10:45 AM |  | 6
39 | Yes | Auto Scheduled | Adding to VS /Deployment Script | 2.5 hrs | October 28, 2021 8:00 AM | October 28, 2021 10:30 AM |  | 6
40 | Yes | Auto Scheduled | Configuring Framework Tables | 2.5 hrs | October 28, 2021 8:00 AM | October 28, 2021 10:30 AM |  | 6
41 | Yes | Auto Scheduled | Matillion Pipeline | 8 hrs | October 28, 2021 8:00 AM | October 28, 2021 5:00 PM |  | 6
42 | Yes | Auto Scheduled | QA- to check with Shohreh | 3 hrs | October 28, 2021 8:00 AM | October 28, 2021 11:00 AM |  | 6
43 | Yes | Auto Scheduled | Calabrio | 1 day | October 27, 2021 5:00 PM | October 28, 2021 5:00 PM | 8 | 5 | Cant start without task 8 which is unknown.
44 | Yes | Auto Scheduled | Create Table Scripts | 5.75 hrs | October 28, 2021 8:00 AM | October 28, 2021 2:45 PM |  | 6
45 | Yes | Auto Scheduled | Adding to VS /Deployment Script | 1.25 hrs | October 28, 2021 8:00 AM | October 28, 2021 9:15 AM |  | 6
46 | Yes | Auto Scheduled | Configuring Framework Tables | 1.25 hrs | October 28, 2021 8:00 AM | October 28, 2021 9:15 AM |  | 6
47 | Yes | Auto Scheduled | Matillion Pipeline | 8 hrs | October 28, 2021 8:00 AM | October 28, 2021 5:00 PM |  | 6
48 | Yes | Auto Scheduled | QA- to check with Shohreh | 0 hrs | October 27, 2021 5:00 PM | October 27, 2021 5:00 PM |  | 6
49 | Yes | Auto Scheduled | MDM | 89 days | September 8, 2021 8:00 AM | January 10, 2022 5:00 PM |  | 3
50 | Yes | Auto Scheduled | DEV | 89 days | September 8, 2021 8:00 AM | January 10, 2022 5:00 PM |  | 4
51 | Yes | Auto Scheduled | Reltio MDM DEV environment ready to use for the CDP project | 29 days | September 8, 2021 8:00 AM | October 18, 2021 5:00 PM |  | 5
52 | Yes | Auto Scheduled | Create initial MDM roles for Customer domain | 12 days | November 15, 2021 8:00 AM | November 30, 2021 5:00 PM | 61FF,51FF | 5
53 | Yes | Auto Scheduled | Snowflake and Matillion connectivity from Reltio | 12 days | November 15, 2021 8:00 AM | November 30, 2021 5:00 PM | 61FF,51FF | 5
54 | Yes | Auto Scheduled | Complete data mapping and data analysis for the MVP1 Master data elements | 27 days | October 14, 2021 8:00 AM | November 19, 2021 5:00 PM |  | 5
55 | Yes | Auto Scheduled | Create CSS and CRIS data files for MDM in DEV (and possibly) using Matillion based on the data mapping document (dependency - #4) | 25 days | November 8, 2021 8:00 AM | December 10, 2021 5:00 PM | 54FS-10d | 5
56 | Yes | Auto Scheduled | Document Master data business rules – matching, workflow, governance access etc | 15 days | November 1, 2021 8:00 AM | November 19, 2021 5:00 PM |  | 5
57 | Yes | Auto Scheduled | Configure first draft of Reltio MDM as per the data mapping and business rules in DEV | 25 days | December 7, 2021 8:00 AM | January 10, 2022 5:00 PM | 55FS-4d | 5
58 | Yes | Auto Scheduled | Configure some customer reference data into Reltio RDM module (dependency - #1, #4) | 25 days | December 7, 2021 8:00 AM | January 10, 2022 5:00 PM | 55FS-4d | 5
59 | Yes | Auto Scheduled | Try to load customer data files into DEV Reltio (dependency - #1 ,#6) | 20 days | November 15, 2021 8:00 AM | December 10, 2021 5:00 PM | 55FS-20d | 5
60 | Yes | Auto Scheduled | Test & Prod | 40 days | October 21, 2021 8:00 AM | December 15, 2021 5:00 PM |  | 4
61 | Yes | Auto Scheduled | Reltio MDM TEST, and PROD environment ready to use for the CDP project | 29 days | October 21, 2021 8:00 AM | November 30, 2021 5:00 PM |  | 5
62 | Yes | Auto Scheduled | Configure Reltio Snowflake connector to MDM Golden record data load into Snowflake only if we were able to create some golden record in MDM (Dependency - #3, #8, #9) | 13 days | November 15, 2021 8:00 AM | December 1, 2021 5:00 PM |  | 5
63 | Yes | Auto Scheduled | Adjust configuration of MDM roles to support Customer domain | 10 days | December 2, 2021 8:00 AM | December 15, 2021 5:00 PM | 62 | 5

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | gopi | g | Work |  |  |  |  | 100% | $0.00/h | 0
2 | Padmavati | P | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Moupiya | M | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Sushanta | S | Work |  |  |  |  | 100% | $0.00/h | 0
5 | Raymond | R | Work |  |  |  |  | 100% | $0.00/h | 0
6 | Sean | S | Work |  |  |  |  | 100% | $0.00/h | 0
7 | Suzanne | S | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Bitbucket readiness | Moupiya | 0 | 8h | 100%
Bitbucket readiness | Sushanta | 0 | 8h | 100%
Mattillion Dev box | Raymond | 0 | 8h | 100%
Mattillion Dev box | Sean | 0 | 8h | 100%
ZBR Team and DBA for data details | Raymond | 0 | 8h | 100%
ZBR Team and DBA for data details | Sushanta | 0 | 8h | 100%
ZBR Team and DBA for data details | Suzanne | 0 | 8h | 100%
Create Table Scripts (15 tables) | gopi | 0.90000000000000002 | 46h | 100%
Create Table Scripts (remaining tables 26) | gopi | 0 | 24h | 100%
Adding to VS /Deployment Script | gopi | 0 | 10h | 100%
Configuring Framework Tables | gopi | 0 | 10h | 100%
Matillion Pipeline | gopi | 0 | 40h | 100%
Create Table Scripts | Padmavati | 0 | 46h | 100%

## Stories for MDM
# | MDM Tasks | Story Description |  | Story Point | SAFe Team | Feature | Story # | Sprint #
DEV
| Reltio MDM DEV environment ready to use for the CDP project | Task completed
| Create initial MDM roles for Customer domain | Task completed
| Snowflake and Matillion connectivity from Reltio | Task completed
| Complete data mapping and data analysis for the MVP1 Master data elements |  | Close the current story and create a new one. - Create some sub tasks for other team memebers. | 13 | CDT_Data_Integration | CDTPROG-64 | CDTTEAM-520 | TI2.23.2.21
| As an MDM developer, I want to document MDM Data Mapping for Reltio (version 2) | This is the 2nd version of the MDM data mapping document. As a MDM lead, I should be able to review and complete MDM data mapping for Reltio MDM configuration so it can use by Reltio Configurator. This need is fulfilled by creating data mapping document. This is continuation of the previous story CDTTEAM-520 to cover the rest of the attributes and transformation rules. |  | 8 | CDT_Data_Integration |  | CDTTEAM-670 |  | TI2.24.3.21
| Create CSS and CRIS data files for MDM in DEV (and possibly) using Matillion based on the data mapping document (dependency - #6) | As a MDM lead, I should be able to review and complete MDM data mapping for Reltio MDM configuration so it can use by Reltio Configurator. This need is fulfilled by creating data mapping document. | Two story - one for CSS and one for CRIS. Create sub tasks for other team members. | 13 for each story | CDT_Data_Integration | CDTPROG-34 CDTPROG-33 | CDTTEAM-521 CDTTEAM-522 | TI2.23.2.21 | TI2.24.3.21
| Document Master data business rules – matching, workflow, governance access etc | This is continuation of the previous story CDTTEAM-520 to cover the rest of the attributes and transformation rules. |  | 8 | CDT_Data_Integration | CDTPROG-64 | CDTTEAM-524 | TI2.23.2.21
| Configure first draft of Reltio MDM as per the data mapping and business rules in DEV (Dependency #6 & 8) | As a MDM Lead, I should be able to configure the Reltio MDM in Dev as per the data mapping and business rules defined as part of MVP1 requirements. This need is fulfilled by configuring the Reltio MDM in dev environment. |  | 13 | CDT_Data_Integration | CDTPROG-64
| Configure some customer reference data into Reltio RDM module (dependency - #6, #9) | As a MDM Lead, I should be able to configure the Reltio RDM in Dev as per the data mapping and reference data defined as part of MVP1 requirements. This need is fulfilled by configuring the Reltio RDM in dev environment. |  | 5 | CDT_Data_Integration | CDTPROG-64
| Try to load customer data files into DEV Reltio (dependency - ) | As a MDM lead, I should be able to load source data files into Reltio MDM in Dev. This need is fulfilled by loading the source data files into Reltio MDM. | Two story - one for CSS and one for CRIS | 8 for each story | CDT_Data_Integration
| As a MDM Lead, I should be able to create MDM Match Rule report format for Business review during Match Tuning | As a Reltio MDM Business Lead, I should be able to create a suggestive MDM Match Rule execution report format so that it can be leveraged and populated by Technical team to get the match report reviewed by Business stakeholders |  | 5 |  | CDTPROG-64 | CDTTEAM-672
| As a Reltio MDM Business System Lead, I should be able to define Reltio MDM Roles and respective users for setup | As a Reltio MDM Business Lead, I should be able to document different required Reltio MDM roles and list of respective users. |  |  |  | CDTPROG-64 | CDTTEAM-673
Test & Prod
| Reltio MDM TEST, and PROD environment ready to use for the CDP project | Shall we create a single story for this? |  | Not required
| Configure Reltio Snowflake connector to MDM Golden record data load into Snowflake only if we were able to create some golden record in MDM (Dependency - #3, #8, #9) | As a MDM lead, I should be able to configure Snowflake connector in Reltio Test & Prod environment so that golden records from Reltio can be loaded into Snowflake. This need is fulfilled by configuring Snowflake account and enabling Snowflake connector in Reltio. | Two story - one for test and one for prod | 5 for each story | CDT_Data_Integration
| Adjust configuration of MDM roles to support Customer domain | As a MDM lead, I should be able to add new roles or modify existing roles in Reltio MDM to support Customer domain business requirements. | Break into two stories - one for AD Roles creation and one for Reltio roles | 3 for each story | CDT_Data_Integration
| Onboard Reltio team members | As a MDM lead, I should be able to onboard Reltio team members so that they can start working in the project. |  | 8 | CDT_Data_Integration | CDTPROG-216 | CDTTEAM-523 | TI2.23.2.21