## Slide 1: CUSTOMER DATA PLATFORM : MVP1
National Grid
Sprint # - Update

## Slide 2: Agenda
One Page - Status, Risks and Issues

## Slide 3
Key Highlights | Grid:home training complete and CDP page in development
Last One Weeks Accomplished Tasks
Sponsor briefing completed Leadership touchpoint completed
Next One Weeks Planned Tasks
Review of communication channels and gap assessment Development of Grid:home page template
Change Management | Lead : Lauren Montgomery | Week Ending | 
Main Objectives: Share program communications with key stakeholders and impacted employees |  |  | Overall Status Green
Upcoming Milestones | Planned Start Date | Planned End Date | Revised End Date | Status / Comments
Grid:home page launch | 10/7/2021 | 11/3/2021 |  | On track
Customer Change Network Presentation | 10/7/2021 | 10/22/2021 |  | On track
Major Dependencies | Target Date | Status
Change Impact Tracking to allow for validation and communications | Weekly / ongoing | 
Resources | Date | Status
Top issues | Mitigation Plan | Target Date
Top Risks | Mitigation Plan | Target Date
Unable to validate and share changes if none are entered into tracker | All squads review and submit change impacts weekly | Ongoing

## Slide 4
Key Highlights | Reltio DEV environment is available to use SSO with NG Azure AD is completed Initial MDM roles are configured in Azure AD and Reltio
Last One Weeks Accomplished Tasks
Reltio DEV environment is available to use Presented full end to end architecture to the team
Next One Weeks Planned Tasks
Connectivity with Matillion Complete few steps of Snowflake connectivity
Master Data Management | Lead : Nishit Ajwaliya | Week Ending: 10/15/2021 | 
Main Objectives: Share program communications with key stakeholders and impacted employees |  |  | Overall Status Green
Upcoming Milestones | Planned Start Date | Planned End Date | Revised End Date | Status / Comments
Connectivity with Matillion | 10/7/2021 | 10/21/2021 |  | On track
Connectivity with Snowflake | 10/7/2021 | 10/29/2021 |  | On track
Major Dependencies | Target Date | Status
Logical Data Model of MVP1 scope elements | TBD | 
Resources | Date | Status
Reltio Professional Service | 10/25/2021 | Green
Top issues | Mitigation Plan | Target Date
Top Risks | Mitigation Plan | Target Date

## Slide 5
Key Highlights | Sprint Planning Agreed and Completed​ Delivered Axon configuration with National Grid structures such as organization, top level data domains, policies, regulations etc. Established regular “show and tell” sessions for steering group to drive business requirements
Last One Weeks Accomplished Tasks
Sprint 3 concluded with DG delivering 36 out of 38 stories (1 blocked by defect, 1 returned to backlog due to Axon version issues) Agreed scope for Sprint 4 and developed backlog for delivery of data glossary capability within Axon.
Next One Weeks Planned Tasks
Identify any glossary related attributes required by CDT or WDD so it can be factored into the starter glossary in Informatica Axon, i.e., the need to capture data criticality​ Work with Enterprise Information Architect to determine if "Axon first" is the right approach, or if there is greater value in starting with EDC​ Build the DG MVP1 to provide glossary management functionality​ Review Vishal's stories and re-work into what makes sense knowing what we now know​ Create additional user stories to cover unplanned activities, meetings, etc.​ Establish project support process for system issues​ Continue to source for Resources
Squad Name – Data Governance | Lead : Diane LoPreste | Week Ending 8/10/2021 | 
Main Objectives: Creating data capability pillars by deploying a data management and governance enterprise solution framework & approach using Customer as the first MVP that provides a Data Catalog, Data Glossary, Data Quality, Critical Data and Authority & Control |  |  | Overall Status Green
Major Dependencies | Target Date | Status
Clarity on “training approach” and “route to production” from project team​ |  | Raised as JIRA stories to track progress
The governance tools require documenting outside of any temporary project structure provide future teams such as support an enduring record of what has been built, how it works, what the enterprise tool delivers etc. At present there is no “system owner“ to take on this responsibility |  | Roles first raised as an issue 29th July 2021
There is an absence of a senior role to give direction, to ensure the expected business value is delivered and to drive Axon / EDC requirements. Without the roadmap, the team are left with no clear direction, requirements or confidence in the value of what is being delivered |  | First raised as an issue 29th July 2021
Resources | Date | Status
John Followell – Data Governance & Management Lead |  | Onboarded
Gavin Marshall – Informatica User Operating Model Lead |  | Onboarded
Morgan Reynolds – Data Governance & Management Analyst |  | Onboarded
Maryam Moshrefi – Reltio MDM Analyst |  | Onboarded
Apurba Sarkar – Reltio MDM Lead | 10/8 | Awaiting email from IT – System Access
Nishal Doctor - Informatica Business Systems Analyst (US) |  | Onboarding
Ramesh Govindan - Data Governance & Management Lead |  | Onboarding
Informatica Business Systems Analyst (UK) |  | Open / Interviewing
MDM Principal Business Analyst |  | Open / Interviewing
Top issues | Mitigation Plan | Target Date
Finding Resources / Onboarding Timeline | Reviewing CV’s / Interviewing | Ongoing
Informatica Tool Precedence Axon vs. EDC | AI Working Group / Informatica | ~10/12/2021
The ‘Ops Model’ covering topics such as DGC ToRs has multiple, parallel teams working in isolation, e.g.,. CDT DG lead, DG team, Accenture on WDD | Customer Product Team / DG Team to discuss and determine plan | 
Top Risks | Mitigation Plan | Target Date
Axon/EDC – CDQ Interface | Integration Team/ Informatica | 
Upcoming Milestones | Planned Date | Revised Date | Status / Comments
Playback of sprint deliverables to steering group |  |  | In Progress
Notes: Resources should be a footnote on page 4, Decision required should be added

## Slide 6: Action Log (Open Items)
Sl No | Date | RAID | Description | Owner | Target End Date | Status | Remarks