## Slide 1: CUSTOMER DATA PLATFORM : MVP1
National Grid
Weekly Update
Week Ending 10/22/2021

## Slide 2: Agenda
One Page - Status, Risks and Issues

## Slide 3
Key Highlights | Snowflake/Matillion Data Engineers are onboarded and assigned to this Sprint work. CSS/CRIS Assessment completed. UCCE and Calabrio assessment started. CSS CDC 15 tables –Data ingestion Framework setup completed Started on CSA, CSA Lite, Vision Template and BSR’s Data element documents for CSS and CRIS completed and started UCCE data element document.
Last One Weeks Accomplished Tasks
CRIS data element document completed. CSS data element document completed. Completed CSS assessment. Including work/tasks identified for MVP1. Completed CRIS assessment. Including work/tasks identified for MVP1. Matillion job created to test CSS/CRIS data load with configuration. Initial draft Tech specification completed. Started working on CSA/CSA Lite along with Amol. Started working on BSR’s for CDP and ZBR.
Next One Weeks Planned Tasks
Follow up and test on UCCE/Calabrio IP Firewall request. Work on UCCE handbook and data element document. Work on DEV data load process – Setup SQL scripts, Matillion jobs and framework ready for CSS CDC tables. Work on Technical Spec for CSS CDC table load process. Work on CSA/CSA Lite along with Amol. Work on BSR’s for CDP and ZBR. Meet IVR team for source system details and understand data Follow-up with business on MVP1 data requirements.
Squad Name – Data Integration | Lead : Kiranmai Nandikonda |  | 
Main Objectives: Data integration – Connect to Source systems and load data into Cloud platform Snowflake. |  |  | Overall Status Amber
Major Dependencies | Target Date | Status
CSS code tables​ firewall completion |  | Checking with Security team - in progress
UCCE, Calabrio and UWF dev server firewall request | 10/27/21 | Checking with Security team - in progress
IVR other systems – CVP, CATS and BPA source system details |  | Checking with team, weekly meeting to discuss
Resources | Date | Status
Gopi Dungrani |  | Onboarded
Rajashekar Gande |  | Onboarded – 50%
Hom-yip Doris |  | Onboarded
Bhanuprakash Thota |  | Onboarded
Vamshi reddy Jakkula |  | Onboarded
Venkata Chebolu |  | Onboarded – 50%
Ralph Mendoza |  | Onboarded – 50 %
Padmavathi Kancham |  | Onboarded
Shruti Patil |  | Onboarded
Top issues | Mitigation Plan | Target Date
DEV Matillion ready | Users created and copy jobs from POC server. | ~10/26/2021
MVP1 Scope – Identify CSS/CRIS tables for first load. | Waiting for Mike is to share it. | 10/22/2021
Top Risks | Mitigation Plan | Target Date
IVR systems details | Raymond escalating for it | 10/22/21
ZBR Data Files | Mike to provide it. | 10/22/21
Upcoming Milestones | Planned Date | Revised Date | Status / Comments
Connect to UCCE, Calabrio and UWF Source systems | 10/28/2021 |  | 
Notes: Ongoing discussion on how much EDC can we fit in and what are the requirements (tool experience would be useful here) 3, 4, 2 done, 5 done, 6 done
Identify any glossary related attributes required by CDT or WDD so it can be factored into the starter glossary in Informatica Axon, i.e., the need to capture data criticality​
Work with Enterprise Information Architect to determine if "Axon first" is the right approach, or if there is greater value in starting with EDC​
Build the DG MVP1 to provide glossary management functionality​
Review Vishal's stories and re-work into what makes sense knowing what we now know​
Create additional user stories to cover unplanned activities, meetings, etc.​
Establish project support process for system issues​
Continue to source for Resources

## Slide 4
Key Highlights | Customer Change Network Presentation complete
Last One Weeks Accomplished Tasks
Customer Org BRM complete (10/19) Customer Change Network Meeting Complete (10/22)
Next One Weeks Planned Tasks
Review Training Strategy Initial Branding Discussions with Marketing Team (10/26) Change Impact Validation Internal Leadership Review of Grid:home page template
Change Management | Lead : Lauren Montgomery |  | 
Main Objectives: Share program communications with key stakeholders and impacted employees |  |  | Overall Status Green
Upcoming Milestones | Planned Start Date | Planned End Date | Revised End Date | Status / Comments
Grid:home page launch | 10/7/2021 | 11/3/2021 |  | On track
Customer Change Network Presentation | 10/7/2021 | 10/22/2021 |  | Complete
Major Dependencies | Target Date | Status
Change Impact Tracking to allow for validation and communications | 11/3/2021 | 
Resources | Date | Status
Change Management integration with other business areas needed | 10/29/2021 | 
ZBR efforts picking up and will require time and effort from Lauren Montgomery | 10/29/2021 | 
Top issues | Mitigation Plan | Target Date
Top Risks | Mitigation Plan | Target Date

## Slide 5
Key Highlights | Reltio DEV environment is available to use SSO with NG Azure AD is completed Initial MDM roles are configured in Azure AD and Reltio Connectivity with Matillion is completed that will allow connectivity with Customer source systems – CRIS and CSS New MDM resources are onboarded Received confirmation on Reltio professional service resources Reltio professional service team should be joining from 11/08/2021 Reltio TEST and PROD environments setups are in progress MDM data mapping and analysis are in progress
Last One Weeks Accomplished Tasks
Reltio Professional service contract has signed, and resources identified Snowflake account for Reltio is created and connectivity made Continuously making progress for data Mapping and analysis for MDM MVP1 data elements Team members are getting access for Reltio, Source systems, and Matillion
Next One Weeks Planned Tasks
Complete Snowflake-Reltio connectivity Continue working on MDM specific data mapping and analysis Complete few steps of TEST and PROD environments
Master Data Management | Lead : Nishit Ajwaliya |  | 
Main Objectives: Create curated Customer Golden master record with Unique enterprise persistent customer Id in Reltio MDM and sync data with Snowflake for the downstream use. |  |  | Overall Status Green
Upcoming Milestones | Planned Start Date | Planned End Date | Revised End Date | Status / Comments
Connectivity with Snowflake | 10/7/2021 | 11/03/2021 |  | On track
MDM Specific data mapping | 10/11/2021 | 11/19/2021 |  | On track
Reltio TEST and PROD environment setup | 10/21/2021 | 11/30/021 |  | On track
Onboard Reltio professional service team | 11/08/2021 | 11/20/2021 |  | On track
Major Dependencies | Target Date | Status
Logical Data Model of MVP1 scope elements | TBD | Amber
Resources | Date | Status
Reltio Professional Service Resources | 11/08/2021 | Green
Top issues | Mitigation Plan | Target Date
Logical Data Model for MVP1 scope entities and elements | Continue working on MDM as per current information from Core business team and adjust once LDM is available | TBD
Top Risks | Mitigation Plan | Target Date

## Slide 6
Key Highlights | Sprint Planning Agreed and Completed​ Continuing to Deliver Axon configuration with National Grid structures such as organization, top level data domains, policies, regulations etc. Established regular “show and tell” sessions for steering group to drive business requirements
Last One Weeks Accomplished Tasks
Sprint 4 concluded with DG delivering 10 out of 12 (2 stories were added to sprint mid-stream w/o DG approval) Agreed scope for Sprint 5 and developed backlog for delivery of data glossary capability within Axon and EDC.
Next One Weeks Planned Tasks
First Steps loading 2 US Customer source systems (CRIS and CSS) into EDC Agree scope for MVP1 Data Governance Review Vishal’s stories and re-work into what makes sense knowing what we now know​ Create additional sprint user stories to cover unplanned activities, meetings, etc. (ongoing)​ Establish project support process for system issues​ (ongoing) Overviews & Meet & Greets for Newly Onboarded Resources Interviewing Candidates for Informatica Analyst and BA Roles Role descriptions diagram for Customer & Central Resource Structure Diagram
Squad Name – Data Governance | Lead : Diane LoPreste |  | 
Main Objectives: Creating data capability pillars by deploying a data management and governance enterprise solution framework & approach using Customer as the first MVP that provides a Data Catalog, Data Glossary, Data Quality, Critical Data and Authority & Control |  |  | Overall Status Green
Major Dependencies | Target Date | Status
Clarity on “training approach” and “route to production” from project team​ |  | Raised to Core Product Team to clarify - as JIRA stories to track progress
The governance tools require documenting outside of any temporary project structure provide future teams such as support an enduring record of what has been built, how it works, what the enterprise tool delivers etc. At present there is no “system owner“ to take on this responsibility |  | Raised to Core Product Team to resolve - as an issue 29th July 2021
There is an absence of a senior role to give direction, to ensure the expected business value is delivered and to drive Axon / EDC requirements. Without the roadmap, the team are left with no clear direction, requirements or confidence in the value of what is being delivered |  | Raised to Core Product Team to resolve - as an issue 29th July 2021
Resources | Date | Status
John Followell – Data Governance & Management Lead |  | Onboarded
Gavin Marshall – Informatica User Operating Model Lead |  | Onboarded
Morgan Reynolds – Data Governance & Management Analyst |  | Onboarded
Maryam Moshrefi – Reltio MDM Analyst |  | Onboarded
Apurba Sarkar – Reltio MDM Lead | 10/14 | Onboarded
Nishal Doctor - Informatica Business Systems Analyst (US) | 10/22 | Onboarded
Ramesh Govindan - Data Governance & Management Lead | 10/22 | Onboarded
Informatica Business Systems Analyst (UK) |  | Interviewing
MDM Principal Business Analyst |  | Open / Interviewing
Top issues | Mitigation Plan | Target Date
Finding Resources / Onboarding Timeline | Interviewing / Offers Made | Ongoing
Informatica Tool Precedence Axon vs. EDC | AI Working Group / Informatica | ~10/12/2021
The ‘Ops Model’ covering topics such as DGC ToRs has multiple, parallel teams working in isolation, e.g.,. CDT DG lead, DG team, Accenture on WDD | Reported to Core Product Team to Resolve | 
Top Risks | Mitigation Plan | Target Date
Axon/EDC – CDQ Interface |  | 
Upcoming Milestones | Planned Date | Revised Date | Status / Comments
Playback of sprint deliverables to steering group |  |  | In Progress

## Slide 7
Key Highlights | Akhilesh is onboarded. Started early draft of Core customer Logical Model. Completed enterprise data domains for Customer AMI subject area. Attended AMI PI planning
Last One Weeks Accomplished Tasks
Worked on Core customer Logical model and discussed some scenarios with SMEs. Worked with SMEs to gather the requirements for Products and services/CE/ZBR. Attended AMI PI planning sessions. Reviewed the L&G meter reading model and mapped model tables/attributes to the enterprise customer AMI subject area data domain.
Next One Weeks Planned Tasks
Multiple calls scheduled to discuss about Core customer use cases and requirements. Work on core customer logical data model. Continue to review the use cases for Core/CE/Products & services/ZBR. Continue analysis of MVP1 attributes. Continue to review the L&G meter reading model and mapping model tables/attributes to the Enterprise Customer AMI subject area data domain. Start early draft of Customer AMI/Meter profile data. Continue to work on Enterprise CDM data for Customer meter data.
Squad Name: Data Modeling | Lead : Maria Saiz |  | 
Main Objectives: Understand and confirm Core Customer requirements and work on Core customer data model. Understand the use cases for Products & services & ZBR/AMI. |  |  | Overall Status Green
Upcoming Milestones | Planned Start Date | Planned End Date | Revised End Date | Status / Comments
Major Dependencies | Target Date | Status
Analyze the data scope of MVP1 |  | Need Check with SMEs to get data scope of MVP1
Confirm core customer use cases with Business |  | Scheduled multiple meetings to discuss
Business needs to provide AMI user stories |  | Need to work with Business and Technical team.
Resources | Date | Status
Rajasheker Veikanula |  | Onboarded
Vidyadhar Jonnalagadda |  | Onboarded
Akhilesh Ghore |  | Onboarded
Top issues | Mitigation Plan | Target Date
Akhilesh has issue with VDI and other SWs |  | 
Team server access issue |  | 
Top Risks | Mitigation Plan | Target Date

## Slide 8: Action Log (Open Items)
Sl No | Area | Date | RAID | Description | Owner | Target End Date | Status | Remarks