## Slide 1: Workforce Data Domain Phase 2
Overview of Workstream

## Slide 2: Contents page
01 | Background | 03-04
02 | Vision and Benefits | 05-06
02 | High Level Plan | 07
03 | Team Structure | 08
04 | Governance | 09
05 | Risks | 10
06 | Key Actions/Next Steps | 16
07 | AOB | 17

## Slide 3: Workforce Data Landscape & Risks
Landscape
Workforce data is the most highly consumed data domain at National Grid
it is at the core of several key end-to-end business processes
we have over 120 downstream systems that utilise data stored in our workforce systems of record
there exists three systems of record - myHub EC (& onboarding), SAP ECC UK & SAP ECC US.
we also store data about UK MSP1 workers in the ACG2 database managed by Group IT.
we also store data about US MSP workers in SAP ECC US
we have 23,500 active employees, 1,350 active contingent workers and 9,000 active MSP workers
as a company, we must manage the identity data of all these workers to:
  allow safe and secure provisioning of access to our systems and premises
  on and off board workers
  deliver many HR functional processes to (mainly) employees.
1 Managed Service Provider (MSP)
2 Access Control Group (ACG)
3 Workforce Data Domain (WDD) - comprises all employees and non-employees (Contingent [Pontoon & Per-temp] & MSPs)
4 Integrated Access Management (IAM)
Risks
Complexity of myHub integrations with separate UK & US SAP instances is very high – it constrains myHub performance and adversely impacts downstream systems that utilize workforce data
downstream systems do not take data from the master source, myHub, rather, from a downstream source SAP
there exist no workforce Data Quality assessment & reporting capabilities
there is an insufficient governance and accountability for workforce data
a culture not enabled by good workforce data hygiene processes
a 2020 BCG study of all National Grid’s data domains estimate the costs of bad data are £60 – 81M
  assessment of WDD identified critical deficiencies which exposes us to security risks
  has already impacted our major programs
  necessitates costly manual efforts to deliver daily operational services.
there exists a massive gap in workforce data of ~9000 MSPs, circa £565M annual spend
  this segment of workforce data is maintained manually across multiple systems, processes and owners
  thus not enabling required levels of IAM4, among other controls processes

## Slide 4: Steps We’re Taking to Improve Workforce Data and Control Risks
Defined WDD Owner and governance framework supported by key enabling technology enabling culture of accountability
Automated Data Quality monitoring tools, reports and dashboards
  Will enable Process & Data Owners to proactively sustain the quality of data in their stewardship
Construct an Enterprise Data Platform, EDP (‘data warehouse’)
  We will feed updated workforce data into this platform
    Repository for other workforce data e.g. Sickness, Absence, Cases, Appreciate, Benefits, Sentiment
  Will be source of all workforce data for consumers & ‘downstream systems’ delivering an improved ecosystem of systems integrations
    Moves away from point-to-point integration which is costly, not scalable and constrains myHub
  Enabling greater self-service access to data, security and controls
    Applications, such as Power BI, used by HR and all BUs have access to workforce data
    More effective reporting solutions can be delivered by HR and Business Services vs. exclusively MyHub
Benefits
Cost and complexity of systems integrations reduced
IAM enabler
Improved IT Strategic Architecture built (EDP,MDM,DQ,APIs)
Data assurance, standards, procedures and controls built
Golden record and data models, data capability matured
Data quality is continuously measured and managed for 33k workers
WDD Project Ph II
EDP is an enterprise data platform (SnowFlake) cloud DB, a unifying storage for data mastered in many separate systems – often referred to as a ‘data warehouse’ or ‘data lake’
MDM is the master data management solution that delivers a unique worker id (‘Golden Record’) and supports IAM – supports Extract Transform Load (ETL) activities
DQ is data quality automated systems such as Informatica Cloud Data Quality, we feed in data, measure its quality and report and manage defects for data owners
APIs are application programming interfaces, the modern way to get data from source and import it into a target system
Shift focus to maintaining data holistically (and no longer as one-off efforts) through implementation of a sustainable data management framework across the entire employee and non-employee WDD and supporting business operations
Delivers improved accountability for data quality
Automated Data Quality monitoring and reporting tools
Consumers of data use consistent ‘key’ fields for all applications
IAM enabler
Global Worker Tracking 1
    Will feed updated Contingent and MSP worker data into EDP providing total workforce ecosystem
      Will enable critical process such as IAM
      Provide visibility of total workforce enabling WFP
Procurement System to manage all non-employee MSPs with supporting processes, data ownership and accountabilities
TOTEX of £2.6M
Interim Solution
Consolidates ACG & SAP MSP Data critical to IAM go live
Tactical MDM & Golden Record
Target Solution
Total workforce view available through EDP IAM enabler
Fieldglass Solution feed to EDP
TOTEX of £2.10M
1 Sanctioning paused amidst stretching priorities in the Procurement organization

## Slide 5: Vision
The vision is to….
Simplify, organise and clean our data landscape so we are able to speak a common language across the Workforce domain.
      Simplification, through data automation & integration.
      Provide a channel for workforce data to be consumed by dependant systems.
      Organisation, through a data operating model, governance & data culture.
      Driving data integrity, through enterprise tooling and insight

## Slide 6: Benefits
Reducing the cost of integrations
    We will implement an API layer to allow consumption of data from the EDP by trusted consumers.
    We avoid PTP, and reduce the costs and issues associated with PTP.
    We can also change our core workforce platforms more easily (myHR2.0).
      In recent times NG has written custom integrations to Poppulo and Industrial Training Services requiring substantial man hours (Appendix 5 Recent point to point integrations with myHub). We incentivise legacy PTP integration consumers to switch meaning we reduce the load on the ODS and reduce the impact of ODS change on them. Reduce the dependency on SAP platforms as integration sources (myHub (cloud), SAP ECC (on premise in UK and US) – this frees us up from a dependency on WIPRO to provide SAP CPI and SAP PI work packs.
Reducing the friction of data consumption
    We will publish trusted data assets in the EDP and permission our users to access the data pertinent to them. They can ingest this into their reporting tools.
    This moves us away from point to point reporting where reporting teams are often running the same report for different users.
    Consumers can get the right data faster be it for SOX internal controls, workflows (how well are HR processes working, auditing (which data points were edited by who and when).
    All our worker data will be in one place, supported by a data glossary and data governance – consumers are enabled to get the data they need when they want it.
Reducing Pain Points
    In Phase 1, we collated over 160 HR process pain points. 35 of these present an opportunity to improve – they require analysis, solutioning, potential change to our data operating model and potential change to our governance processes.
    The project will seek out priority data use cases for improvement such as the logistics of verifying report authenticity for SARBOX controls, to improving how we manage step progression data management, where this is not fully delivered by our existing platforms.
Deliver strategic Master Data Management
    We will create and persist a unique enterprise ID to support our target architecture of a platform for employees (myHub) and a platform for contractors and MSPs (GWT).
    This ID will be populated back into the worker systems of record and its particular benefit is around contractor to permanent conversions where the process will match and merge the 2 worker identities, meaning that a contractor to perm conversion does not lose their access on Friday and then raise multiple tickets on Monday to re-instate lost access
In

## Slide 7: WDD Architecture

## Slide 8: High Level Plan
Epics |  | Aug 21 |  | Sep 21 |  | Oct 21 |  | Nov 21 |  | Dec 1 |  | Jan 22 |  | Feb 22 |  | Mar 22 |  | Apr 22 | 
 | Sprints | 1 | 2 | 3 | 4 | 5 | 5 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Data Governance
Operating Model
Integration
Establish “As Is” & “To Be” HR
Op Data Model
Roles & Responsibilities Documented
WDD Data Vision & Roadmap Documented
Document Data Definitions & Quality
Requirements
Interaction Model Doc
Key Roles Identified and Trained
Regular Review & maintenance process
in place
Integration Requirements Documented
Communicate out Data Principles &
Standards in HR
Data Modelling
Data Modeling Signed off
Target Data Operating Model Implemented
MDM configuration /Source sys Integration
MDM – CDP Integration
Mulesoft API
Data Quality Self Service Set up
HR Data Forums
Implement Quick Process fix
Implement Data List in MyHUB
CDP Source Systems Integration
MVP1
MVP1
MVP1
MVP1
MVP1
MVP2
MVP2
MVP2
MVP2
MVP2
MVP3
MVP3
MVP3
MVP3
MVP3

## Slide 9
WDD DELIVERY SQUADS
+
+
COMMON COMPETENCY TEAM
WORKFORCE
DATA
DOMAIN
AGILE RELEASE TEAM
Juliette Trollope
HR Product Director
Shems Mohammed
Principle Solution Architect
Dan Senter
Data Lead
Sanjeev Kapoor
I & O Lead
Sam Read
Technology Risk Lead
Suky Muttoo
IT Commercial Lead
Basav Mahadevaiah
Security Lead
Dominic Hewitt
IT Finance Lead
Capgem TBC
Integration Consultants
Capgem TBC
Integration Analysts
SEM Alyson Jones
Capgem TBC
Data Modellers
Capgem TBC
Data Analysts
Capgem TBC
Data Consultants
Harsh Mundel
Lead Data Architect
Tolu Adeyanju “Customer Insights” / Data SME
Nishit Ajwaliya
Enterprise Information Architect
Capgem TBC
Testers x5
Tolu Adeyanju
Data Domain Owner
Emma Mease
Nicky Berry
SME (Design/ SIT/UAT))
Shalini Saxena
Solution Architect
Wipro TBC
Integration Dev
Wipro TBC
Tester #1
Sujata Goyal
SAP Integration
SEM
TBC
Fieldglass Func. Consultant
Andy Earnshaw
Environment & Config
TBC
Change & Readiness
TBC
Group People Analytics Data Specialist’
Gagendeep Singh
QES Test Lead
Kelly Britton
Part-Time PSO
Gavin Farrell
Project Manager
NG Business
NG IT
IT Partners
Programme Snr Leadership Team
KEY
Wipro TBC
Integration Developers
Wipro TBC
Testers
Anand Venkatapthi
SF Func Consultant
Wipro TBC
ABAP
Capgem TBC
Data Modellers/Engineers
Capgem TBC
Data Analysts
Capgem TBC
Data Consultants
Capgem TBC
Integration Analysts
Capgem TBC
Integration Architect & Consultants
TBC
Service Transition
Mandira Sen
Domain EA
Capgem TBC
Scrum Master
Capgem TBC
Testers
+ Potential need for multiple squads working in parallel to cover the scope in
this “workstream”
TBC
Integration Solution Architect
Andy Noton
IT Portfolio Del Mgr.
Andy Doyle Andi Karaboutis SteerCo
Gary Dionne
Business Lead
Lauren Van Der Kolk
Business Owner
Clare Mann
IT Sponsor
Capgem TBC
Data Modellers
Capgem TBC
Data Analysts
Capgem TBC
Data Consultants x2
Capgem TBC
Data Analysts Ofshore
x3
Melisa Nieforth
SME (Design/ SIT/UAT))
Vacancy
Product Manager
Sean MacAuley
ART Engineer
TBC
Agile Transformation Office SME
+ E.g. SAP Integration Dev Squad
Rohan Kapoor
IT HR Business Partner
TBC
Roles / Resources Not Yet Confirmed
Data Model & Integration Squads
Data Operating Model & Governance Squad
Shared
Scrum Master
Dan Senter
Head of Global
Data Governance
Role to oversee 2 projects
Vacancy
Business Programme Mgr. (TDA Role)
Kam Bharj
Data Governance Lead

## Slide 10: Governance
Meeting | Scope | Attendees | Frequency
Steerco | Programme Leadership will input a monthly status report via email and host a meeting as required to manage escalations. SteerCo members to cascade latest updates to their respective Functions and Programmes | Bala Lakshmanan Lauren Van Der Kolk Daniel Robertson Julie Shelvey Plus PMB | Monthly
PMB | Manage individual programme workstreams to plan and budget. Discuss and align on required escalations. Align on decisions for relevant design authority. | Rohan Kapoor Gary Dionne Bharat Tripathi Dan Senter Juliette Trollope Andy Noton (myHR2.0) Stuart Tomkinson Plus Workstream Lead Meeting | Fortnightly
Workstream Lead Meeting | Manage alignment and delivery of workstreams, including RAID | Gavin Farrell Alyson Jones Tolu Adeyanui Nishit Ajwaliya Kam Bharj Sujata Goyal | Weekly
Scrum | Provide update on progress and activities for coming day, including any blockers | Gavin Farrell Harsh Mundel / Shems Mohammed Tolu Adeyanui Nishit Ajwaliya Kam Bharj Sujata Goyal Capgemini Wipro QES | Daily

## Slide 11: Risks and Issues
Ref | Description | Score | Mitigation
1 | There is a risk that with current Covid Restrictions around travel and office working will impact timelines and schedule | 15 | Microsoft Teams will enable us to collaborate and communicate in a seamless way, with 3rd Party and National Grid teams. OneDrive for Business will help us share files and collaborate on documentation and looking at Microsoft Whiteboard to facilitate the agile approach
2 | There is a risk that there is going to be significant complexity in understanding the extent of the impact as a result of the design decisions made in moving to standard Position Management & Org Hierarchy. | 15 | Team working to ensure that the right people are going to be in the room to consider all likely impacts. In addition, formal ‘impact assessments’ will be mobilised as soon as possible and not idled until independent activities are completed.
3 | There is a risk that we are not aligned with other critical Projects e.g MyFinance | 12 | As part of MyHR work We have set up a ‘Dependencies’ workstream and this includes representatives from the major Programmes in our Governance Structure.
4 | There is a risk that we do not have leadership buy in to make decisions at appropriate time. | 15 | Currently working with key stakeholders and sponsorship to ensure each resource has delegated authority and a clear accountability in the final design. We will also ask the support of our SteerCo to ensure such stakeholders have the required delegated authority and clear communication channels to their respective Function / Business. Executive Steering Group in place.
5 | There is a risk that we are not transparent with the benefits and need to avoid any misrepresentation of the outcomes of this programme and the impacts on the end user or internal teams. Including the timing of when those outcomes will be achieved. | 12 | Need to be clear that the outcomes of this Programme are those anticipated post implementation phase. We are proposing an initial design phase to validate the achievability of those outcomes and therefore will limit any wider communications until the point at which our desired outcomes are validated.
6 | There is a risk that we do not have Critical resource from the Business at the implementation Phase | 15 | During the implementation phase, we must be fully transparent with our internal teams and end users for example, where a modified process will likely require an uplift in effort, we must communicate this and be transparent about the design principles which have caused it. Particularly US and UK HR Business Services for which we received their support on 3rd March (Tom LaVeck, Val Elliott and Julie Shelvey

## Slide 13: How WDD Improvements are Enabling Digital First Ambitions
Target State (FY23)
Future State (Q1 FY22)
Current State (Q4 FY21)
1 Extract Transform Load (ETL) is process of loading data into a data model where data often needs to be changed (transformed) to meet required use case
2 Structured Query Language (SQL) enables automation of database environment ETL processes
Automation and Self-service access to HR People Analytics being realized through a Power BI environment
HR Professionals and the Business are being provided unprecedented self-service access to HR data and insights
Complex, time and resource intensive analytics performed in Excel is being automated in a SQL server and Power BI Environment
  The way in which data is acquired for HR’s People Analytics BI environment will evolve from manual loads from myHub to automated loads from new EDP solution
Inaugural State (2020)
Automated SQL data extraction through EDP connection
Automated data extraction of other WF data; Sickness, Absence, Cases, Appreciate, Benefits, Sentiment & more through EDP
Automated data extraction of non-employee contingent / contractor worker (Pontoon & PerTemp) and MSPs data through EDP
SQL Automated point-to-point integration with myHub to extract data
Back end SQL2 Server Data Model
Automated ETL within SQL
Back end Excel Data Model
Manual ETL1
Manual Data mining from myHub by running reports
Manual data mining of other WF data from Appreciate database
Manual Data mining from myHub by running reports
Manual data mining of other WF data from Appreciate database
Manual data mining of other WF data from Appreciate, Sickness, databases
  Access to never before available data will eventually be delivered through EDP solution
  A Power BI solution connected to an EDP (data warehouse) is nimble and cost effective eliminating further investment in very costly myHub Workforce Analytics and Reporting modules
HR’s Power BI solution exemplifies how the other ~120 down stream system consumers of workforce data can interact with workforce data through the EDP solution
Access to non-employee contingent / contractor worker (Pontoon & PerTemp) data is through myHub
No Access to MSP worker data
End State
Transition State

## Slide 14: How WDD Improvements are Enabling Digital First Ambitions
IT’s IAM Project automating critical security and controls processes is being enabled by WDD Improvements
HR’s new DQ tools are assessing >800k HR data attributes weekly which has led to sustained >99% data accuracy across MyHub ‘golden record’/key fields essential to IAM go-live this spring
  HR’s new DQ expertise has enabled expansion of DQ assessments to include ACG and SAP MSP data which was a gap putting IAM project at risk
  Process and Data owners (UK & US Bus. Serv, & IT) are engaged and now proactively remediating data issues and/or process deficiencies which are causing them – this exemplifies the future approach to active DQ Management
  HR’s new manual DQ tools are being formalized and automated through WDD Project Ph II (cloud based tool called Infomatica) which will provide automated, real time monitoring for process & data owners
1 Extract Transform Load (ETL) is process of loading data into a data model where data often needs to be changed (transformed) to meet required configuration
2 Structured Query Language (SQL) enables automation of database environment
MyHR 2.0 ambitions will be supported by a new EDP eco-system
WDD will improve the way consumers of workforce data interact with HR systems for data by interacting with an EDP vs. point-to-point integration with MyHub
  Will reduce complexities introduced into MyHub required to accommodate downstream systems
  Potentially enable reduced integrations with SAP enabling more standard configurations of MyHub
    More complex data requirements of SAP could potentially be satisfied though MDM / ETL connectivity with EDP
Enabling greater self-service access to data, security and controls
  Improved reporting solutions can be delivered by HR and Business Services through EDP vs. by MyHub exclusively

## Slide 15: Workforce Data Ownership & Accountabilities
Workforce Data Domain Owner
Responsibility for the use of workforce data and a stake in ensuring that the data is properly defined and maintained throughout the domain. Is a leader in the overall HR function and has ultimate accountability for the quality of the data in their domain. As such, has ultimate authority for decisions relating to that data, including enforcement of and adherence to those decisions.
Data Owner
Responsibility for data within their own Process area. Have stake in ensuring that the data is fully functional and properly maintained throughout their Process Area as per the guidance of the Data Domain Owner. Are leaders responsible for resolving DQ issues.
Data Steward
Custodian of workforce data. Reporting to the Data Owner, the Data Steward is the main point of contact for data Users and Producers to resolve data issues in their function
Workforce Data Domain Governance and accountability for data quality is dependent upon certain data ownership roles and responsibilities
An HR Data Governance Council has been established – Aligned to existing Global Process Owners forum
WDD Project Ph II will establish a more senior Data Governance Council that looks across all Company Data Domains
  Establish data quality standards
  Deliver DQ measures and reporting to Data Owners and Data Stewards
  Administer statutory obligations e.g. GDPR Purge, Data Confidentiality, etc.
  Govern data use cases and reporting practices with decision making authority for data in their function in consultation with WDDO
  Monitor DQ reporting – Direct Data Steward data remediation activities
  Remediate Process deficiencies and/or champion Product Fixes of issues contributing to substandard DQ
  Monitor DQ reporting and proactively fix data that does not meet minimum standards