## Assumptions
Phase 1 Assumptions
Data Owners, etc are chargeable to the project

## Resource Chart Phase 1
|  |  |  | Months 1-3 |  |  |  | Months 4-6 |  |  |  | Months 7-9 |  |  |  | Months 10-12 |  |  |  | Months 13-15 |  |  |  | Months 16-18 |  |  |  | Months 19-21 |  |  |  | Months 22-24
|  |  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4 |  |  |  | Q5 |  |  |  | Q6 |  |  |  | Q7 |  |  |  | Q8
Area | Application | Role |  | NG Count | SI/SV Count | Total FTE Count |  | NG Count | SI/SV Count | Total FTE Count |  | NG Count | SI/SV Count | Total FTE Count |  | NG Count | SI/SV Count | Total FTE Count |  | NG Count | SI/SV Count | Total FTE Count |  | NG Count | SI/SV Count | Total FTE Count |  | NG Count | SI/SV Count | Total FTE Count |  | NG Count | SI/SV Count | Total FTE Count
| Persistent Customer ID | Scrum Master |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 0
|  | Business Analyst |  |  | 1 | 1 |  |  | 3 | 4 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  | 2 | 2 |  |  | 2 | 2 |  |  |  | 0
|  | Solution Architect |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  | 0.5 | 0.5 |  |  | 0.5 | 0.5 |  |  |  | 0
|  | Data Architect |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0
|  | Data Modeler |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Data Modeler |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Integration/DBA |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0
|  | Integration/DBA |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0
|  | Testing Lead |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0
|  | Testers |  |  |  | 0 |  |  | 1 | 1 |  |  | 3 | 3 |  |  | 3 | 3 |  |  |  | 0 |  |  | 4 | 4 |  |  | 4 | 4 |  |  |  | 0
|  | Data Qualtiy Analyst |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Data Analyst |  |  | 1 | 1 |  |  | 3 | 4 |  |  | 2 | 2 |  |  | 2 | 2 |  |  |  | 0 |  |  | 3 | 3 |  |  | 3 | 3 |  |  |  | 0
| Trusted Customer Data | Scrum Master |  | 1 |  | 1 |  | 1 |  | 2 |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Business Analyst |  |  | 3 | 3 |  |  | 3 | 6 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Solution Architect |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Data Architect |  |  | 1 | 1 |  |  | 1 | 2 |  |  | 1 | 1 |  |  | 2 | 2 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Integration/DBA |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Integration/DBA |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Testing Lead |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Testers |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Data Modeler |  |  | 1 | 1 |  |  | 1 | 2 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Data Modeler |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Data Qualtiy Analyst |  |  | 1 | 1 |  |  | 1 | 2 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Data Analyst |  |  | 1 | 1 |  |  | 1 | 2 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| MDM | Scrum Master |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 0 |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1
|  | Business Analyst |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 2 | 2 |  |  | 1 | 1 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1
|  | Solution Architect |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1
|  | Data Architect |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1
|  | Data Modeler |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Infrastructure Architect |  | 0.25 |  | 0.25 |  | 0.25 |  | 0.25 |  | 0.25 |  | 0.25 |  | 0.25 |  | 0.25 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Data Modeler |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1
|  | Integration/DBA |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1
|  | Testing Lead |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1
|  | Testers |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 2 | 2 |  |  | 1 | 1 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1
|  | Data Analyst |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 2 | 2 |  |  | 1 | 1 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1
|  | Data Quality Analyst |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1
|  | Data Analyst |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
| Single 360 Degree View | Scrum Master |  | 1 |  | 1 |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 0 |  |  |  | 0
|  | Business Analyst |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0
|  | Solution Architect |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Data Architect |  |  | 1 | 1 |  |  | 2 | 2 |  |  | 2 | 2 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0
|  | Data Modeler |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0
|  | Integration/DBA |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Testing Lead |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Testers |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0
|  | Data Qualtiy Analyst |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Data Analyst |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0
| Digitial Insights & | Scrum Master |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 1 |  | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 1 |  | 1
| Omni Channel Analytics | Business Analyst |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1
|  | Solution Architect |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Integration/DBA |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Integration/DBA |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  | 2 | 2 |  |  | 2 | 2
|  | Testing Lead |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1
|  | Testers |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 3 | 3 |  |  |  | 0 |  |  |  | 0 |  |  | 0.66667 | 0.66667 |  |  | 0.66667 | 0.66667
|  | Data Analyst |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 2 | 2 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Campaign Management | Scrum Master |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 1 |  | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Business Analyst |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0
|  | Data Architect |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0
|  | Data Modeler |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0
|  | Integration/DBA |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0
|  | Integration/DBA |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  | 1 | 1
|  | Testing Lead |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  | 1 | 1
|  | Testers |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 2 | 2 |  |  | 4 | 4 |  |  | 4 | 4 |  |  |  | 0 |  |  | 2 | 2
|  | Data Qualtiy Analyst |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0
|  | Data Analyst |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 2 | 2 |  |  | 3 | 3 |  |  | 3 | 3 |  |  |  | 0 |  |  |  | 0
| CSR Analytics and | Scrum Master |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1
| Optimization | Business Analyst |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1
|  | Data Architect |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Data Modeler |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Integration/DBA |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Integration/DBA |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 2 | 2 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Testers |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Data Qualtiy Analyst |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1
|  | Data Analyst |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1
| Actionable Insights | Business Analyst |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Testing Lead |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Testers |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  | 0.66667 | 0.66667 |  |  | 0.66667 | 0.66667
|  | Data Qualtiy Analyst |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Data Analyst |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1
| Situaltional Awareness | Testers |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  | 0.66667 | 0.66667 |  |  | 0.66667 | 0.66667
|  | Data Analyst |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 |  |  |  | 0 |  |  | 1 | 1 |  |  | 1 | 1
Shared Services
|  | Solution Architect |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  | 0 |  |  | 1 | 1 |  |  | 3 | 3 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 2 | 2
|  | Domain Architect |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
|  | Information Architect |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
|  | GSD Lead |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
|  | GSD Tech Lead |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
|  | IT Program Lead |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2
|  | Business Lead |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
|  | Data Governance Lead |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
|  | Project Lead |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1
|  | Business SME |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
|  | Data SME |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
| Change Management | Change Management Lead |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2
| Program | Change Leadership Lead |  | 1 |  | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1
|  | Communication Lead |  | 1 |  | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1
|  | Change Analyst |  |  | 1 | 1 |  | 0 | 1 | 1 |  | 0 | 1 | 1 |  | 0 | 1 | 1 |  | 0 | 1 | 1 |  | 0 | 1 | 1 |  | 0 | 1 | 1 |  | 0 | 1 | 1
| Epic | Stakeholder Engagment Analyst |  |  | 1 | 1 |  | 0 | 1 | 1 |  | 0 | 1 | 1 |  | 0 | 1 | 1 |  | 0 | 1 | 1 |  | 0 | 1 | 1 |  | 0 | 1 | 1 |  | 0 | 1 | 1
| Security | Corp Security Lead/Architect |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
|  | Corp Security Analyst |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2
Other
| Release Management | Release Train Engineer |  | 1 |  | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1
|  | Release Manager |  | 1 |  | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1
ox these | Business Readiness/ | Business Readiness Lead |  |  |  | 0 |  |  | 0 | 0 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1
| Training | Business Readiness Analyst |  |  |  | 0 |  |  | 0 | 0 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1
|  | Training Dev Analyst |  |  | 1 | 1 |  | 0 | 1 | 1 |  | 0 | 1 | 1 |  | 0 | 2 | 2 |  | 0 | 2 | 2 |  | 0 | 2 | 2 |  | 0 | 2 | 2 |  | 0 | 2 | 2
| Technical Support | Environment Manager |  | 1 |  | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1
| Dev Ops | Cloud Services Engineer Lead |  | 1 |  | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1
|  | DevOps Engineer Lead |  | 1 |  | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1 |  | 1 | 0 | 1
| Total |  |  | 22.25 | 32 | 54.25 |  | 22.25 | 42 | 74.25 |  | 24.25 | 42 | 66.25 |  | 26.25 | 69 | 95.25 |  | 24 | 51 | 75 |  | 23 | 41.5 | 64.5 |  | 24 | 39.5 | 63.5 |  | 24 | 34 | 58
| Offshore |  |  |  | 16 |  |  |  | 23 |  |  |  | 28 |  |  |  | 48 |  |  |  | 35 |  |  |  | 28 |  |  |  | 26 |  |  |  | 22
| Onshore |  |  |  | 16 |  |  |  | 19 |  |  |  | 14 |  |  |  | 21 |  |  |  | 16 |  |  |  | 13.5 |  |  |  | 13.5 |  |  |  | 12
Cost Breakdown
Quarterly Cost
|  | Estimate Yearly Cost |  |  |  | Cost per Quarter |  |  |  | Cost per Quarter |  |  |  | Cost per Quarter |  |  |  | Cost per Quarter |  |  |  | Cost per Quarter |  |  |  | Cost per Quarter |  |  |  | Cost per Quarter |  |  |  | Cost per Quarter |  | Breakdown by NG/SI
| Offshore Rate/Qtr | 67500 | 16875 |  |  | 270000 |  |  |  | 388125 |  |  |  | 472500 |  |  |  | 810000 |  |  |  | 590625 |  |  |  | 472500 |  |  |  | 438750 |  |  |  | 371250 |  | 3813750
| Onshore Rate/Qtr | 200000 | 50000 |  |  | 800000 |  |  |  | 950000 |  |  |  | 700000 |  |  |  | 1050000 |  |  |  | 800000 |  |  |  | 675000 |  |  |  | 675000 |  |  |  | 600000 |  | 6250000
| Onshore Rate/Qtr - NG | 200000 | 50000 |  |  | 1112500 |  |  |  | 1112500 |  |  |  | 1212500 |  |  |  | 1312500 |  |  |  | 1200000 |  |  |  | 1150000 |  |  |  | 1200000 |  |  |  | 1200000 |  | 9500000
| Total |  |  |  |  | 2182500 |  |  |  | 2450625 |  |  |  | 2385000 |  |  |  | 3172500 |  |  |  | 2590625 |  |  |  | 2297500 |  |  |  | 2313750 |  |  |  | 2171250
[18 empty] | 10190625 | [17 empty] | 19563750
CapEx/OpEx Estimate
| Category |  |  |  |  | CapEx/OpEx Estimate |  |  |  | CapEx/OpEx Estimate |  |  |  | CapEx/OpEx Estimate |  |  |  | CapEx/OpEx Estimate |  |  |  | CapEx/OpEx Estimate |  |  |  | CapEx/OpEx Estimate |  |  |  | CapEx/OpEx Estimate |  |  |  | CapEx/OpEx Estimate
NG OPEX
SI/SV OPEX Onshore
SI/SV OPEX Offshore
Total
|  |  |  | FY 2022 | TotEx | 2182500 |  |  |  | 2450625 |  |  |  | 2385000 |  |  |  | 3172500 |  | FY 2023 | TotEx | 2590625 |  | FY 2024 | TotEx | 2297500 |  | FY 2024 | TotEx | 2313750 |  | FY 2024 | TotEx | 2171250
[5 empty] | OpEx | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | OpEx | 0 |  |  | OpEx | 0 |  |  | OpEx | 0 |  |  | OpEx | 0
[5 empty] | CapEx | 2182500 |  |  |  | 2450625 |  |  |  | 2385000 |  |  |  | 3172500 |  |  | CapEx | 2590625 |  |  | CapEx | 2297500 |  |  | CapEx | 2313750 |  |  | CapEx | 2171250
Total Cost
[6 empty] | Cost Breakdown |  |  |  | Cost Breakdown |  |  |  | Cost Breakdown |  |  |  | Cost Breakdown |  |  |  | Cost Breakdown |  |  |  | Cost Breakdown |  |  |  | Cost Breakdown |  |  |  | Cost Breakdown |  | Breakdown
|  | Data Platform |  |  |  | 631250 |  |  |  | 915625 |  |  |  | 716250 |  |  |  | 984375 |  |  |  | 268125 |  |  |  | 393750 |  |  |  | 661875 |  |  |  | 268125 |  | 4839375
|  | Predictive Analytics |  |  |  | 234375 |  |  |  | 218125 |  |  |  | 234375 |  |  |  | 686875 |  |  |  | 520000 |  |  |  | 470000 |  |  |  | 61875 |  |  |  | 229375 |  | 2655000
|  | Trusted Data Program |  |  |  | 0 |  |  |  | 0 |  |  |  | 67500 |  |  |  | 67500 |  |  |  | 268750 |  |  |  | 0 |  |  |  | 156250 |  |  |  | 190000 |  | 750000
|  | PMO |  |  |  | 600000 |  |  |  | 600000 |  |  |  | 550000 |  |  |  | 600000 |  |  |  | 700000 |  |  |  | 600000 |  |  |  | 600000 |  |  |  | 650000 |  | 4900000
|  | Change Management/Business Readiness |  |  |  | 316875 |  |  |  | 316875 |  |  |  | 416875 |  |  |  | 433750 |  |  |  | 433750 |  |  |  | 433750 |  |  |  | 433750 |  |  |  | 433750 |  | 3219375
|  | Security |  |  |  | 150000 | 1066875 |  |  | 150000 | 1066875 |  |  | 150000 | 1116875 |  |  | 150000 | 1183750 |  |  | 150000 | 1283750 |  |  | 150000 | 1183750 |  |  | 150000 | 1183750 |  |  | 150000 | 1233750 | 9285625
|  | Release Management |  |  |  | 100000 |  |  |  | 100000 |  |  |  | 100000 |  |  |  | 100000 |  |  |  | 100000 |  |  |  | 100000 |  |  |  | 100000 |  |  |  | 100000 |  | 800000
|  | Dev/Ops (Tech Support) |  |  |  | 150000 | 250000 |  |  | 150000 | 250000 |  |  | 150000 | 250000 |  |  | 150000 | 250000 |  |  | 150000 | 250000 |  |  | 150000 | 250000 |  |  | 150000 | 250000 |  |  | 150000 | 250000 | 2950000
[6 empty] | 2182500 |  |  |  | 2450625 |  |  |  | 2385000 |  |  |  | 3172500 |  |  |  | 2590625 |  |  |  | 2297500 |  |  |  | 2313750 |  |  |  | 2171250 |  | 19563750

## Phase 1 Epics Top Sheet
Phase 1
|  |  |  | Foundations |  |  |  |  | Extend |  |  |  | Enhance | Enhance | Enhance | Enhance | Enhance | Enhance | Enhance | Optimize | Optimize | Optimize | Operationalize
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 21
|  |  |  | Build Foundational Data Elements (MDM, Trusted Data) | Build Foundational Data Elements (Insights / Analytics) | Enterprise Data Architecture Alignment | Implement Baseline Data Tools | Interim Persistent Key Capability | Extend Foundational Data Elements - Persistent Key | Extend Foundational Data Elements - Trusted Data | Extend Foundational Data Elements - MDM | Implement Enhanced Data Tools | Expand and Enhance Data Architecture Model | Build Initial Enhanced Data Capabilities (MDM, TD) | Build Initial Enhanced Data Capabilities (Analytics / Insights) | Expand and Enhance Tool Usage (MDM, Trusted Data) | Expand, Integrate and Enhance Tool Usage (Insights & Analytics) | Build Expanded Enhanced Data Capabilities | Build Initial Enhanced Customer Interaction Capabilities | Optimize Foundational Data Elements - Persistent Key | Optimize Foundational Data Elements - MDM | Build Expanded Enhanced Customer Interaction Capabilities | Operationalize Customer Interaction Capabilities & Automate Insights
Thread | Capability(L2) | Capability Details (L3) |  | 26 | 4 | 4 | 4 | 5 | 7 | 7 | 6 | 3 | 5 | 6 | 5 | 9 | 4 | 6 | 10 | 3 | 8 | 14 | 4
Persistent Key Identifier | Develop Persistent Key Identifier | Define the persistent Customer Identifier | 2 | bar: 1; 5
|  | Assess match potential across active Residential active/prospect/archived files | 2 | bar: 1; 5
|  | Assess match potential across active Commercial active/prospect/archived files | 1 | bar: 6
|  | Apply link across prospects and past customers | 2 | bar: 1; 5
|  | Define the approach for contacts vs. customers, and individuals vs. households for persistent management | 2 | bar: 1; 5
|  | Collaborate on MyAccount & Personalization engine data model design and marketing data model design | 2 | bar: 1; 5
|  | Define how CSS/CRIS or CRM overlay will manage Customer vs. Account views | 1 | bar: 1
| Integrate/ Append Persistent Key Identifier for Downstream applications | Apply Persistent Key (Residential) into CSS and CRIS | 1 | bar: 6
|  | Establish data hygiene change capture and tracing for Residential name/address hygiene actions | 1 | bar: 6
|  | Integrate persistent Key into MyAccount initiative (including Personalization and Preference center mgmt.) | 1 | bar: 6
|  | Build out MyAccount and preference two-way exchange for interim contact updates into CIAP and Marketing Cloud | 1 | bar: 6
|  | Enable Wave 1 new CIAP for Customer 360 using Customer Key (single view) | 1 | bar: 6
|  | Define the Bill/Pay Domain Data Capabilities - Data Matrix Wave 1 | 1 | bar: 6
|  | Define interim solution to support business roadmap | 1 | bar: 3
|  | Enable future CCAE - initial ad-hoc persistent key skip-trace analytics using | 1 | bar: 17
| Integrate Persistent Key Idnetifieer with Upstream appilications | Define universal validation for GF, GBE, InDemand, Vendor new customerss, establish master data design through Hub/MDM and external delta file (real -time processing | 1 | bar: 3
|  | Integrate into Campaign Mgmt environment (future Marketing Cloud) and all third-party contact and digital mechanisms for Residential customers | 1 | bar: 17
|  | Design C&I and third-party data management model, including roll-ups and management within CRM environment | 1 | bar: 17
|  | Integrate into future InDemand customer utilization and validation flows | 1 | bar: 19
|  | Utilize within streamlining and migration of all data mgmt platforms (mainframe, CDI, server) | 1 | bar: 19
|  | Roll-Out Commercial customers consistent with C&I Account and EE needs | 1 | bar: 19
Master Data Management | Establish the “Golden Record” and initial implementation​ | Establish a definition of a customer | 1 | bar: 1
|  | Establish a “Golden Record” for customer that contains with key data entities that should be part of a customer record and defined | 1 | bar: 1
|  | Define entity relationships (customer, premise, etc.) | 1 | bar: 1
|  | Assign teams who will be responsible for “Golden Record” | 1 | bar: 1
|  | Develop business rules to perform data profiling on key Customer MDM entities from CRIS & CSS | 1 | bar: 1
| Implement Master Data Management Tool | Determine architecture for Hub | 1 | bar: 3
|  | Implement initial release of Customer MDM with data from CRIS & CSS | 1 | bar: 4
|  | Establish manual/batch load to CIAP | 1 | bar: 4
|  | Establish basic maintenance processes & screens and security model | 1 | bar: 4
| Automate the integration of the customer “Golden Record”​ | Perform discrepancy analysis in accordance to customer definition between CSS and CRIS | 1 | bar: 8
|  | Establish MDM performance KPIs and SLAs | 1 | bar: 8
|  | Establishing entity relationships | 1 | bar: 8
|  | Synchronize broader governance and Customer MDM processes | 1 | bar: 8
|  | Implement workflow within MDM with the inclusion of business users | 1 | bar: 13
|  | Automate the integration of MDM solution to CIAP, GridForce, and CRM | 1 | bar: 13
|  | Enhance MDM Maintenance Screens & processes | 1 | bar: 13
|  | Establish MDM COE | 1 | bar: 13
| Enable end-to-end management of master data​ | Integrate MDM to all downstream applications | 1 | bar: 18
|  | Establish MDM Hub with data flowing bi-directionally, real-time, with relevant systems | 1 | bar: 18
|  | Implement front-end screens for more user management of the business rules | 1 | bar: 18
|  | Automate entity relationships | 1 | bar: 18
|  | Perform Discrepancy analysis in accordance to customer definition between customer data systems outside of CRIS and CSS | 1 | bar: 18
|  | Design the process for data profiling so that it is consistently performed and monitored | 1 | bar: 18
|  | Design the process for metadata management so that it is active for Customer definitions and accessible to business users | 1 | bar: 18
|  | Enhance and enrich data through the inclusion of 3rd party data | 1 | bar: 18
Trusted Customer Data | Data Governance Realignment | Fill open DG role Assignments | 1 | bar: 1
|  | Develop data governance operating charter and modify cadence | 1 | bar: 1
|  | Establish common terminology rolled out in a training curriculum for governance organizations and established for roles | 1 | bar: 1
|  | Define Role and Organizational RACI | 1 | bar: 1
|  | Define the operating model and council structure planned with tactical councils | 1 | bar: 1
| Initial Data Quality & Remediation | Identify critical data elements (CDE) with assigned ownership and stewardship | 1 | bar: 1
|  | Establish a common Data Quality tool | 1 | bar: 4
|  | Establish and prioritize remediation plans in joint effort with the business team for Data Quality Issues discovered during CDTA | 1 | bar: 1
|  | Define additional Business Rules for data with business Customer Data users | 1 | bar: 1
|  | Establish Customer metrics hierarchy and link to supporting data | 1 | bar: 1
|  | Establish common terminology rolled out in a training curriculum for governance organizations and established for roles | 1 | bar: 1
|  | Collect and SummarizeD Q issues established by business group | 1 | bar: 1
|  | Perform Column Based profiling | 1 | bar: 1
|  | Enable central control of processes and procedures for governance | 1 | bar: 1
| Enable enhancements of Trusted Customer Data elements | Build Metadata catalog | 1 | bar: 7
|  | Design Metadata management and supporting processes | 1 | bar: 7
|  | Assign Information Roles and Responsibilities to data and business team members | 1 | bar: 7
|  | Create Data Governance councils | 1 | bar: 7
|  | Create and communicate Principles for data management to the data governance councils | 1 | bar: 7
|  | Define and Establish the Data Governance Council cadence | 1 | bar: 7
Customer 360 | Refine NG Data Model | Refine Customer Data Model to support the unified data platform | 1 | bar: 1
|  | Refine Event entity in the data model | 1 | bar: 1
|  | Refine Agreement entity in the data model | 1 | bar: 7
|  | Refine Promotion/Ad entity in the data model | 1 | bar: 15
|  | Refine Survey Entity in the Data Model | 1 | bar: 15
|  | Refine Equipment Entity in the Data Model | 1 | bar: 15
|  | Refine Georgraphy Entity in the Data Model | 1 | bar: 19
| Build Foundational Analytics Environment | Build out detailed analytics use cases to validate prioritized business data capabilities | 2 | bar: 2; 10
|  | Complete Evaluation of tools required for the initial POC and plan for tools to support the broader data platform | 2 | bar: 2; 10
|  | Stand up initial Proof Of Concept technology platform, aligned to prioritized use case(s) | 1 | bar: 9
|  | Define and map initial metrics hierarchy to analytics | 1 | bar: 9
|  | Stand up small scale analytics POC with structured data from CRIS & CSS serving as the initial data source | 1 | bar: 14
|  | Utilize the defined business use cases and metrics to build initial analytics for 2-3 key business areas | 1 | bar: 14
| Build a pilot for the integrated view of the customer | Build an initial small scale Data platform Pilot from the POC | 1 | bar: 13
|  | Based on use case priorities, integrate, transform and enrich additional data sources (Salesforce, maximo, etc.) within the centralized data environment | 1 | bar: 13
|  | Design and build a consumption layer to access the unified customer view for an initial set of business functions eg (Marketing, Customer Billing, AMO,CSR) | 1 | bar: 13
|  | Integrate and expand the initial dashboards developed through the POC into dynamic analytics that incorporate newly ingested data sources | 1 | bar: 13
|  | Design and Build reports for the initial defined data metrics and scale across high priority areas of the customer domain | 1 | bar: 13
|  | Design and build enhanced data metrics reports to scale across entire customer domain | 2 | bar: 3; 21
Digital Insights and Omni Channel Analytics | Capture detailed digital data interactions​ | Create a detailed view of data currently captured from existing front digital interactions and where it is stored (Sprinklr, Kubra, PrefMgmt, Apps Insights, WebLogs) | 1 | bar: 11
|  | Perform a detailed assessment of the completeness of existing digital customer interaction data | 1 | bar: 12
|  | Identify detailed data flow gaps for existing front end applications | 1 | bar: 12
|  | Define required digital interaction data from the front end channel platforms including: • Digital log data • Web movement • Click tracking • Cookies • Web interaction data | 1 | bar: 12
|  | Define Interaction Domain Data Capabilities Wave 1 to caputre/manage/tag/llnk moments across channels by customer | 1 | bar: 8
| Link digital data interactions across customer lifecycle​ | Link the digital interaction data (digital data, campaign, change file, CSR session & vendor logs) between front end data sources (eg social, call center) | 1 | bar: 12
|  | Mapped customer journey experiential phases to the digital data interactions • Eg. prospect, acquire, service, nurture, retain to social, call center, IVR, mobile, MyAccount | 1 | bar: 12
|  | Identify detailed data flow gaps for existing front end applications | 1 | bar: 15
|  | Link existing customer tracking such as marketing communications (i.e. promote EasyBill programs) to new tracking / data log opportunities | 1 | bar: 21
Campaign Management | Setup and design of the intial CM data environment | Initial CM data environment design for email, text, phone, direct mail | 1 | bar: 11
|  | Design for integration of opt-out source files into CM data environment | 1 | bar: 11
|  | Design for integration of preferences and MyAccount contact coordination into CM environment | 1 | bar: 11
|  | Develop Services Domain Data Model Capabilities - Wave 2 to support self-service & click-through maketing to My Account | 1 | bar: 16
|  | Initial load and test of aggregate marketing data into CM environment | 1 | bar: 11
|  | Design and test of email links and cookie attribution | 1 | bar: 11
|  | Develop Product Domain Data Capabilities - Wave 1 to enable pipeline adoption anlaytics | 1 | bar: 9
| Launch of integrated CM environment for Systems of Record | Launch of integrated CM environment | 1 | bar: 14
|  | Build streamlined specification, creation, export, management campaign lists based on production-ready CM data set | 1 | bar: 14
|  | Design the process and build the Initial change data capture flows and data processing from SoRs (CSS, CRIS) | 1 | bar: 15
|  | Migrate best contact scoring functionality to be managed through logic within CM model, export of same to critical Systems of Insight | 1 | bar: 15
CSR Analytics and Optimization | Enrich baseline CSR measurements to incorporate 1st level outcomes​ | Design and Build enhanced call type analysis for core transactions based on System of Record transactional activity linked to call | 1 | bar: 16
|  | Initial modelling of call outcome/ success by call type* including completion and follow-up tracking across call and case logs | 1 | bar: 10
|  | Initial call deflection statistics enabled by digital channel (outbound and inbound) statistics vs. call center volumes by event or call type | 1 | bar: 16
|  | Initial call deflection statistics enabled by digital channel (outbound and inbound) statistics vs. call center volumes by event or call type | 1 | bar: 16
| Develop time-based analytics and propensities that support alternative treatments​ | Design and capture end-to-end call cycle and call handling details by call type based on total time engaged statistics (time on web, time in IVR queue, time on call) by call type | 1 | bar: 19
|  | Design and Build analytics to identify leading indicators of both end-to-end and CSR cycle times, leading to modeling of high/long vs. low/quick propensity callers in aggregate or by certain call types | 1 | bar: 19
|  | Design and Build analytics to support root cause analysis and experimental design for varying queue management and call treatments | 1 | bar: 21
Longitudinal Views /Actionable Insights | Define where and how longitudinal data can add value ​ | Design and Build a model factor environment for existing model: • Functional / analytical requirements • Data requirements • Triggering / workflow requirements | 2 | bar: 2; 10
|  | Capture initial data management capabilities to begin the logging and archiving of current history (relationship, journey moments, aggregate analytics, segmentation, NBA/PR) recommendations) and projections | 1 | bar: 16
|  | Design and Build initial change data capture filtering to minimize “noise” and unnecessary model updates based on out-of-bounds or missing data | 2 | bar: 16; 21
|  | Design and Build a data glossary of data to be loaded into longitudinal data environment | 1 | bar: 16
| Build the environment and define its use​ to provide value from the longituninal data | Rebuild longitudinal macro history based on relevant, feasible data | 1 | bar: 19
|  | Develop visual support and pattern analytics to support the business unit mapping of customer journey phases leading data and insights | 1 | bar: 19
|  | Build a prototyping environment where segmentation/treatment analytical and live testing can managed | 1 | bar: 19
|  | Design treatment-based business process workflow management so that decision trees and treatment steps can be modelled by business users | 1 | bar: 19
Situational Awareness | Identify data that details situational view of customer​ | Define data elements around situational awareness | 2 | bar: 2; 10
|  | Identify key systems that capture this data and validate/ensure the quality | 1 | bar: 16
|  | Define how CSS/CRIS/CRM will store this data and how it will be presented to CSR or in Digital Channel | 1 | bar: 16
|  | Develop Operational Domain Data Capabilities - Wave 2 to master SoR and CRM Situations and associated flows | 1 | bar: 8
|  | Identify mechanisms for triggering and maintaining active SA board | 1 | bar: 16
| Enhance Customer Experience through data capture​ | Deploy Initial Situational Awareness to CSRs through CRM overlay (basic situations i.e. Outage, Work Order Status, Application, Case) | 1 | bar: 19
|  | Define dynamic scripts for CSR as part of SA response | 1 | bar: 19
|  | Implement mechanisms for triggering and maintaining active SA board | 1 | bar: 19
|  | Establish key change data capture processes for triggering/intake/update of SA data -Eg. OMS/Maximo/Storms sends outage and work order status updates in real time -Eg. Customer information from CSS/CRIS | 1 | bar: 19
Note on Q44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: this is for internal crews only; manage 3rd paries in phase 2
Note on J91: Kerr, Katherine: add work order types for failure and tear-down that feed back to APM
Note on O91: Kerr, Katherine: add work order types for failure and tear-down that feed back to APM
Note on S91: Kerr, Katherine: add work order types for failure and tear-down that feed back to APM
Note on T91: Kerr, Katherine: add work order types for failure and tear-down that feed back to APM

## Phase 1 Epic 1
|  | Months | 0-6
|  |  | Build Foundational Data Elements (MDM, Trusted Data) | NG Count |  | SI Count
Thread | Capability(L2) | Capability Details (L3) | 0 | Product Owner | SME | Business Analyst | Data Architect | Data Modeler | Data Analyst | Data Qualtiy Analyst
|  | Total |  | 0.5 | 1 | 3 | 2 | 1 | 3 | 1
Persistent Key Identifier | Develop Persistent Key Identifier | Define the persistent Customer Identifier
Assess match potential across active Residential active/prospect/archived files
Apply link across prospects and past customers
Define the approach for contacts vs. customers, and individuals vs. households for persistent management
Collaborate on MyAccount & Personalization engine data model design and marketing data model design
Define how CSS/CRIS or CRM overlay will manage Customer vs. Account views
Master Data Management | Establish the “Golden Record” and initial implementation​ | Establish a definition of a customer
Establish a “Golden Record” for customer that contains with key data entities that should be part of a customer record and defined
Define entity relationships (customer, premise, etc.)
Assign teams who will be responsible for “Golden Record”
Develop business rules to perform data profiling on key Customer MDM entities from CRIS & CSS
Trusted Customer Data | Data Governance Realignment | Fill open DG role Assignments
Develop data governance operating charter and modify cadence
Establish common terminology rolled out in a training curriculum for governance organizations and established for roles
Define Role and Organizational RACI
Define the operating model and council structure planned with tactical councils
| Initial Data Quality & Remediation | Identify critical data elements (CDE) with assigned ownership and stewardship
Establish and prioritize remediation plans in joint effort with the business team for Data Quality Issues discovered during CDTA
Define additional Business Rules for data with business Customer Data users
Establish Customer metrics hierarchy and link to supporting data
Establish common terminology rolled out in a training curriculum for governance organizations and established for roles
Collect and SummarizeD Q issues established by business group
Perform Column Based profiling
Enable central control of processes and procedures for governance
Customer 360 | Refine NG Data Model | Refine Customer Data Model to support the unified data platform
Refine Event entity in the data model

## Phase 1 Epic 2
|  | Months | 1-6
|  |  | Build Foundational Data Elements (Insights / Analytics) | NG Count |  |  | SI Count
Thread | Capability(L2) | Capability Details (L3) | 0 | Product Owner | SME | Scrum Master | Business Analyst | Solution Architect | Data Architect | Integration/DBA | Testing Lead | Testers | Data Analyst
|  | Total |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Customer 360 | Build Foundational Analytics Environment | Build out detailed analytics use cases to validate prioritized business data capabilities
Complete Evaluation of tools required for the initial POC and plan for tools to support the broader data platform
Longitudinal Views /Actionable Insights | Define where and how longitudinal data can add value ​ | Design and Build a model factor environment for existing model: • Functional / analytical requirements • Data requirements • Triggering / workflow requirements
Situational Awareness | Identify data that details situational view of customer​ | Define data elements around situational awareness

## Phase 1 Epic 3
|  | Months | 4-6
|  |  | Enterprise Data Architecture Alignment | NG Count | SI Count
Thread | Capability(L2) | Capability Details (L3) | 0 | Product Owner | Business Analyst | Solution Architect | Data Architect | Integration/ DBA | Testing Lead | Testers | Data Analyst | Data Modeler
|  | Total |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Persistent Key Identifier | Integrate/ Append Persistent Key Identifier for Downstream applications | Define interim solution to support business roadmap
| Integrate Persistent Key Identifier with Upstream appilications | Define universal validation for GF, GBE, InDemand, Vendor new customerss, establish master data design through Hub/MDM and external delta file (real -time processing
Master Data Management | Implement Master Data Management Tool | Determine architecture for Hub
Customer 360 | Build a pilot for the integrated view of the customer | Design and build enhanced data metrics reports to scale across entire customer domain

## Phase 1 Epic 4
|  | Months | 2-6
|  |  | Implement Baseline Data Tools | NG Count |  | SI Count
Thread | Capability(L2) | Capability Details (L3) | 0 | Product Owner | Scrum Master | Business Analyst | Solution Architect | Data Architect | Integration/DBA | Testing Lead | Testers | Data Analyst
|  | Total |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Master Data Management | Implement Master Data Management Tool | Implement initial release of Customer MDM with data from CRIS & CSS
Establish manual/batch load to CIAP
Establish basic maintenance processes & screens and security model
Trusted Customer Data | Initial Data Quality & Remediation | Establish a common Data Quality tool

## Phase 1 Epic 5
|  | Months | 4-6
|  |  | Interim Persistent Key Capability | NG Count |  | SI Count
Thread | Capability(L2) | Capability Details (L3) | 0 | Product Owner | Scrum Master | Business Analyst | Solution Architect | Data Architect | Integration/DBA | Testing Lead | Testers | Data Analyst
|  | Total |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Persistent Key Identifier | Develop Persistent Key Identifier | Define the persistent Customer Identifier
Assess match potential across active Residential active/ prospect/archived files
Apply link across prospects and past customers
Define the approach for contacts vs. customers, and individuals vs. households for persistent management
Collaborate on MyAccount & Personalization engine data model design and marketing data model design
Enable Wave 1 new CIAP for Customer 360 using Customer Key (single view)
Define the Bill/Pay Domain Data Capabilities - Data Matrix Wave 1

## Phase 1 Epic 6
|  | Months | 7-12
|  |  | Extend Foundational Data Elements - Persistent Key | NG Count |  | SI Count
Thread | Capability(L2) | Capability Details (L3) | 0 | Product Owner | Scrum Master | Business Analyst | Solution Architect | Data Architect | Integration/ DBA | Testing Lead | Testers | Data Analyst | Data Qualtiy Analyst | Data Modeler
|  | Total |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Persistent Key Identifier | Develop Persistent Key Identifier | Assess match potential across active Commercial active/prospect/archived files |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1
| Integrate/ Append Persistent Key Identifier for Downstream applications | Apply Persistent Key (Residential) into CSS and CRIS
Establish data hygiene change capture and tracing for Residential name/address hygiene actions
Integrate persistent Key into MyAccount initiative (including Personalization and Preference center mgmt.)
Build out MyAccount and preference two-way exchange for interim contact updates into CIAP and Marketing Cloud
Enable Wave 1 new CIAP for Customer 360 using Customer Key (single view)
Define the Bill/Pay Domain Data Capabilities - Data Matrix Wave 1

## Phase 1 Epic 7
|  | Months | 7-12
|  |  | Extend Foundational Data Elements - MDM | NG Count | SI Count
Thread | Capability(L2) | Capability Details (L3) | 0 | Product Owner | Business Analyst | Solution Architect | Data Architect | Data Analyst | Data Qualtiy Analyst
|  | Total |  | 1 | 1 | 1 | 1 | 1 | 1
Trusted Customer Data | Enable enhancements of Trusted Customer Data elements | Build Metadata catalog |  |  | 1 | 1 | 1 | 2 | 1
Design Metadata management and supporting processes
Assign Information Roles and Responsibilities to data and business team members
Create Data Governance councils
Create and communicate Principles for data management to the data governance councils
Define and Establish the Data Governance Council cadence
Customer 360 | Refine NG Data Model | Refine Agreement entity in the data model

## Phase 1 Epic 8
|  | Months | 7-12
|  |  | Extend Foundational Data Elements - MDM | NG Count | SI Count
Thread | Capability(L2) | Capability Details (L3) | 0 | Product Owner | Business Analyst | Solution Architect | Data Architect | Integration/ DBA | Testing Lead | Testers | Data Analyst | Data Modeler
|  | Total |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Master Data Management | Automate the integration of the customer “Golden Record”​ | Perform discrepancy analysis in accordance to customer definition between CSS and CRIS |  |  | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1
Establish MDM performance KPIs and SLAs
Establishing entity relationships
Synchronize broader governance and Customer MDM processes
Digital Insights and Omni Channel Analytics | Capture detailed digital data interactions​ | Define Interaction Domain Data Capabilities Wave 1 to caputre/manage/tag/llnk moments across channels by customer
Situational Awareness | Identify data that details situational view of customer​ | Develop Operational Domain Data Capabilities - Wave 2 to master SoR and CRM Situations and associated flows

## Phase 1 Epic 9
|  | Months | 4-9
|  |  | Implement Enhanced Data Tools | NG Count | SI Count
Thread | Capability(L2) | Capability Details (L3) | 0 | Product Owner | Business Analyst | Solution Architect | Data Architect | Integration/DBA | Testing Lead | Data Analyst
|  | Total |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
Customer 360 | Build Foundational Analytics Environment | Stand up initial Proof Of Concept technology platform, aligned to prioritized use case(s) |  |  | 1 | 1 | 1 | 1 | 1 | 1
Define and map initial metrics hierarchy to analytics
Campaign Management | Setup and design of the intial CM data environment | Develop Product Domain Data Capabilities - Wave 1 to enable pipeline adoption anlaytics

## Phase 1 Epic 10
| Months | 7-12
|  |  | Expand and Enhance Data Architecture Model | NG Count |  | SI Count
Thread | Capability(L2) | Capability Details (L3) | 0 | Product Owner | Scrum Master | Business Analyst | Data Architect | Data Modeler | Integration/DBA | Testers | Data Analyst
|  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Customer 360 | Build Foundational Analytics Environment | Build out detailed analytics use cases to validate prioritized business data capabilities |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Complete Evaluation of tools required for the initial POC and plan for tools to support the broader data platform
CSR Analytics and Optimization | Enrich baseline CSR measurements to incorporate 1st level outcomes​ | Initial modelling of call outcome/ success by call type* including completion and follow-up tracking across call and case logs
Longitudinal Views /Actionable Insights | Define where and how longitudinal data can add value ​ | Design and Build a model factor environment for existing model: • Functional / analytical requirements • Data requirements • Triggering / workflow requirements
Situational Awareness | Identify data that details situational view of customer​ | Define data elements around situational awareness

## Phase 1 Epic 11
| Months | 10-18
|  |  | Build Initial Enhanced Data Capabilities (MDM, TD) | NG Count | SI Count
Thread | Capability(L2) | Capability Details (L3) | 0 | Product Owner | Business Analyst | Data Architect | Data Modeler | Integration/ DBA | Integration/ DBA | Testing Lead | Testers | Data Qualtiy Analyst | Data Analyst
|  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2
Digital Insights and Omni Channel Analytics | Capture detailed digital data interactions​ | Create a detailed view of data currently captured from existing front digital interactions and where it is stored (Sprinklr, Kubra, PrefMgmt, Apps Insights, WebLogs) |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2
Campaign Management | Setup and design of the intial CM data environment | Initial CM data environment design for email, text, phone, direct mail
Design for integration of opt-out source files into CM data environment
Design for integration of preferences and MyAccount contact coordination into CM environment
Initial load and test of aggregate marketing data into CM environment
Design and test of email links and cookie attribution

## Phase 1 Epic 12
|  | Months | 13-15
|  |  |  | Build Initial Enhanced Data Capabilities (Analytics / Insights) | NG Count |  | SI Count
Thread | Capability(L2) | Capability Details (L3) |  |  | Product Owner | Scrum Master | Business Analyst | Solution Architect | Integration/ DBA | Integration/ DBA | Testing Lead | Testers | Data Analyst
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2
Digital Insights and Omni Channel Analytics | Capture detailed digital data interactions​ | Perform a detailed assessment of the completeness of existing digital customer interaction data |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2
Identify detailed data flow gaps for existing front end applications
Define required digital interaction data from the front end channel platforms including: • Digital log data • Web movement • Click tracking • Cookies • Web interaction data
| Link digital data interactions across customer lifecycle​ | Link the digital interaction data (digital data, campaign, change file, CSR session & vendor logs) between front end data sources (eg social, call center)
Mapped customer journey experiential phases to the digital data interactions • Eg. prospect, acquire, service, nurture, retain to social, call center, IVR, mobile, MyAccount

## Phase 1 Epic 13
|  | Months | 10-15
|  |  |  | Expand and Enhance Tool Usage (MDM, Trusted Data) | NG Count |  | SI Count
Thread | Capability(L2) | Capability Details (L3) |  |  | Product Owner | Scrum Master | Business Analyst | Solution Architect | Data Architect | Integration/DBA | Integration/DBA | Testing Lead | Testers | Data Analyst
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1
Master Data Management | Automate the integration of the customer “Golden Record”​ | Implement workflow within MDM with the inclusion of business users |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1
Automate the integration of MDM solution to CIAP, GridForce, and CRM
Enhance MDM Maintenance Screens & processes
Establish MDM COE
Trusted Data | Build a pilot for the integrated view of the customer | Build an initial small scale Data platform Pilot from the POC
Based on use case priorities, integrate, transform and enrich additional data sources (Salesforce, maximo, etc.) within the centralized data environment
Design and build a consumption layer to access the unified customer view for an initial set of business functions eg (Marketing, Customer Billing, AMO,CSR)
Integrate and expand the initial dashboards developed through the POC into dynamic analytics that incorporate newly ingested data sources
Design and Build reports for the initial defined data metrics and scale across high priority areas of the customer domain
Trusted Customer Data | Data Governance Realignment | Fill open DG role Assignments
Develop data governance operating charter and modify cadence
Establish common terminology rolled out in a training curriculum for governance organizations and established for roles
Define Role and Organizational RACI
Define the operating model and council structure planned with tactical councils
| Initial Data Quality & Remediation | Identify critical data elements (CDE) with assigned ownership and stewardship
Establish a common Data Quality tool
Establish and prioritize remediation plans in joint effort with the business team for Data Quality Issues discovered during CDTA
Define additional Business Rules for data with business Customer Data users
Establish Customer metrics hierarchy and link to supporting data
Establish common terminology rolled out in a training curriculum for governance organizations and established for roles
Collect and SummarizeD Q issues established by business group
Perform Column Based profiling
Enable central control of processes and procedures for governance
| Enable enhancements of Trusted Customer Data elements | Build Metadata catalog
Design Metadata management and supporting processes
Assign Information Roles and Responsibilities to data and business team members
Create Data Governance councils
Create and communicate Principles for data management to the data governance councils
Define and Establish the Data Governance Council cadence
Customer 360 | Refine NG Data Model | Refine Customer Data Model to support the unified data platform
Refine Event entity in the data model
Refine Agreement entity in the data model
Refine Promotion/Ad entity in the data model
Refine Survey Entity in the Data Model
Refine Equipment Entity in the Data Model
Refine Georgraphy Entity in the Data Model
| Build Foundational Analytics Environment | Build out detailed analytics use cases to validate prioritized business data capabilities
Complete Evaluation of tools required for the initial POC and plan for tools to support the broader data platform
Stand up initial Proof Of Concept technology platform, aligned to prioritized use case(s)
Define and map initial metrics hierarchy to analytics
Stand up small scale analytics POC with structured data from CRIS & CSS serving as the initial data source
Utilize the defined business use cases and metrics to build initial analytics for 2-3 key business areas
| Build a pilot for the integrated view of the customer | Build an initial small scale Data platform Pilot from the POC
Based on use case priorities, integrate, transform and enrich additional data sources (Salesforce, maximo, etc.) within the centralized data environment
Design and build a consumption layer to access the unified customer view for an initial set of business functions eg (Marketing, Customer Billing, AMO,CSR)
Integrate and expand the initial dashboards developed through the POC into dynamic analytics that incorporate newly ingested data sources
Design and Build reports for the initial defined data metrics and scale across high priority areas of the customer domain
Design and build enhanced data metrics reports to scale across entire customer domain
Digital Insights and Omni Channel Analytics | Capture detailed digital data interactions​ | Create a detailed view of data currently captured from existing front digital interactions and where it is stored (Sprinklr, Kubra, PrefMgmt, Apps Insights, WebLogs)
Perform a detailed assessment of the completeness of existing digital customer interaction data
Identify detailed data flow gaps for existing front end applications
Define required digital interaction data from the front end channel platforms including: • Digital log data • Web movement • Click tracking • Cookies • Web interaction data
Define Interaction Domain Data Capabilities Wave 1 to caputre/manage/tag/llnk moments across channels by customer
| Link digital data interactions across customer lifecycle​ | Link the digital interaction data (digital data, campaign, change file, CSR session & vendor logs) between front end data sources (eg social, call center)
Mapped customer journey experiential phases to the digital data interactions • Eg. prospect, acquire, service, nurture, retain to social, call center, IVR, mobile, MyAccount
Identify detailed data flow gaps for existing front end applications
Link existing customer tracking such as marketing communications (i.e. promote EasyBill programs) to new tracking / data log opportunities
Campaign Management | Setup and design of the intial CM data environment | Initial CM data environment design for email, text, phone, direct mail
Design for integration of opt-out source files into CM data environment
Design for integration of preferences and MyAccount contact coordination into CM environment
Develop Services Domain Data Model Capabilities - Wave 2 to support self-service & click-through maketing to My Account
Initial load and test of aggregate marketing data into CM environment
Design and test of email links and cookie attribution
Develop Product Domain Data Capabilities - Wave 1 to enable pipeline adoption anlaytics
| Launch of integrated CM environment for Systems of Record | Launch of integrated CM environment
Build streamlined specification, creation, export, management campaign lists based on production-ready CM data set
Design the process and build the Initial change data capture flows and data processing from SoRs (CSS, CRIS)
Migrate best contact scoring functionality to be managed through logic within CM model, export of same to critical Systems of Insight
CSR Analytics and Optimization | Enrich baseline CSR measurements to incorporate 1st level outcomes​ | Design and Build enhanced call type analysis for core transactions based on System of Record transactional activity linked to call
Initial modelling of call outcome/ success by call type* including completion and follow-up tracking across call and case logs
Initial call deflection statistics enabled by digital channel (outbound and inbound) statistics vs. call center volumes by event or call type
Initial call deflection statistics enabled by digital channel (outbound and inbound) statistics vs. call center volumes by event or call type
| Develop time-based analytics and propensities that support alternative treatments​ | Design and capture end-to-end call cycle and call handling details by call type based on total time engaged statistics (time on web, time in IVR queue, time on call) by call type
Design and Build analytics to identify leading indicators of both end-to-end and CSR cycle times, leading to modeling of high/long vs. low/quick propensity callers in aggregate or by certain call types
Design and Build analytics to support root cause analysis and experimental design for varying queue management and call treatments
Longitudinal Views /Actionable Insights | Define where and how longitudinal data can add value ​ | Design and Build a model factor environment for existing model: • Functional / analytical requirements • Data requirements • Triggering / workflow requirements
Capture initial data management capabilities to begin the logging and archiving of current history (relationship, journey moments, aggregate analytics, segmentation, NBA/PR) recommendations) and projections
Design and Build initial change data capture filtering to minimize “noise” and unnecessary model updates based on out-of-bounds or missing data
Design and Build a data glossary of data to be loaded into longitudinal data environment
| Build the environment and define its use​ to provide value from the longituninal data | Rebuild longitudinal macro history based on relevant, feasible data
Develop visual support and pattern analytics to support the business unit mapping of customer journey phases leading data and insights
Build a prototyping environment where segmentation/treatment analytical and live testing can managed
Design treatment-based business process workflow management so that decision trees and treatment steps can be modelled by business users
Situational Awareness | Identify data that details situational view of customer​ | Define data elements around situational awareness
Identify key systems that capture this data and validate/ensure the quality
Define how CSS/CRIS/CRM will store this data and how it will be presented to CSR or in Digital Channel
Develop Operational Domain Data Capabilities - Wave 2 to master SoR and CRM Situations and associated flows
Identify mechanisms for triggering and maintaining active SA board
| Enhance Customer Experience through data capture​ | Deploy Initial Situational Awareness to CSRs through CRM overlay (basic situations i.e. Outage, Work Order Status, Application, Case)
Define dynamic scripts for CSR as part of SA response
Implement mechanisms for triggering and maintaining active SA board
Establish key change data capture processes for triggering/intake/update of SA data -Eg. OMS/Maximo/Storms sends outage and work order status updates in real time -Eg. Customer information from CSS/CRIS

## Phase 1 Epic 14
|  | Months | 13-18
|  |  |  | Expand, Integrate and Enhance Tool Usage (Insights & Analytics) | NG Count |  | SI Count
Thread | Capability(L2) | Capability Details (L3) |  |  | Product Owner | Scrum Master | Business Analyst | Solution Architect | Data Architect | Data Modeler | Integration/ DBA | Integration/ DBA | Testing Lead | Testers | Data Analyst
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2
Customer 360 | Build Foundational Analytics Environment | Stand up small scale analytics POC with structured data from CRIS & CSS serving as the initial data source |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2
Utilize the defined business use cases and metrics to build initial analytics for 2-3 key business areas
Campaign Management | Launch of integrated CM environment for Systems of Record | Launch of integrated CM environment
Build streamlined specification, creation, export, management campaign lists based on production-ready CM data set
Trusted Customer Data
Customer 360
Digital Insights and Omni Channel Analytics
Campaign Management
CSR Analytics and Optimization
Longitudinal Views /Actionable Insights
Situational Awareness

## Phase 1 Epic 15
|  | Months | 16-21
|  |  |  | Build Expanded Enhanced Data Capabilities | NG Count | SI Count
Thread | Capability(L2) | Capability Details (L3) |  |  | Product Owner | Business Analyst | Solution Architect | Data Architect | Integration/ DBA | Integration/ DBA | Testing Lead | Testers | Data Analyst
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
Customer 360 | Build Foundational Analytics Environment | Refine Promotion/Ad entity in the data model
Refine Survey Entity in the Data Model
Refine Equipment Entity in the Data Model
Digital Insights | Link digital data interactions across customer lifecycle​ | Identify detailed data flow gaps for existing front end applications
Campaign Management | Launch of integrated CM environment for Systems of Record | Design the process and build the Initial change data capture flows and data processing from SoRs (CSS, CRIS)
Migrate best contact scoring functionality to be managed through logic within CM model, export of same to critical Systems of Insight

## Phase 1 Epic 16
|  | Months | 13-15
|  |  |  | Build Initial Enhanced Customer Interaction Capabilities | NG Count |  | SI Count
Thread | Capability(L2) | Capability Details (L3) |  |  | Product Owner | Scrum Master | Business Analyst | Solution Architect | Data Architect/modeler | Integration/DBA | Integration/DBA | Testing Lead | Testers | Data Qualtiy Analyst | Data Analyst
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 1
Campaign Management | Setup and design of the intial CM data environment | Develop Services Domain Data Model Capabilities - Wave 2 to support self-service & click-through maketing to My Account |  |  |  | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 1
CSR Analytics and Optimization | Enrich baseline CSR measurements to incorporate 1st level outcomes​ | Design and Build enhanced call type analysis for core transactions based on System of Record transactional activity linked to call
Initial call deflection statistics enabled by digital channel (outbound and inbound) statistics vs. call center volumes by event or call type
Initial call deflection statistics enabled by digital channel (outbound and inbound) statistics vs. call center volumes by event or call type
Longitudinal Views /Actionable Insights | Define where and how longitudinal data can add value ​ | Capture initial data management capabilities to begin the logging and archiving of current history (relationship, journey moments, aggregate analytics, segmentation, NBA/PR) recommendations) and projections
Design and Build initial change data capture filtering to minimize “noise” and unnecessary model updates based on out-of-bounds or missing data
Design and Build a data glossary of data to be loaded into longitudinal data environment
Situational Awareness | Identify data that details situational view of customer​ | Identify key systems that capture this data and validate/ensure the quality
Define how CSS/CRIS/CRM will store this data and how it will be presented to CSR or in Digital Channel
Identify mechanisms for triggering and maintaining active SA board
Trusted Customer Data | Data Governance Realignment | Fill open DG role Assignments
Develop data governance operating charter and modify cadence
Establish common terminology rolled out in a training curriculum for governance organizations and established for roles
Define Role and Organizational RACI
Define the operating model and council structure planned with tactical councils
| Initial Data Quality & Remediation | Identify critical data elements (CDE) with assigned ownership and stewardship
Establish a common Data Quality tool
Establish and prioritize remediation plans in joint effort with the business team for Data Quality Issues discovered during CDTA
Define additional Business Rules for data with business Customer Data users
Establish Customer metrics hierarchy and link to supporting data
Establish common terminology rolled out in a training curriculum for governance organizations and established for roles
Collect and SummarizeD Q issues established by business group
Perform Column Based profiling
Enable central control of processes and procedures for governance
| Enable enhancements of Trusted Customer Data elements | Build Metadata catalog
Design Metadata management and supporting processes
Assign Information Roles and Responsibilities to data and business team members
Create Data Governance councils
Create and communicate Principles for data management to the data governance councils
Define and Establish the Data Governance Council cadence
Customer 360 | Refine NG Data Model | Refine Customer Data Model to support the unified data platform
Refine Event entity in the data model
Refine Agreement entity in the data model
Refine Promotion/Ad entity in the data model
Refine Survey Entity in the Data Model
Refine Equipment Entity in the Data Model
Refine Georgraphy Entity in the Data Model
| Build Foundational Analytics Environment | Build out detailed analytics use cases to validate prioritized business data capabilities
Complete Evaluation of tools required for the initial POC and plan for tools to support the broader data platform
Stand up initial Proof Of Concept technology platform, aligned to prioritized use case(s)
Define and map initial metrics hierarchy to analytics
Stand up small scale analytics POC with structured data from CRIS & CSS serving as the initial data source
Utilize the defined business use cases and metrics to build initial analytics for 2-3 key business areas
| Build a pilot for the integrated view of the customer | Build an initial small scale Data platform Pilot from the POC
Based on use case priorities, integrate, transform and enrich additional data sources (Salesforce, maximo, etc.) within the centralized data environment
Design and build a consumption layer to access the unified customer view for an initial set of business functions eg (Marketing, Customer Billing, AMO,CSR)
Integrate and expand the initial dashboards developed through the POC into dynamic analytics that incorporate newly ingested data sources
Design and Build reports for the initial defined data metrics and scale across high priority areas of the customer domain
Design and build enhanced data metrics reports to scale across entire customer domain
Digital Insights and Omni Channel Analytics | Capture detailed digital data interactions​ | Create a detailed view of data currently captured from existing front digital interactions and where it is stored (Sprinklr, Kubra, PrefMgmt, Apps Insights, WebLogs)
Perform a detailed assessment of the completeness of existing digital customer interaction data
Identify detailed data flow gaps for existing front end applications
Define required digital interaction data from the front end channel platforms including: • Digital log data • Web movement • Click tracking • Cookies • Web interaction data
Define Interaction Domain Data Capabilities Wave 1 to caputre/manage/tag/llnk moments across channels by customer
| Link digital data interactions across customer lifecycle​ | Link the digital interaction data (digital data, campaign, change file, CSR session & vendor logs) between front end data sources (eg social, call center)
Mapped customer journey experiential phases to the digital data interactions • Eg. prospect, acquire, service, nurture, retain to social, call center, IVR, mobile, MyAccount
Identify detailed data flow gaps for existing front end applications
Link existing customer tracking such as marketing communications (i.e. promote EasyBill programs) to new tracking / data log opportunities
Campaign Management | Setup and design of the intial CM data environment | Initial CM data environment design for email, text, phone, direct mail
Design for integration of opt-out source files into CM data environment
Design for integration of preferences and MyAccount contact coordination into CM environment
Develop Services Domain Data Model Capabilities - Wave 2 to support self-service & click-through maketing to My Account
Initial load and test of aggregate marketing data into CM environment
Design and test of email links and cookie attribution
Develop Product Domain Data Capabilities - Wave 1 to enable pipeline adoption anlaytics
| Launch of integrated CM environment for Systems of Record | Launch of integrated CM environment
Build streamlined specification, creation, export, management campaign lists based on production-ready CM data set
Design the process and build the Initial change data capture flows and data processing from SoRs (CSS, CRIS)
Migrate best contact scoring functionality to be managed through logic within CM model, export of same to critical Systems of Insight
CSR Analytics and Optimization | Enrich baseline CSR measurements to incorporate 1st level outcomes​ | Design and Build enhanced call type analysis for core transactions based on System of Record transactional activity linked to call
Initial modelling of call outcome/ success by call type* including completion and follow-up tracking across call and case logs
Initial call deflection statistics enabled by digital channel (outbound and inbound) statistics vs. call center volumes by event or call type
Initial call deflection statistics enabled by digital channel (outbound and inbound) statistics vs. call center volumes by event or call type
| Develop time-based analytics and propensities that support alternative treatments​ | Design and capture end-to-end call cycle and call handling details by call type based on total time engaged statistics (time on web, time in IVR queue, time on call) by call type
Design and Build analytics to identify leading indicators of both end-to-end and CSR cycle times, leading to modeling of high/long vs. low/quick propensity callers in aggregate or by certain call types
Design and Build analytics to support root cause analysis and experimental design for varying queue management and call treatments
Longitudinal Views /Actionable Insights | Define where and how longitudinal data can add value ​ | Design and Build a model factor environment for existing model: • Functional / analytical requirements • Data requirements • Triggering / workflow requirements
Capture initial data management capabilities to begin the logging and archiving of current history (relationship, journey moments, aggregate analytics, segmentation, NBA/PR) recommendations) and projections
Design and Build initial change data capture filtering to minimize “noise” and unnecessary model updates based on out-of-bounds or missing data
Design and Build a data glossary of data to be loaded into longitudinal data environment
| Build the environment and define its use​ to provide value from the longituninal data | Rebuild longitudinal macro history based on relevant, feasible data
Develop visual support and pattern analytics to support the business unit mapping of customer journey phases leading data and insights
Build a prototyping environment where segmentation/treatment analytical and live testing can managed
Design treatment-based business process workflow management so that decision trees and treatment steps can be modelled by business users
Situational Awareness | Identify data that details situational view of customer​ | Define data elements around situational awareness
Identify key systems that capture this data and validate/ensure the quality
Define how CSS/CRIS/CRM will store this data and how it will be presented to CSR or in Digital Channel
Develop Operational Domain Data Capabilities - Wave 2 to master SoR and CRM Situations and associated flows
Identify mechanisms for triggering and maintaining active SA board
| Enhance Customer Experience through data capture​ | Deploy Initial Situational Awareness to CSRs through CRM overlay (basic situations i.e. Outage, Work Order Status, Application, Case)
Define dynamic scripts for CSR as part of SA response
Implement mechanisms for triggering and maintaining active SA board
Establish key change data capture processes for triggering/intake/update of SA data -Eg. OMS/Maximo/Storms sends outage and work order status updates in real time -Eg. Customer information from CSS/CRIS

## Phase 1 Epic 17
|  | Months | 16-21
|  |  |  | Optimize Foundational Data Elements - Persistent Key | NG Count |  | SI/SV Count
Thread | Capability(L2) | Capability Details (L3) |  |  | Product Owner | Scrum Master | Business Analyst | Solution Architect | Integration/DBA | Integration/DBA | Testing Lead | Testers | Data Analyst
[5 empty] | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 2 | 1
Persistent Key Identifier | Integrate/ Append Persistent Key Identifier for Downstream applications | Enable future CCAE - initial ad-hoc persistent key skip-trace analytics using |  |  | 0.5 | 1 | 1 | 0.5 | 1 | 1 | 1 | 2 | 1
| Integrate Persistent Key Idnetifieer with Upstream appilications | Integrate into Campaign Mgmt environment (future Marketing Cloud) and all third-party contact and digital mechanisms for Residential customers
Design C&I and third-party data management model, including roll-ups and management within CRM environment

## Phase 1 Epic 18
|  | Months | 19-24
|  |  |  | Optimize Foundational Data Elements - MDM | NG Count |  | SI Count
Thread | Capability(L2) | Capability Details (L3) |  |  | Product Owner | Scrum Master | Business Analyst | Solution Architect | Data Architect | Data Modeler | Testing Lead | Testers | Data Analyst
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Master Data Management | Enable end-to-end management of master data​ | Integrate MDM to all downstream applications |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Establish MDM Hub with data flowing bi-directionally, real-time, with relevant systems
Implement front-end screens for more user management of the business rules
Automate entity relationships
Perform Discrepancy analysis in accordance to customer definition between customer data systems outside of CRIS and CSS
Design the process for data profiling so that it is consistently performed and monitored
Design the process for metadata management so that it is active for Customer definitions and accessible to business users
Enhance and enrich data through the inclusion of 3rd party data

## Phase 1 Epic 19
|  | Months | 19-24
|  |  |  | Build Expanded Enhanced Customer Interaction Capabilities | NG Count |  | SI/SV Count
Thread | Capability(L2) | Capability Details (L3) |  |  | Product Owner | Scrum Master | Business Analyst | Solution Architect | Integration/DBA | Testing Lead | Testers | Data Analyst
[5 empty] | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2
Persistent Key Identifier | Integrate Persistent Key Idnetifieer with Upstream appilications | Integrate into future InDemand customer utilization and validation flows |  |  | 0.5 | 1 | 1 | 1 | 2 | 1 | 2 | 2
Utilize within streamlining and migration of all data mgmt platforms (mainframe, CDI, server)
Roll-Out Commercial customers consistent with C&I Account and EE needs
Digital Insights and Omni Channel Analytics | Link digital data interactions across customer lifecycle​ | Link existing customer tracking such as marketing communications (i.e. promote EasyBill programs) to new tracking / data log opportunities
CSR Analytics and Optimization | Develop time-based analytics and propensities that support alternative treatments​ | Design and capture end-to-end call cycle and call handling details by call type based on total time engaged statistics (time on web, time in IVR queue, time on call) by call type
Design and Build analytics to identify leading indicators of both end-to-end and CSR cycle times, leading to modeling of high/long vs. low/quick propensity callers in aggregate or by certain call types
Design and Build analytics to support root cause analysis and experimental design for varying queue management and call treatments
Longitudinal Views /Actionable Insights | Build the environment and define its use​ to provide value from the longituninal data | Rebuild longitudinal macro history based on relevant, feasible data
Develop visual support and pattern analytics to support the business unit mapping of customer journey phases leading data and insights
Build a prototyping environment where segmentation/treatment analytical and live testing can managed
Design treatment-based business process workflow management so that decision trees and treatment steps can be modelled by business users
Situational Awareness | Enhance Customer Experience through data capture​ | Deploy Initial Situational Awareness to CSRs through CRM overlay (basic situations i.e. Outage, Work Order Status, Application, Case)
Define dynamic scripts for CSR as part of SA response
Implement mechanisms for triggering and maintaining active SA board
Establish key change data capture processes for triggering/intake/update of SA data -Eg. OMS/Maximo/Storms sends outage and work order status updates in real time -Eg. Customer information from CSS/CRIS

## Phase 1 Epic 21
|  | Months | 22-24
|  |  |  | Operationalize Customer Interaction Capabilities & Automate Insights | NG Count |  | SI/SV Count
Capability ID | Capability(L2) | Capability Details (L3) |  |  | Product Owner | Scrum Master | Business Analyst | Solution Architect | Integration/ DBA | Testing Lead | Testers | Data Qualtiy Analyst | Data Analyst
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1
Customer 360 | Build a pilot for the integrated view of the customer | Design and build enhanced data metrics reports to scale across entire customer domain |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1
Digital Insights and Omni Channel Analytics | Link digital data interactions across customer lifecycle​ | Link existing customer tracking such as marketing communications (i.e. promote EasyBill programs) to new tracking / data log opportunities
CSR Analytics and Optimization | Develop time-based analytics and propensities that support alternative treatments​ | Design and Build analytics to support root cause analysis and experimental design for varying queue management and call treatments
Longitudinal Views /Actionable Insights | Define where and how longitudinal data can add value ​ | Design and Build initial change data capture filtering to minimize “noise” and unnecessary model updates based on out-of-bounds or missing data
Trusted Customer Data
| Initial Data Quality & Remediation | Identify critical data elements (CDE) with assigned ownership and stewardship
Establish a common Data Quality tool
Establish and prioritize remediation plans in joint effort with the business team for Data Quality Issues discovered during CDTA
Define additional Business Rules for data with business Customer Data users
Establish Customer metrics hierarchy and link to supporting data
Establish common terminology rolled out in a training curriculum for governance organizations and established for roles
Collect and SummarizeD Q issues established by business group
Perform Column Based profiling
Enable central control of processes and procedures for governance
| Enable enhancements of Trusted Customer Data elements | Build Metadata catalog
Design Metadata management and supporting processes
Assign Information Roles and Responsibilities to data and business team members
Create Data Governance councils
Create and communicate Principles for data management to the data governance councils
Define and Establish the Data Governance Council cadence
Customer 360 | Refine NG Data Model | Refine Customer Data Model to support the unified data platform
Refine Event entity in the data model
Refine Agreement entity in the data model
Refine Promotion/Ad entity in the data model
Refine Survey Entity in the Data Model
Refine Equipment Entity in the Data Model
Refine Georgraphy Entity in the Data Model
| Build Foundational Analytics Environment | Build out detailed analytics use cases to validate prioritized business data capabilities
Complete Evaluation of tools required for the initial POC and plan for tools to support the broader data platform
Stand up initial Proof Of Concept technology platform, aligned to prioritized use case(s)
Define and map initial metrics hierarchy to analytics
Stand up small scale analytics POC with structured data from CRIS & CSS serving as the initial data source
Utilize the defined business use cases and metrics to build initial analytics for 2-3 key business areas
| Build a pilot for the integrated view of the customer | Build an initial small scale Data platform Pilot from the POC
Based on use case priorities, integrate, transform and enrich additional data sources (Salesforce, maximo, etc.) within the centralized data environment
Design and build a consumption layer to access the unified customer view for an initial set of business functions eg (Marketing, Customer Billing, AMO,CSR)
Integrate and expand the initial dashboards developed through the POC into dynamic analytics that incorporate newly ingested data sources
Design and Build reports for the initial defined data metrics and scale across high priority areas of the customer domain
Design and build enhanced data metrics reports to scale across entire customer domain
Digital Insights and Omni Channel Analytics | Capture detailed digital data interactions​ | Create a detailed view of data currently captured from existing front digital interactions and where it is stored (Sprinklr, Kubra, PrefMgmt, Apps Insights, WebLogs)
Perform a detailed assessment of the completeness of existing digital customer interaction data
Identify detailed data flow gaps for existing front end applications
Define required digital interaction data from the front end channel platforms including: • Digital log data • Web movement • Click tracking • Cookies • Web interaction data
Define Interaction Domain Data Capabilities Wave 1 to caputre/manage/tag/llnk moments across channels by customer
| Link digital data interactions across customer lifecycle​ | Link the digital interaction data (digital data, campaign, change file, CSR session & vendor logs) between front end data sources (eg social, call center)
Mapped customer journey experiential phases to the digital data interactions • Eg. prospect, acquire, service, nurture, retain to social, call center, IVR, mobile, MyAccount
Identify detailed data flow gaps for existing front end applications
Link existing customer tracking such as marketing communications (i.e. promote EasyBill programs) to new tracking / data log opportunities
Campaign Management | Setup and design of the intial CM data environment | Initial CM data environment design for email, text, phone, direct mail
Design for integration of opt-out source files into CM data environment
Design for integration of preferences and MyAccount contact coordination into CM environment
Develop Services Domain Data Model Capabilities - Wave 2 to support self-service & click-through maketing to My Account
Initial load and test of aggregate marketing data into CM environment
Design and test of email links and cookie attribution
Develop Product Domain Data Capabilities - Wave 1 to enable pipeline adoption anlaytics
| Launch of integrated CM environment for Systems of Record | Launch of integrated CM environment
Build streamlined specification, creation, export, management campaign lists based on production-ready CM data set
Design the process and build the Initial change data capture flows and data processing from SoRs (CSS, CRIS)
Migrate best contact scoring functionality to be managed through logic within CM model, export of same to critical Systems of Insight
CSR Analytics and Optimization | Enrich baseline CSR measurements to incorporate 1st level outcomes​ | Design and Build enhanced call type analysis for core transactions based on System of Record transactional activity linked to call
Initial modelling of call outcome/ success by call type* including completion and follow-up tracking across call and case logs
Initial call deflection statistics enabled by digital channel (outbound and inbound) statistics vs. call center volumes by event or call type
Initial call deflection statistics enabled by digital channel (outbound and inbound) statistics vs. call center volumes by event or call type
| Develop time-based analytics and propensities that support alternative treatments​ | Design and capture end-to-end call cycle and call handling details by call type based on total time engaged statistics (time on web, time in IVR queue, time on call) by call type
Design and Build analytics to identify leading indicators of both end-to-end and CSR cycle times, leading to modeling of high/long vs. low/quick propensity callers in aggregate or by certain call types
Design and Build analytics to support root cause analysis and experimental design for varying queue management and call treatments
Longitudinal Views /Actionable Insights | Define where and how longitudinal data can add value ​ | Design and Build a model factor environment for existing model: • Functional / analytical requirements • Data requirements • Triggering / workflow requirements
Capture initial data management capabilities to begin the logging and archiving of current history (relationship, journey moments, aggregate analytics, segmentation, NBA/PR) recommendations) and projections
Design and Build initial change data capture filtering to minimize “noise” and unnecessary model updates based on out-of-bounds or missing data
Design and Build a data glossary of data to be loaded into longitudinal data environment
| Build the environment and define its use​ to provide value from the longituninal data | Rebuild longitudinal macro history based on relevant, feasible data
Develop visual support and pattern analytics to support the business unit mapping of customer journey phases leading data and insights
Build a prototyping environment where segmentation/treatment analytical and live testing can managed
Design treatment-based business process workflow management so that decision trees and treatment steps can be modelled by business users
Situational Awareness | Identify data that details situational view of customer​ | Define data elements around situational awareness
Identify key systems that capture this data and validate/ensure the quality
Define how CSS/CRIS/CRM will store this data and how it will be presented to CSR or in Digital Channel
Develop Operational Domain Data Capabilities - Wave 2 to master SoR and CRM Situations and associated flows
Identify mechanisms for triggering and maintaining active SA board
| Enhance Customer Experience through data capture​ | Deploy Initial Situational Awareness to CSRs through CRM overlay (basic situations i.e. Outage, Work Order Status, Application, Case)
Define dynamic scripts for CSR as part of SA response
Implement mechanisms for triggering and maintaining active SA board
Establish key change data capture processes for triggering/intake/update of SA data -Eg. OMS/Maximo/Storms sends outage and work order status updates in real time -Eg. Customer information from CSS/CRIS