## Sheet1
|  | resources needed | risks
data model | conceptual is available |  |  | immediate
logical need to be developed
tool is available
Master Record
Data profiling | CDQ will be available in Jan |  | need to bring data into an environment for profiling - Snowflake will be available in Feb and data needs to be loaded here | March
CDC | complete design and architecture in jan for CDC (Joe, Bharat's tem, Sam, Joe) | IBM resources | Resource constraint with CSS expertise. | Feb
Data catalog
|  | Scope | Activities in 10 weeks starting Jan 18 | Comments | Owners | Cost
|  | Interim id | business rules |  | Alex | 120K | Bus resource
|  |  | Data model |  | Nishit/Bharat/Joe/Alex | ? | Bharat
|  |  | snowflake shld be available in |  | Bharat | 120K? | EA
|  |  | CDC Design |  | Ajwaliya/Bharat | ? | Diane
|  |  | Data catalog (lineage) | Ongoing | Alex/Diane
|  |  | understand UWP Design on persisitent |  | Nishit/Bharat/Joe
|  | Data quality | Bus rules
|  |  | Snowflake shld be available for staging data | Includes integrations
CDC Design for specfiic data
Data quality dashboards (Metrics)
Data clean up

## Sheet2
# | Scope | Activities in 10 weeks starting Jan 18 | Approximate Timeline | Comments | Owners | Support
1 | Interim Customer Persistent ID | Business requirements, rules and use cases | Jan-Feb -> Persistent ID Feb-March -> MDM/EDP |  | Alex
|  | Data Catalog and Data Lineage | Jan-Feb -> Data Catalog Feb-March -> Data Lineage | On going.Not directly related to Persistent ID | Alex, Diane, Maria, Bharat
|  | Data Model Using ERStudio (Conceptual, Logical) | Jan -> Persistent ID Jan-Feb -> Full |  | Indranil, Maria, Nishit | Joe, Alex
|  | CRIS and CSS Change Data Capture(CDC) | Jan -> Architecture and Design Feb -> Development (Persistent ID specific tables) March -> Additional Tables |  | Joe, Nishit, Bharat, IBM
|  | Design and Development (Snowflake) | Jan -> Understand Unified Portal Persistent ID solution Feb -> Standup Snowflake Feb -> Persistent ID Design March -> Start Persistent ID Development in Snowflake |  | Bharat | Joe, Fred W, Nishit
2 | Data Quality (DQ) | Business requirements, rules and use cases | Jan -> Entities and attributes for DQ Jan-Feb -> DQ requirements/rules/ user cases |  | Alex
|  | CRIS and CSS Change Data Capture(CDC) | Jan -> Architecture and Design Feb-March -> Development (DQ specific tables) March -> Additional Tables |  | Joe, Nishit, Bharat, IBM
|  | CRIS and CSS Data extract and Stage in Snowflake | Feb -> Standup Snowflake March -> Stage data in Snowflake |  | Bharat | Joe, Fred W, Joe
|  | Data quality dashboards (Metrics) | Jan -> Standup Informatica Cloud Data Quality (CDQ) March -> Data pofiling March??? -> Start building DQ dashboards and matrix reports |  | Bharat | Alex, Diane
|  | Data clean up in CRIS and CSS | Jan-March -> Address known data quality issues |  | Alex
3 | Data Governance | Setup Data Goveranace principles and processes |  |  | Diane
|  | Identify/setup Roles and Resposibilities |  |  | Diane

## Sheet3
# | Category | Scope Description | Data Tool Dependency
1 | Customer Data Modeling | Create Enterprise Customer Conceptual Data Model | Idera ERStudio
Create Customer Logical Conceptual Data Model
Create Physical Data Model
2 | Customer Data Catalog, Data Governance, Data Quality | Build Customer data catalog | Informatica EDC
|  | Setup Data Goveranace principles and processes | Informatica AXON
|  | Create standard and rules based Customer Data Quality Profiles | Informatica CDQ
Build Customer data quality reports and dashboards
3 | Customer Master Data Repository | Create Persistent Enterprise Customer ID | Reltio MDM Mulesoft Matillion
Migrate Persistent Customer ID from CXP Unified Customer Data
Build Customer Master data repository for the key golden record fields of entities like Account, Profile, Identifiers, Contact, Preference, Product etc.
Integrate with CRIS and CSS CDC Master tables
4 | Customer Enterprise Data Repository | Build Customer Cloud Data Repository for the key golden record of entities like Account, Profile, Identifiers, Contact, Preference, Product, Billing, Payment, Credit,Work Orders etc. | Snowflake Mulesoft Matillion
Integrate with Reltio MDM API for Customer Master Data
Integrate with CRIS and CSS CDC Transaction tables