## Slide 1
Data & Interfaces Approach
CRIS to CSS Migration Project
April 22, 2022

## Slide 2: Agenda
Project Goal & Objectives
Agile Process
Project Timeline
Data Conversion
  Conversion Approach
  Conversion Scope
  Conversion Scope Parameters
Interfaces
  Integration Approach
  Interface Grouping by Work Effort Type & Function
Global Technical Risks
Next Steps
Appendix
C2C Migration Project SharePoint Site: https://nationalgridplc.sharepoint.com/sites/GRP-PROJ-EXT-US-INV6434_CRIS_To_CSS

## Slide 3: Project Goal & Objectives
The purpose of the C2C migration project is the consolidation of the two CIS applications into a single one handling all companies.

## Slide 4: Using Agile to Build on Incremental Success
“New” CSS
Foundational
Reporting
Convert
Service-
Impacting
History
Post Received
Payments
Foundational
Customer
Letters
Foundation
Interfaces:
Meter Read,
Cash
Foundation
Financials
Bill
Most Common
Accounts
Foundation
Master Data
Configuration
Setup Batch
Comparison
Tool
Convert Core
Master Data
Foundational
Operation
Management
Most Common Rates
Bill All
Meter Types
Additional
Metered
Rates
Complete
Payment
Lifecycle
Bill Print
New
Customer
Setup
Foundation
Interfaces:
Field Activity
Convert
Billing-
Impacting
History
Non-Meter
Based
Billing
Non-Metered
Rates
Revenue
Assurance
Premise
Service
Customer
Self Service
Meter
Inventory
Management
Out-tier
Rates
Financials
Completion
Foundational
Collections
Epic 1: Foundational Data and Interfaces
Epic 2: Basic Meter-to-Cash
Epic 3: New Customers and Intermediate Billing
Epic 4: Revenue Assurance and Advanced Billing
Epic 5: Meter Management and Financial Completion

## Slide 5: Project Timeline

## Slide 6: Conversion Approach
A key goal of the data conversion effort is to leverage, whenever possible, the CRIS to CSS data conversion methodology, mapping, program code, and validation queries that were built as part of the 2014/2015 project that explored converting CRIS to CSS.
While the systems have both changed since then, that project had successfully executed a full-scale load of CRIS data into CSS and therefore it is expected that the 2014/2015 artifacts will be highly re-useable to cost-effectively accomplish the objectives of this current project.
CRIS companies will be utilizing CSS functionality with minimum exceptions and conversion team will be adopting the CSS way of working.
Link to D-6 Data Conversion Approach
D-6 Data Conversion Approach.docx

## Slide 7: Conversion Scope
This section provides the boundaries of the data conversion effort. The table below summarizes the information that will be converted and excluded as outlined in COA.
Data types from legacy to be converted | Customer Data Premise Data Meter Data Open Accounts Receivable Inventory Data Accounts Payable Data
Data types from legacy to be excluded | Closed Accounts Receivable (inactive accounts with zero balances) Accounts with zero balances will not be converted if the final bill is older than twelve (12) months Budget billing plan history Service orders and requests Workflow Items (“WFMs”)

## Slide 8: Conversion Scope Parameters
Data reconciliation will require resources with current source system(s) knowledge to perform validation of the converted data between Source and Target systems. The C2C Team will provide the queries and reports for the Target system outputs.
Data Conversion will include 3 years of operational data on the Go-Live Date.
This estimate includes 8 data conversion cycles in the project distributed as follows:
    Epic 1: Foundational Data and Interfaces - Data Migration -> Convert the Core Master Data
    Epic 2: Basic Meter to Cash - Data Migration -> Convert Service Impacting History
    Epic 3: New Customers and Intermediate Billing - Data Migration -> Convert Billing Impacting History
    Epic 4: Revenue Assurance and Advanced Billing - Data Migration -> Iterative mock conversions to refine process
    Epic 5: Meter Management and Financial Completion - Data Migration -> Iterative mock conversions to refine process
    Dress Rehearsal 1 Migration, including a Mock Conversion
    Dress Rehearsal 2 Migration, including a Mock Conversion
    Production Data Migration
The conversion (Automated Data cleansing, Extraction, Transformation, Load) Services are included in the scope of services.
Conversion scope will be driven by data identified as required for to operate CSS.
During Conversion for customers in CRIS there will be no customer matching. All CRIS customer will get new customer number in CSS.
Masking rules will be followed as per CRIS and CSS Process

## Slide 9: Integration Approach
The C2C migration project is not introducing any new architecture structures and the CSS technical architecture stays intact.
CRIS companies will be utilizing CSS functionality and interfaces with minimum exceptions. Therefore, the technical team is adopting the CSS way of working. Eventually, CRIS interfaces will be disabled and then removed/eliminated.
The C2C migration project team is responsible for, (with the coordination of the Data Center Migration project), the full-scale performance testing ensuring the enhanced CSS application environment and its interfaces can support the added volume of transactions, added data capacity, added user capacity, CSS-related on-line response time and batch performance.
Go Anywhere and MuleSoft are National Grid’s strategic partner and platform for designing, securing, deploying, and managing APIs and file transfer-based integrations, as well as driving reuse of Integration assets at a global scale. Wherever new internal and external interfaces with CSS are required for this project, the first choice for the design is to utilize these new patterns.
The C2C migration project is taking advantage of the interface improvements implemented by Project INVP 6523, (Go Anywhere and MuleSoft) hosted in the cloud.
The CSS application will be moved to upgraded Mainframe after the Data Center migration project.

## Slide 10: Interface Grouping by Work Effort Type & Function
Interface Groups | Interface Count | Batch | Real Time/MSG | Internal | External | Appendix
CRIS interfaces that can be migrated to the corresponding CSS interfaces with - NO modifications. * Transaction volume is expected to be increased. | 92 | 67 | 25 | 42 | 50 | B
CRIS interfaces that can be migrated to the corresponding CSS interfaces with modifications. * Transaction volume is expected to be increased. | 13 | 10 | 3 | 5 | 8 | C
CRIS interfaces to be migrated to work with CSS application, (no corresponding CSS interface) | 22 | 20 | 2 | 7 | 15 | D
CRIS interfaces no longer needed or applicable. | 1 |  |  |  |  | E
Interfaces under further validation/Investigation | 9 |  |  |  |  | A
Grand Total | 137 |  |  |  |  | 
Summary List of Project Interfaces:

## Slide 11: Interface Groupings
To be Migrated
MDSI (Advantex)
EBB
DIS - Distribution Information System
SPIPE
Broker Management (BMS)
Enernoc/ M2M
EnergyStar - EPA Portfolio Manager data
Marketer Billing System (MBS)
Broker Management (BMS)
UTX payments
Health and Human Services (HHS)
Human Resources Administration (HRA)
NY DSS County Web Portal
NYSERDA - Energy Affordability Customer Data
Stoner AKA Synergy
Boston Housing Authority
Boston University
City of Boston
Boston College
NYC Transportation Authority
NYC Housing Authority
NYC Municipal
To be Modified
CRIS Collection Agency Management
Field Selection Database - CWQ
Active Collections Call
Active Collections Letters (RUI)
FAD/CAP Agencies (MA)
SFDC CRM Order Management
GIS
Gas Transportation Information System (GTIS) - Imbalance Billing
Gas Transportation Information System (GTIS) / Transportation Services Applications (TSA)
Customer Directed Payments (CDP)
No Modifications (Follow CSS)
AIMS IVR
UWP
ESG – EDI
OPOWER
MA DOR
JP Morgan Chase
Pitney Bowes
Bill Print – RRD
CIAP
Striata
Fiserv
Honeywell
Itron FCS
Experian
++++ See Extended list on Appendix B

## Slide 12: Global Technical Risks
Risk # | Risk Title | C2C Team Owner | Risk Cause | Risk Detail | Risk Effect | Risk Score | Risk Status
1 | CSS Operational Batch Performance | Infrastructure | If the addition of the CRIS accounts creates unacceptable batch throughput performance levels | We may need to make major changes to the infrastructure, batch architecture and batch job schedule | this would increase the effort on the project and potentially delay the project go live | 14 | Open
4 | Mainframe Capacity Dev and Test | Infrastructure | If the current mainframe does not have capacity to support the Dev and Test environments for the initial launch | We may need to delay the launch of the program if we cannot find an alternate solution | this could delay the completion of the project beyond the business desired timeframe | 7 | Open
7 | GBE and C2C Timeline Conflicts | Customer Service | If the GBE and CRIS to CSS Migration program deliver significant changes to the same customer service groups in a short period of time | We may have a longer than normal call wait and call handle times for a more extended period of time | this could effect customer satisfaction and end user adoption | 25 | Open
8 | Business Staffing Support | PMO | If CSS staff are not available to be staffed on the project | The project may take longer to deliver its intended benefits | this could impact the costs and delivery schedule of the program | 14 | Open
9 | CRIS Data No Fit in CSS Model | Data Conversion | If the CRIS key entities cannot be mapped to the existing CSS data model | the data might be lost from CRIS | this could result in severe limitations on ability to serve these customers and potential fines from regulators in support of rate cases and litigation related to customers | 8 | Open
10 | Supplier Services EDI Transaction Solution | Billing | If the CSS support for Supplier Services does not meet the business needs | The process may need to be re-imagined to support all of the jurisdictions that NG delivers service | this could impact the costs and delivery schedule of the program | 6 | Open
13 | AGS Performance issues | Data Conversion | Potential capacity and contention for AGS | By adding additional accounts from CRIS, issues with AGS will be amplified hence need a action by program to mitigate and provide solution options for AGS | AGS performance will be impacted as volume of accounts are increased | 16 | Open
14 | Data Center Migration Timeline Dependency | PMO | C2C leadership has agreed that the final three months prior to go live should be spent testing in the new data center. If the Data Center Migration project is delayed, C2C entry into the new center may be delayed and this presents a risk to the C2C implementation schedule. | The data center move was originally scheduled for the summer of 2022. It was pushed back to early September of 2022 and the latest projections have it going in mid November of 2022. If this November date holds, there isn't three months available prior to the scheduled C2C production deployment on 1/17/2023. | The C2C team has options to pursue, including taking more risk by reducing the testing scope in the new data center, crashing the schedule to keep the scope of testing in the new DC the same while reducing the duration, or extending the project schedule to keep the 3 month baseline. | 36 | Open
C2C Global Risk Register: https://nationalgridplc.sharepoint.com/sites/GRP-PROJ-EXT-US-INV6434_CRIS_To_CSS/Lists/C2C%20RR

## Slide 13: NEXT STEPS
Schedule weekly calls with functional leads to discuss interfaces by functionality, (payload/data, design approach, transaction volumes, security, data transmission protocols, encryption, functional and performance testing).
Schedule initial call to discuss data strategy and data migration/mapping approach, data cleansing.
Continue with weekly calls to further present the design of the interfaces.
C2C Migration Project’s Jira Scrum Board: https://jira.us.ngridtools.com/secure/RapidBoard.jspa?rapidView=1565&view=planning.nodetail&issueLimit=100

## Slide 14
APPENDIX

## Slide 15: Appendix A: Interfaces Under Review
The following interfaces are under validation, further research and investigation.
Cash Receipts Data Entry Manager (cris iii) (1)
CDW CRIS Revenue and Statistics (1)
Edisim - TBD
Economic Incentive Rates (cris iii) (3)
Common Front End (CFE) (25)
Special Ledgers (CRIS) (1)
Summary Billing (CRIS) (5)
Transportation System (CRIS) (7)
Revenue & Statistics (TBD)

## Slide 16: APPENDIX B: Interfaces with No Modifications
Ref # | Category | Interface Name/Application | Description | Replaced by CIS Project? | Frequency | External Party Name | Internal or External
1 | Analytics | Customer Insights and Analytics (CIAP) | Sales & Marketing Group Data Mart (Usage, General Customer Info, Copies of Existing Billing Systems Data) | Replaced as Part of CIS Replacement Project | Weekly |  | Internal
2 | Analytics | Gas Load Forecasting | Usage and Customer Information Used by Advanced Analytics Group (ADA) | Survives CIS Replacement Project | Quarterly |  | Internal
3 | Analytics | CIAP on Tableau or Other Platform (Future) | Sales & Marketing Group Data Mart (Usage, General Customer Info, Copies of Existing Billing Systems Data) | Replaced as Part of CIS Replacement Project | Daily |  | Internal
4 | Analytics | CRIS Microstrategy Data Warehouse | Flattened Customer Information that is Financially Oriented for Revenue Accounting Reporting | Replaced as Part of CIS Replacement Project | Daily |  | Internal
205 |  | Energy Markets Web | This is the relatively new eCommerce web site which customers can interact with to purchase items such as thermostats. This does interface to the legacy CIS systems and will need to integrate with the new CIS. | Survives CIS Replacement Project | Real-Time | Customers | External
199 | Bill Presentment | Electronic Forms and Signature Tool 2 | Outbound Documents Repository (Signing Functionality) | Will be in Production Prior to CIS Replacement Project | Real-Time | FormAssembly | External
8 | Analytics | PageCenter | CSS and CRIS Report Distribution Tool | Survives CIS Replacement Project | Daily |  | Internal
197 | Customer Communication | Exposed Gas Shutoff Valve Alerts | Exposure of Gas Shutoff Valve Alerts or other value lifecycle alerts to channels | Survives CIS Replacement Project | Real-Time |  | Internal
10 | Analytics | Credit and Collections Analytics Engine (CCAE) | Credit Analytics Platform for Both CSS and CRIS - Supports Assignment of Accounts for Cut-Off, etc. - Operational System - Supported Directly by Business Customer, Service, and Balance Information | Survives CIS Replacement Project | Daily |  | Internal
11 | Analytics | Billing Operations MSSS | Commission Investigation Requests (Rate Case) Tracking; includes Distribution System Information | Survives CIS Replacement Project | Daily |  | Internal
12 | Analytics | Distributed Generation Business Objects | Used to Query Assets and Revenue information in STORMS (May Moving to Tableau for New England) | Survives CIS Replacement Project | Daily |  | Internal
196 | Distribution System Management | Itron Field Deployment Manager (Gas Shutoff Valves) | Receive and acknowledge information on new, changed, or removed Gas Shutoff Valves and the associated premises | Survives CIS Replacement Project | Real-Time |  | Internal
14 | Bill Presentment | Books for the Blind | Large Print Bills Raw Billing Data Provided | Interface is not Electronic Currently - Expected to be Electronic for CIS Replacement | Daily | Books for the Blind | External
15 | Bill Presentment | ISIS Papyrus | CRIS Letter Composition Software Package (to be Replaced by OpenText Exstream) | Will be Replaced Prior to CIS Replacement Project | Daily |  | Internal
16 | Bill Presentment | OpenText Exstream | Bill/Letter Composition Engine | Survives CIS Replacement Project | Daily |  | Internal
17 | Bill Presentment | Pitney Bowes EngageOne Vault | Bill Image Extract for CSS and CRIS | Survives CIS Replacement Project | Daily |  | Internal
18 | Bill Presentment | Pitney Bowes EngageOne Vault | Bill Image Repository | Survives CIS Replacement Project | Real-Time |  | Internal
195 | Distribution System Management | Itron MDM (SaaS) (Gas Shutoff Valve Alerts) | Receive and acknowledge Gas Shutoff Valve Alerts and other valve lifecycle alert messages, including low-battery and tampering messages | Survives CIS Replacement Project | Real-Time |  | Internal
20 | Bill Presentment | Fiserv | eBill and ePay Channel using Dedicated Inbound Payment Channel (Includes Bill Insert Schedule and URLs for Inclusion with eBills) | Survives CIS Replacement Project | Daily | Fiserv | External
21 | Bill Presentment | Striata Transactional E-Mail (eBill) | eBill and ePay Channel using Existing Western Union Inbound Payment Channel (Includes Bill Insert Schedule and URLs for Inclusion with eBills) | Survives CIS Replacement Project | Daily | Striata | External
22 | Bill Presentment | Bill Print | Various Files to Support Print and Mail Functions (Includes Bill Insert Schedule Information) | Survives CIS Replacement Project | Daily | Novitex | External
23 | Bill Presentment | Department of Army; AKA United States Army Corps | Outbound, Customer-Specific Bill Data Extract | Survives CIS Replacement Project | Daily | Department of Army; AKA United States Army Corps | External
188 | Measurement & AMI | Honeywell/ Metretek | Feeds Data for Billing and Daily Gas Nominations | Survives CIS Replacement Project | Daily |  | Internal
186 | Customer Choice | Community Choice Aggregation Reporting Portal | Portal to allow access to data related to community choice aggregation | Survives CIS Replacement Project | Daily |  | External
185 | Customer Choice | Community Choice Aggregation File Exchange | Various request records from aggregators and responses from National Grid | Survives CIS Replacement Project | Daily |  | External
184 | Measurement & AMI | Itron FCS | Itron Field Collection System - Usage Information for Gas and Non-AMI Electric | Survives CIS Replacement Project | Daily |  | Internal
183 | Billing | No Bill Data | Both CRIS and CSS Extracts providing data to NoBill Tools | Will be Made Redundant by CIS Replacement Project | Daily |  | Internal
182 | Billing | Timeliness Reporting of exceptions | Export of Exception Data Status | Will be Made Redundant by CIS Replacement Project | Daily |  | Internal
180 | Payments | Western Union Speedpay | Inbound Payments | Survives CIS Replacement Project | Daily | Western Union | External
31 | Payments | Customer Directed Payments (CDP) | Functionality to Provide Billing Information Spreadsheets to Customers with Multiple Accounts and to Accept Spreadsheets back with Payment Allocation Information Specified by Customers) | Survives CIS Replacement Project | Daily | various customers | External
179 | Payments | TransCentra | Lockbox Reversals (NSF) | Survives CIS Replacement Project | Daily | TransCentra | External
33 | Bill Presentment | Documentum | Document Images | Replaced as Part of CIS Replacement Project | Real-Time |  | Internal
34 | Bill Presentment | Electronic Forms and Signature Tool 1 | Outbound Documents Repository (Signing Functionality) | Will be in Production Prior to CIS Replacement Project | Real-Time | DocuSign | External
178 | Bill Presentment | Metrotech NGrid Office | Large Print Bills Raw Billing Data Provided | Interface is not Electronic Currently - Expected to be Electronic for CIS Replacement | Daily |  | External
177 | Credit & Collections | Liens/Legal Database | Database functionality for monitoring, letters, referral packets. Includes adding suspends to accounts as well as tracking of legal fees. Some work can take an extended period of time (years) before resolutions are reached. Should be included in the same way as Non-Utility Billing and Protections/Compliance within the document. | Replaced as Part of CIS Replacement Project | Near-Real Time |  | Internal

## Slide 17: APPENDIX B: Interfaces with No Modifications (Cont)
Ref # | Category | Interface Name/Application | Description | Replaced by CIS Project? | Frequency | External Party Name | Internal or External
37 | Billing | Degree Day Data | Degree Day/Temperature Data | Survives CIS Replacement Project | Daily | WSI | External
38 | Billing | Average Temperature Data | Temperature Data to Support Bill Print | Survives CIS Replacement Project | Daily | WSI | External
39 | Billing | Therm Factor Data | Calculation of Therm Factors values based on Mcf/dth values (Mcf = thousand cubic feet of gas; dth = dekatherm) | Survives CIS Replacement Project | Daily | WSI | External
176 | Credit & Collections | Protections/Compliance Database | Database functionality for monitoring, letters, certifications, agreements etc. Some examples include Life Support, Medical and Moratorium related work. Should be included in the same way as Non-Utility Billing within the document. | Replaced as Part of CIS Replacement Project | Near-Real Time |  | Internal
175 | Billing | Finalist | Support for CASS Processing | Will be Made Redundant by CIS Replacement Project | Daily |  | Internal
172 | Payments | Collection Agency Cash Files |  | Survives CIS Replacement Project | Daily | Multiple collection agency vendors | External
171 | Payments | PIMS | Payment Investigation Management System | Replaced as Part of CIS Replacement Project | Daily |  | Internal
170 | Payments | 820 Payments / Remittance Advises | Inbound 820 Payment / Remittance Advice Transactions | Survives CIS Replacement Project | Daily | Various Customers | External
168 | Payments | Fiserv | eBill and ePay - CSS and CRIS including payment channel | Survives CIS Replacement Project | Daily | Fiserv | External
167 | Payments | Western Union Walk-In Office | Payment Reversal Information | Survives CIS Replacement Project | Daily | Western Union | External
47 | Billing | Tax Exempt Vendor | New Designations to CIS of Tax Exempt Accounts | Survives CIS Replacement Project | Daily | Avalara | External
48 | Billing | Tax Exempt Vendor | Customer/Account Data on Accounts to Ensure that Certificates Exist to Support Confirmation/Reconciliation of Tax Exempt Customers | Survives CIS Replacement Project | Monthly | Avalara | External
49 | Billing | Tax Area Validation | Address and Tax Area Information (Future) | Will be in Production Prior to CIS Replacement Project | Monthly |  | Internal
50 | Billing | Mailstream | Support for Presort Accuracy, Validation, and Evaluation (PAVE™) Functionality | Survives CIS Replacement Project | Daily |  | Internal
51 | Billing | Code One | Support for Coding Accuracy Support System (CASS) Functionality | Survives CIS Replacement Project | Daily |  | Internal
52 | Billing | Verimove | Support for National Change of Address (NCOA) Functionality | Survives CIS Replacement Project | Daily | Verimove | External
53 | Billing | Mail 360 | Support for Barcoding Functionality | Survives CIS Replacement Project | Daily |  | Internal
54 | Billing | PLATTS | Daily Gas Market Pricing Provided by S&P Global Platts (Future) | Survives CIS Replacement Project | Daily | Platts | External
55 | Credit & Collections | Experian - Behavioral Scoring | Support for Active Collections Action Decision Model | Survives CIS Replacement Project | Daily | Experian | External
166 | Payments | Western Union Walk-In Office | Inbound Payments | Survives CIS Replacement Project | Daily | Western Union | External
165 | Payments | Western Union Speedpay | Western Union SpeedPay - IVR, Web, Mobile (Positive Payment Information) | Survives CIS Replacement Project | Daily | Western Union | External
164 | Payments | JPMorgan Chase | ACH Reversals (NSF) | Survives CIS Replacement Project | Daily | JPMorgan Chase | External
163 | Payments | JPMorgan Chase | ACH (Includes MyAccount and Direct Pay) | Survives CIS Replacement Project | Daily | JPMorgan Chase | External
162 | Payments | JPMorgan Chase eLockbox | Electronic Payments Management | Survives CIS Replacement Project | Daily | JPMorgan Chase | External
61 | Credit & Collections | Collections Data Warehouse for CRIS | Application with Data to Support Credit & Collections Analysis & Queries | Replaced as Part of CIS Replacement Project | Daily |  | Internal
161 | Payments | TransCentra | Lockbox for Mail-In Payments (Positive Payment Information) (Outbound) | Survives CIS Replacement Project | Daily | TransCentra | External
63 | Credit & Collections | Escheatment | Different by State - In-House Process | Survives CIS Replacement Project | Annually | States | External
64 | Credit & Collections | Replevin | Seize Assets (Meter) and Support of Access to Meter Processes | Replaced as Part of CIS Replacement Project | Daily | Schnieder Electric | External
160 | Payments | TransCentra | Lockbox for Mail-In Payments (Inbound) | Survives CIS Replacement Project | Daily | TransCentra | External
159 | Payments | One Step District Office Payments | Cashiering Solution (Downstate) | Survives CIS Replacement Project | Real-Time |  | Internal
67 | CRM | "GridForce" & DG SFDC | SFDC Functionality Separate from Gas Business Enablement SFDC Implementation to Support the Following Functions/Processes: 1. Gas Marketing 2. Tracking Energy Efficiency 3. Distributed Generation Connections 4. New Electric Connections (Workflow, Construction, etc.) 5. New Gas Connections (Workflow, Construction, etc.) 6. C&I customer management | Survives CIS Replacement Project | Real-Time | (Salesforce) | Internal
68 | CRM | SFDC CRM | GBE introduction of new CRM for Contact Center Handling Full Customer Interaction Including 360º View of Customer | Will be in Production Prior to CIS Replacement Project | Real-Time | (Salesforce) | Internal
158 | Payments | Collection Agency Inbound Payments | Inbound Payments From Collection Agencies | Survives CIS Replacement Project | Daily |  | Internal
141 | Meter Inventory Management | Maximo EAM | Meter and Equipment inventory Tracking (Replacing MITS Over Time) (Note: CIS project *may* have responsibility to replace MITS for meter classes not converted over already to Maximo) (Data Shared includes both Basic Meter Asset Information and Test Information) | Survives CIS Replacement Project | Real-Time |  | Internal
139 | Meter Inventory Management | Meter Inventory Tracking System (MITS) | Meter Inventory Tracking (Also Supports "Pick for Test" Process) (Data Shared includes both Basic Meter Asset Information and Test Information) | Survives CIS Replacement Project | Real-Time |  | Internal
72 | Customer Choice | ESG EDI Translator | Legacy Keyspan EDI transaction management | Survives CIS Replacement Project | Daily | ESG | External
130 | Financial / Accounting | SAP - General Ledger | General Ledger Interface | Survives CIS Replacement Project | Monthly |  | Internal
129 | Financial / Accounting | SAP - Outbound Payments | Supporting Payments for Credits Generated in CIS Made to Customers and Third Parties for Generation (RI Renewable Energy Growth Program, MA Smart Energy Solutions) (Specific Accounts Payable Interface) | Survives CIS Replacement Project | Daily |  | Internal
75 | Customer Communication | AIMS - CSR Interaction Recording (Voice, Screen, Data) | Phone Recording - eLoyalty | Survives CIS Replacement Project | Real-Time | eLoyalty | External
76 | Customer Communication | eLoyalty | New IVR implemented as part of AIMS effort | Survives CIS Replacement Project | Real-Time | eLoyalty | External
77 | Customer Communication | AIMS - Outbound Dialing | DAVOX replacement | Survives CIS Replacement Project | Real-Time |  | Internal

## Slide 18: APPENDIX B: Interfaces with No Modifications (Cont)
Ref # | Category | Interface Name/Application | Description | Replaced by CIS Project? | Frequency | External Party Name | Internal or External
77 | Customer Communication | AIMS - Outbound Dialing | DAVOX replacement | Survives CIS Replacement Project | Real-Time |  | Internal
78 | Customer Communication | Global Connect | Outbound Dialing (including appointment reminders) and Others (ad hoc) | Survives CIS Replacement Project | Real-Time | Global Connect | External
79 | Customer Communication | IQOR - meter replacement appointment set up | IQOR - meter replacement appointment set up | Survives CIS Replacement Project | Daily | IQOR | External
80 | Customer Communication | Verizon | Call Center Telephony | Survives CIS Replacement Project | Real-Time | Verizon | External
81 | Customer Communication | AIMS Verizon | IVR | Will be Replaced Prior to CIS Replacement Project | Real-Time | Avaya | External
82 | Customer Communication | Web Rates | Automated Feed to Display Information on the Web, Including Therm Factors, Pricing, etc. | Survives CIS Replacement Project | Daily |  | Internal
123 | Field Work | MAXIMO | Legacy Keyspan Long-Cycle Work Management Tool (Expected that Most Functions will be Migrated to Maximo Work Management (SaaS) (#120) but Some Need for Integration May Remain | Survives CIS Replacement Project | Real-Time |  | Internal
120 | Field Work | Maximo work management | Long Cycle Work Management (SaaS) for Gas Including Support for Processes such as Leak Management | Will be in Production Prior to CIS Replacement Project | Real-Time |  | Internal
116 | Field Work | FWEC | Repository for Field Service Exceptions for CRIS Premises / Accounts / Customers (from both Maximo and MDSI) | Will be Made Redundant by CIS Replacement Project | Daily |  | Internal
115 | Energy Affordability | LI-HEAP Agencies (RI) | Payment Data | Survives CIS Replacement Project | Daily | LI-HEAP Agencies (RI) | External
114 | Energy Affordability | LI-HEAP Agencies (RI) | Energy Affordability File Matching (Outbound - Billing and Customer Information; Inbound - Account Update) | Survives CIS Replacement Project | Daily | LI-HEAP Agencies (RI) | External
103 | Customer Validation | Real Time Address Validation | Via Experian QAS and Performed at Mailing Address Update | Survives CIS Replacement Project | Real-Time | Experian | External
90 | Customer Communication | oPower | Neighborhood Energy Efficiency Comparisons to Support Letters and On-Line Portal | Survives CIS Replacement Project | Daily | oPower | External
102 | Customer Validation | Experian - Positive ID and FACTA Identity Check | Identity Verification | Survives CIS Replacement Project | Real-Time | Experian | External
92 | Customer Communication | Energy Savvy | Weekly Customer & Daily Usage to Support EE and Energy Affordability Programs | Survives CIS Replacement Project | Weekly | Energy Savvy | External
93 | Customer Communication | RISE | Weekly Customer & Daily Usage to Support EE Programs | Survives CIS Replacement Project | Weekly | RISE | External
94 | Customer Communication | Arca | Customer & Daily Usage to Support EE Programs via Batch FTP | Survives CIS Replacement Project | Daily | Arca | External
 | Customer | UWP | UWP interface |  | Real Time |  | Internal

## Slide 19: APPENDIX C: Interfaces with Modifications
Ref # | Category | Interface Name/Application | Description
057 | Credit & Collections | CRIS Collection Agency Management | CRIS Collection Agency Management Tool
059 | Credit & Collections | Field Selection Database - CWQ | External Application to Prioritize and Choose Accounts to be Shut Off for Non-Pay; Also may be Used to Track Meter Periodic Testing Orders
062 | Credit & Collections | Active Collections Call | Account, Customer, Balance Information to Support Outbound Collections Calls
065 | Credit & Collections | Active Collections Letters (RUI) | Outbound Letters for Customers under Active Collections
113 | Energy Affordability | FAD/CAP Agencies (MA) | Outbound Billing and Customer Information for Good Neighbor Fund and Home Energy Assessment Processes
119 | Field Work | SFDC CRM Order Management | SFDC Mobile Work Order Management and Dispatch (Short Cycle)
131 | Geographic | GIS | Premise Information Synchronization
133 | Measurement & AMI | Gas Transportation Information System (GTIS) - Imbalance Billing | Transportation Billing and Imbalance Billing (Billing Determinants) Input
134 | Measurement & AMI | Gas Transportation Information System (GTIS) / Transportation Services Applications (TSA) | Eight Specific Gas Usage Values Exported Per Record
169 | Payments | Customer Directed Payments (CDP) | Inbound "Customer Directed Payment" Account Allocation Information
173 | Payments | Human Resources Administration (NYC HRA) Payment File | Payment information from NYC HRA Payment and Account Information
174 | Payments | Returned Items Notification | Returned Items Notification for Automated Payment Reversal
201 | Billing | Account Validation Database | Several Energy Efficiency vendors have implemented real time account validations (Helgeson, EFI, Simple Energy, Whisker Labs). Also some account validations as part of US Retail Web.

## Slide 20: APPENIDX D: CRIS Interfaces to be Migrated
Ref # | Category | Interface Name/Application | Description | Additional Notes | Directionality | Frequency | External Party Name) | Internal or External | 
204 | Other | EBB | Electronic Bulletin Board/Gas Transportation System - Internet application managing all gas supplies for LI and NY and RI citygate deliveries. Includes KeySpan gas supply, keySpan and LIPA generation. Additionally provides two way communication between KeySpan and suppliers for the Natural Choice program. Functions include deliver requirements, nomination and confirmation reconciliation and SCADA interface of deliveries. Used with CRIS III. | Verified with Sam Greco - There was a desire to replace EBB with a vendor solution but project never got funded. |  | Bidirectional | Real-Time | Gas Marketers | External
190 | Measurement & AMI | Broker Management (BMS) | Hourly Gas Reads Provided for Daily Nomination for NE | Daily Nomination Gas New England | To CIS | TBD |  | Internal | 
187 | Measurement & AMI | Enernoc/ M2M | Feeds Data for Billing Purposes & Support Temperature Control Gas Interruptions | Utilized for Large Commercial Gas Customers for KEDNY & KEDLI |  | To CIS | Monthly | Enel / Enernoc | External
149 | Other | EnergyStar - EPA Portfolio Manager data | Interface to National Load Information Service for Energy Efficiency Purposes | More research. Does this exist on the gas side? Michael E. conversation; Al Martinez is the contact person | Bidirectional | Daily | Schnieder Electric | External | 
136 | Measurement & AMI | Marketer Billing System (MBS) | Gas Usage Information | EDI Discussion/follow on session; does this application remain since it is part of the CRIS tech ecosystem? Alex and Bill Miles, Igor | From CIS | Daily |  | Internal | 
135 | Measurement & AMI | Broker Management (BMS) | Gas Usage Information | EDI Discussion/follow on session; does this application remain since it is part of the CRIS tech ecosystem? Alex and Bill Miles, Igor | From CIS | Daily |  | Internal | 
126 | Field Work | DIS - Distribution Information System | Repository for Gas Piping Information including Geographic Location & Size | Are the assets in DIS moving over to Maximo or will they stay in DIS in the near term? Need this business decision (this is SPIPE equivalent for NY); Need to talk with Alex Solovey | Bidirectional | Daily |  | Internal | 
125 | Field Work | SPIPE | Repository for Service Pipe and Gas Service Information | Are the assets in SPIPE moving over to Maximo or will they stay in SPIPE in the near term? Need this business decision (this is DIS equivalent for NE); Need to talk with Alex Solovey | From CIS | Daily |  | Internal | 
117 | Field Work | MDSI (Advantex) | Short-Cycle Work Management System for Legacy CRIS Premises and KEDLI Premises (Office Application = WinDisp; Field Application = MobilePenAppl) | Short Cycle Work Manager for CRS - Also for Downstate NY Gas and MA Gas and Moving to Maximo; Do we follow the GBE roadmap for transition? Nov/Dec 2021 for LI, but how is NYC going to be handled? Just go to Field Service Lightning or stay with MDSI? Follow up with GBE team and delivery managers | Bidirectional | Real-Time |  | Internal | 
112 | Energy Affordability | UTX payments | NY DSS County Payments | CSS doesn't currently interact with the same NY agencies as CRIS does | Bidirectional | Daily | NY Counties | External | 
111 | Energy Affordability | Health and Human Services (HHS) | NY OTDA Energy Affordability File Matching | CSS doesn't currently interact with the same NY agencies as CRIS does | Bidirectional | Monthly | Health and Human Services (HHS) | External | 
110 | Energy Affordability | Human Resources Administration (HRA) | NYC Energy Affordability File Matching & Winter Season Disconnects | CSS doesn't currently interact with the same NY agencies as CRIS does | Bidirectional | Monthly | Human Resources Administration (HRA) | External | 
109 | Energy Affordability | NY DSS County Web Portal | Web Portal for NY DSS Offices to Set Up and Maintain Assistance Grants to Energy Affordability Customers | CSS doesn't currently interact with the same NY agencies as CRIS does | Bidirectional | Daily | NY Counties | External | 
108 | Energy Affordability | NYSERDA - Energy Affordability Customer Data | Interface for Energy Affordability Customer Information | CSS doesn't currently interact with the same NY agencies as CRIS does | Bidirectional | Daily | NYSERDA | External | 
107 | Distribution System Management | Stoner AKA Synergy | Load-related Information for Brooklyn Union Gas (KEDNY) | Natan is not familiar with this one; does this exist for CRIS? James Steadman is the contact to confirm |  | From CIS | Daily |  | Internal
30 | Bill Presentment | Boston Housing Authority | Outbound, Customer-Specific Bill Data Extract |  | From CIS | Daily | Boston Housing Authority | External | 
29 | Bill Presentment | Boston University | Outbound, Customer-Specific Bill Data Extract |  | From CIS | Daily | Boston University | External | 
28 | Bill Presentment | City of Boston | Outbound, Customer-Specific Bill Data Extract | For street light billing | From CIS | Daily | City of Boston | External | 
27 | Bill Presentment | Boston College | Outbound, Customer-Specific Bill Data Extract |  | From CIS | Daily | Boston College | External | 
26 | Bill Presentment | NYC Transportation Authority | Outbound, Customer-Specific Bill Data Extract |  | From CIS | Monthly | NYC Transportation Authority | External | 
25 | Bill Presentment | NYC Housing Authority | Outbound, Customer-Specific Bill Data Extract |  | From CIS | Monthly | NYC Housing Authority | External | 
24 | Bill Presentment | NYC Municipal | Outbound, Customer-Specific Bill Data Extract |  | From CIS | Monthly | NYC Municipal | External | 

## Slide 21: APPENDIX E / Interface Not Needed
COUNT: 1 Interface
Category: Bill Presentment
Description: CAS Outbound Bill Extract Information for Specific (Large) Customers
Disposition: 01 - System/Function Not to be Replaced by Project and Requires Project Integration