## Test_plan
Task ID | Category | Dependency | Status | Task Description | Primary Task Owner | SecondaryTask Owner | Team | Role | Planned Start Date & Time | Planned End Date & Time | Actual Start Date | Actual End Date | Task Notes
1.1 | Pre-Requisites | Matillion team | Not Started | Python package for Azure and Snowflake | Howard Chen | Howard Chen | MDM | Data Architect
1.2 | Pre-Requisites | Azure team | Completed | Creating the Blob storage | Brian Owen | Brian Owen | Azure | Lead
1.3 | Pre-Requisites |  | Not Started | Configure Blob Storage in Matillion
1.4 | Pre-Requisites |  | Completed | Configure Blob Storage in Reltio
1.5 | Pre-Requisites | NA | Not Started | Matillion - Add the relevant roles in Snowflake with respect to loading data | Abhinav Singh | Abhinav Singh
1.6 | Pre-Requisites | NA | Completed | Configure Bitbucket for Snowflake | Prabhat Ghosh | Vipul Agrawal | MDM | Data Architect,Data Engineer | 2022-01-12 | 2022-01-13 | 2022-01-17 | 2022-01-17
1.7 | Pre-Requisites | NA | Completed | Configure Bitbucket for Matillion | Prabhat Ghosh | Vipul Agrawal | MDM | Data Architect,Data Engineer
1.8 | Pre-Requisites |  | Completed | Configure Bitbucket for Reltio | Prabhat Ghosh | Vipul Agrawal | MDM | Data Architect,Data Engineer
Snowflake Deployment
2.1 | Snowflake Deployment | NA | Not Started | Load DB Scripts to BitBucket Note: Include EDP MDM scripts | Prabhat Ghosh | Vipul Agrawal | MDM | Data Architect,Data Engineer
2.2 | Snowflake Deployment | NA | NA | Snowflake Team get the access to BitBucket Repo | Abhinav Singh | Abhinav Singh | Snowflake Team
2.3 | Snowflake Deployment | NA | Not Started | Snowflake Team get the code from BitBucket Repo | Abhinav Singh | Abhinav Singh | Snowflake Team
2.4 | Snowflake Deployment | Snowflake Team | Not Started | Snowflake team to create the database PROD_CDP_DB | Abhinav and Ranjith | Abhinav and Ranjith | Snowflake Team
2.5 | Snowflake Deployment | Snowflake Team | Not Started | Snowflake team to create the role snowflake role and AD role | Abhinav and Ranjith | Abhinav and Ranjith | Snowflake Team
2.6 | Snowflake Deployment | Snowflake Team | Not Started | Snowflake team to execute the master script.It will create Schema, Tables,View,Functions | Abhinav , Ranjith | Abhinav , Ranjith | Snowflake Team
2.7 | Snowflake Deployment | Snowflake Team | Not Started | snowflake to provide execution Log file to MDM team | Abhinav , Ranjith | Abhinav , Ranjith | Snowflake Team
2.8 | Snowflake Deployment | MDM Team | Not Started | MDM team to validate the deployment | Prabhat Ghosh | Varsha Gore | MDM
2.9 | Snowflake Deployment | Snowflake Team | Not Started | Snowflake Deployment Complete
2.10 | Snowflake Deployment | Snowflake team | Not Started | Drop MDM "*_Contact_*" tables/View | Abhinav , Ranjith, Nick | Abhinav , Ranjith, Nick | Snowflake Team
2.11 | Snowflake Deployment | Snowflake team | Not Started | Truncate all MDM tables | Abhinav , Ranjith, Nick | Abhinav , Ranjith, Nick | Snowflake Team
Matillion
3 | Pre-Requisites | MDM Team | Not Started | Export the job from Matillion Test into the Production |  |  | Matillion team
3.1 | Pre-Requisites | Matillion team | Not Started | CDP Project set up in Matillion |  |  | Matillion team
3.2 | Pre-Requisites | Matillion team | Not Started | setup Prod_MDM environment in Matillion |  |  | Matillion team
3.3 | Matillion Deployment | MDM Team | Not Started | Importing jobs into Matillion Prod from BitBucket | Prabhat Ghosh | Varsha Gore | MDM Team | Data Architect,Data Engineer
3.4 | Matillion Deployment | MDM Team | Not Started | JOB Variable Set Up | Prabhat Ghosh | Varsha Gore | MDM Team | Data Architect,Data Engineer
3.5 | Matillion Deployment | MDM Team | Not Started | Validate All the Pipeline if the JOB variable are set up correctly | Prabhat Ghosh | Varsha Gore | MDM Team | Data Architect,Data Engineer
3.6 | Data Loading into Reltio | 4.1 | Not Started | Execute JOB_MDM_CSS_Data_Load job | Prabhat Ghosh | Vipul Agrawal | MDM | Data Architect,Data Engineer
3.7 | Data Loading into Reltio | 3.6 | Not Started | Execute JOB_MDM_CRIS_Data_Load job | Varsha Gore | Bhuvan Chadha | MDM | Data Engineer
3.8 | Data Loading into Reltio | MDM Team | Not Started | CSS - Data load validation | Prabhat Ghosh | Vipul Agrawal | MDM | Data Architect,Data Engineer
3.9 | Data Loading into Reltio | MDM Team | Not Started | CRIS - Data load validation | Varsha Gore | Bhuvan Chadha | MDM | Data Engineer
3.10 | Data Loading into Reltio | MDM Team | Not Started | Schedule Pipilines | Prabhat Ghosh
3.11 | Data Loading into Reltio | MDM Team | Not Started | Handover to Support team | Prabhat Ghosh | Varsha Gore | MDM | Data Architect,Data Engineer
Reltio
4.1 | Reltio Deployment | MDM Team | Not Started | Export L3 Configuration from Reltio Test(EmL6I4K9rvSM4yF) and apply to Prod(fWsIw6uj4Cl0dOD) | Prabhat Ghosh | Prabhat Ghosh | MDM Team | Data Architect
4.2 | Reltio Deployment | MDM Team | Not Started | Export the Security Metadata Configuration from Reltio Test and apply to Prod(fWsIw6uj4Cl0dOD) | Prabhat Ghosh | Prabhat Ghosh | MDM Team | Data Architect
4.3 | Reltio Deployment | MDM Team | Not Started | Export UI configuration from Reltio Test and apply to Prod(fWsIw6uj4Cl0dOD) | Prabhat Ghosh | Prabhat Ghosh | MDM Team | Data Architect
4.4 | Reltio Deployment | MDM Team | Not Started | Export Lookups from RDM(U2UFtkyANia9nyU) and load into Bitbucket | Prabhat Ghosh | Prabhat Ghosh | MDM Team | Data Architect
4.5 | Reltio Deployment | MDM Team | Not Started | Change the Sequence generator before applying the L3 configuration into PROD(fWsIw6uj4Cl0dOD) | Prabhat Ghosh | Prabhat Ghosh | MDM Team | Data Architect
4.6 | Reltio Deployment | MDM Team | Not Started | Disable all the match rules in the L3 configuration. | Prabhat Ghosh | Prabhat Ghosh | MDM Team | Data Architect
4.7 | Reltio Deployment | MDM Team | Not Started | Create Reltio Support ticket to disable match and streaming, and provide support during data load | Prabhat Ghosh
4.8 |  |  | N/A | D&B Configuration
4.9 |  |  | N/A | Confirm Physical Tenant configuration (Note: for workforce UK Loquate needs to be enabled)
4.10 |  |  | Not Started | Customer roles and Groups
4.11 |  |  | N/A | Workflow export/import
4.12 | Reltio Deployment | MDM Team | Not Started | Import L3 latest configuration and apply into Prod (fWsIw6uj4Cl0dOD) | Prabhat Ghosh | Prabhat Ghosh | MDM Team | Data Architect
4.13 | Reltio Deployment | MDM Team | Not Started | Import Latest Security Metadata configuration and apply into Prod (fWsIw6uj4Cl0dOD) | Prabhat Ghosh | Prabhat Ghosh | MDM Team | Data Architect
4.14 | Reltio Deployment | MDM Team | Not Started | Import latest UI configuration and apply into Prod (fWsIw6uj4Cl0dOD) | Prabhat Ghosh | Prabhat Ghosh | MDM Team | Data Architect
4.15 | Reltio Deployment | MDM Team | Not Started | Import latest Lookup from RDM and apply into PROD (fWsIw6uj4Cl0dOD) | Prabhat Ghosh | Prabhat Ghosh | MDM Team | Data Architect
4.16 | Reltio Deployment | MDM Team | Not Started | Validate the changes by logging into Prod (fWsIw6uj4Cl0dOD) | Prabhat Ghosh | Prabhat Ghosh | MDM Team | Data Architect
4.17 | Data Loading into Reltio | 3.6 ,3.7 | Not Started | Once data load is completed(3.6 and 3.7) re_enable the match rule and apply the configuration rules | Prabhat Ghosh | Prabhat Ghosh | MDM Team | Data Architect
4.18 | Data Loading into Reltio | MDM Team | Not Started | Run the reindexing job in Reltio Prod | Prabhat Ghosh | Prabhat Ghosh | MDM Team | Data Architect
4.19 | Data Loading into Reltio | MDM Team | Not Started | Once the reindexing job is completed reconsolidate the records counts | Prabhat Ghosh | Prabhat Ghosh | MDM Team | Data Architect
4.20 |  | MDM Team | Not Started | Execute API to update Pipeline for Snowflake connector to include all new entities
4.21 |  | MDM Team | Not Started | Execute API to start Snowflake connector jobs
4.22 |  | MDM Team | Not Started | Once job complete, validate record counts in Snowflake
4.23 |  | MDM Team | Not Started | Create Business Friendly Views for Snowflake connector

## Production_Cutover_Plan
Task ID | Category | Tool | Resposible/Owner Team | Status | Task Description | Primary Task Owner | Time to complete (Hours) | Planned Start Date & Time | Planned End Date & Time | Actual Start Date | Actual End Date | Task Notes
Milestone 1 - Pre-deployment Starts
|  |  |  | Not Started | Production Cutover Kick-Off | MDM Team |  | 2022-03-28 08:00
| Pre-deployment | Matillion | Matillion team | Not Started | Install Python package for Azure and Snowflake | Howard Chen | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Snowflake | Snowflake Team | Not Started | Confirm Snowflake Service Account is created and MDM data load roles added to Snowflake service account for Matillion | Abhinav , Ranjith | 20 | 2022-03-28 09:00 | 2022-03-29 05:00
| Pre-deployment | Snowflake | Snowflake Team | Not Started | Receive the Snowflake service account Credentials (Private key and PassPhase) from Snowflake Admin team | Abhinav , Ranjith | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Matillion | MDM Team | Not Started | Configure Snowflake Connections from Python in Matillion | Prabhat Ghosh | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Matillion | MDM Team | Not Started | Configure Snowflake connection in Matillion | Prabhat Ghosh | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Azure | Azure team | Completed | Create Azure Blob Storage for Reltio | Brian Owen | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Azure | Azure team | Completed | Receive Azure Blob Storage connection detail for Matillion and Reltio | Brian Owen | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Matillion | MDM Team | Completed | Configure Azure Blob Storage in Matillion | Prabhat Ghosh | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Reltio | Reltio Team | Completed | Configure Azure Blob Storage in Reltio | Prabhat Ghosh | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-eployment | Azure | Azure team | Completed | Create Azure Service Bus for Reltio PROD | Brian Owen | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-eployment | Azure | Azure team | Completed | Receive Azure Service Bus connection detail for Reltio | Brian Owen | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-eployment | Reltio | Azure team | Completed | Configure Azure Service Bus in Reltio PROD | Prabhat Ghosh | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Bitbucket | MDM Team | Completed | Configure Bitbucket for Snowflake | Prabhat Ghosh | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Bitbucket | MDM Team | Completed | Configure Bitbucket for Matillion | Prabhat Ghosh | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Bitbucket | MDM Team | Completed | Configure Bitbucket for Reltio | Prabhat Ghosh | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Reltio | MDM Team | Completed | Create Reltio Client IDs working with Reltio support | Prabhat Ghosh | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Reltio | MDM Team | Completed | Get Reltio Integration Storage Account information for Reltio PROD Storage connector and share with NG Snowflake DBA | Nishit Ajwaliya | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Snowflake | Snowflake Team | Completed | Create Reltio Snowflake Connector database objects - Database, Schema, Role, Integration Storage, User | Ranjith | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Reltio | MDM Team | Completed | Create Reltio Snowflake Connector Account using Reltio Account API | Nishit Ajwaliya | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Reltio | MDM Team | Completed | Create Reltio Snowflake Connector Pipeline using Reltio Pipeline API | Nishit Ajwaliya | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Reltio | MDM Team | Completed | Create Reltio Snowflake Connector Batch Job using Reltio Job API | Nishit Ajwaliya | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Reltio | MDM Team | Completed | Once job ends, it should create tables and views for each Reltio entities and load Reltio Sample data | Nishit Ajwaliya | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Reltio | MDM Team | Completed | Validate Snowflake Objects and data for each entity | Nishit Ajwaliya | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Reltio | MDM Team | Completed | Snowflake Connector Configuration Complete | Nishit Ajwaliya | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Reltio | MDM Team | Not Started | Create Reltio Support Ticket to make changes in Reltio Physical configuration | Prabhat Ghosh | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Bitbucket | MDM Team | Not Started | Load Reltio metadata configuration ,RDM,Workflow into BitBucket Note: Include EDP MDM scripts | Prabhat Ghosh | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Bitbucket | MDM Team | Not Started | Load Matillion jobs and variables to BitBucket Note: Include EDP MDM scripts | Prabhat Ghosh | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Bitbucket | MDM Team | Not Started | Load DB Scripts to BitBucket Note: Include EDP MDM scripts | Prabhat Ghosh | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Bitbucket | MDM Team | Not Started | Load DB Scripts to BitBucket Note: Include EDP MDM scripts | Prabhat Ghosh | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment |  | MDM Team | Not Started | Send email to snowflake team to check the snowflake script details and be on standby | Prabhat Ghosh | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
| Pre-deployment | Snowflake/Reltio | Business Team | Not Started | Get List of Reltio and Snowflake initial Users and | Vishal P/Mike D | 5 | 2022-03-28 09:00 | 2022-03-28 14:00
Milestone 1 - Pre-deployment Ends
Milestone 2 - Code Deployment Starts
| Snowflake Deployment | Reltio | Business Team | Not Started | Get Green Light to move forward | Vishal P/Mike D | 1 | 2022-03-28 13:00 | 2022-03-28 14:00
| Snowflake Deployment | Snowflake | MDM Team | Not Started | Send email to Snowflake team to start deployment | Prabhat Ghosh | 6 | 2022-03-28 13:00 | 2022-03-28 19:00
| Snowflake Deployment | Bitbucket | Snowflake Team | Not Started | Snowflake Team to get Snowflake Scripts from BitBucket Repository (Other option - MDM team provides scripts to Snowflake team) | Abhinav , Ranjith | 6 | 2022-03-28 13:00 | 2022-03-28 19:00
| Snowflake Deployment | Snowflake | Snowflake Team | Not Started | Snowflake team to create the database PROD_CDP_DB | Abhinav , Ranjith | 6 | 2022-03-28 13:00 | 2022-03-28 19:00
| Snowflake Deployment | Snowflake | Snowflake Team | Not Started | Snowflake team to create the role snowflake role and AD role | Abhinav , Ranjith | 6 | 2022-03-28 13:00 | 2022-03-28 19:00
| Snowflake Deployment | Snowflake | Snowflake Team | Not Started | Snowflake team to execute the master script that creates Schema, Tables, View, Functions | Abhinav , Ranjith | 6 | 2022-03-28 13:00 | 2022-03-28 19:00
| Snowflake Deployment | Snowflake | Snowflake Team | Not Started | Snowflake to provide execution Log file to MDM team | Abhinav , Ranjith | 6 | 2022-03-28 13:00 | 2022-03-28 19:00
| Snowflake Deployment | Snowflake | MDM Team | Not Started | MDM team to validate the deployment | Prabhat Ghosh | 2 | 2022-03-28 13:00 | 2022-03-28 15:00
| Snowflake Deployment | Snowflake | MDM Team | Not Started | Confirm Snowflake Deployment Complete | Prabhat Ghosh | 2 | 2022-03-28 13:00 | 2022-03-28 15:00
| Matillion Deployment | Matillion | Matillion team | Not Started | CDP Project set up in Matillion | Howard Chen | 2 | 2022-03-28 13:00 | 2022-03-28 15:00
| Matillion Deployment | Matillion | Matillion team | Not Started | Setup Prod_MDM environment in Matillion | Howard Chen | 2 | 2022-03-28 13:00 | 2022-03-28 15:00
| Matillion Deployment | Matillion | MDM Team | Not Started | Importing jobs into Matillion Prod from BitBucket | Prabhat Ghosh | 2 | 2022-03-28 13:00 | 2022-03-28 15:00
| Matillion Deployment | Matillion | MDM Team | Not Started | Importing environment script into Matillion Prod from BitBucket | Prabhat Ghosh | 2 | 2022-03-28 13:00 | 2022-03-28 15:00
| Matillion Deployment | Matillion | MDM Team | Not Started | Validate All the Pipeline if the JOB variable are set up correctly | Prabhat Ghosh | 2 | 2022-03-28 13:00 | 2022-03-28 15:00
| Matillion Deployment | Matillion | MDM Team | Not Started | Confirm Matillion Deployment Complete | Prabhat Ghosh | 4 | 2022-03-28 13:00 | 2022-03-28 17:00
| Reltio Deployment | Reltio | MDM Team | Not Started | Import Reltio L3 Configuration to Reltio PROD from Bitbucket | Prabhat Ghosh | 2 | 2022-03-28 13:00 | 2022-03-28 15:00
| Reltio Deployment | Reltio | MDM Team | Not Started | Change the Sequence generator before applying the L3 configuration into Reltio PROD | Prabhat Ghosh | 2 | 2022-03-28 13:00 | 2022-03-28 15:00
| Reltio Deployment | Reltio | MDM Team | Not Started | Import Security Metadata Configuration to Reltio PROD from Bitbucket | Prabhat Ghosh | 2 | 2022-03-28 13:00 | 2022-03-28 15:00
| Reltio Deployment | Reltio | MDM Team | Not Started | Import UI Configuration to Reltio PROD from Bitbucket | Prabhat Ghosh | 2 | 2022-03-28 13:00 | 2022-03-28 15:00
| Reltio Deployment | Reltio | MDM Team | Not Started | Import Lookups/Reference Data to Reltio PROD RDM from Bitbucket | Prabhat Ghosh | 2 | 2022-03-28 13:00 | 2022-03-28 15:00
| Reltio Deployment | Reltio | MDM Team | Not Started | Import Dashboard configuration to Reltio PROD from Bitbucket (including Search count) | Prabhat Ghosh | 2 | 2022-03-28 13:00 | 2022-03-28 15:00
| Reltio Deployment | Reltio | MDM Team | Not Started | Import Workflow configuration to Reltio PROD from Bitbucket | Prabhat Ghosh | 2 | 2022-03-28 13:00 | 2022-03-28 15:00
| Reltio Deployment | Reltio | MDM Team | Not Started | Configure Reltio Customer Roles | Prabhat Ghosh | 5 | 2022-03-28 13:00 | 2022-03-28 18:00
| Reltio Deployment | Reltio | MDM Team/Reltio Team | Not Started | Validate All Reltio PROD confguration | Prabhat Ghosh | 5 | 2022-03-28 13:00 | 2022-03-28 18:00
| Reltio Deployment | Reltio | MDM Team | Not Started | Create Reltio Support ticket to wipe Reltio Data | Prabhat Ghosh | 2 | 2022-03-28 13:00 | 2022-03-28 15:00
| Reltio Deployment | Reltio | Reltio Team | Not Started | Reltio to clean data from PROD | Reltio Support | 5 | 2022-03-28 13:00 | 2022-03-28 18:00
Milestone 2 - Code deployment Ends
Milestone 3 - MDM Data Load Starts
| Pre-load | Reltio | MDM Team | Not Started | Create Reltio Support ticket to support Reltio PROD data load | Prabhat Ghosh | 2 | 2022-03-29 08:00 | 2022-03-29 10:00
| Pre-load | Reltio | Reltio Team | Not Started | Confirm the support contact from Reltio | Kiran Ghanta/Sumit/Ranadeep | 1 | 2022-03-29 08:00 | 2022-03-29 09:00
| Pre-load | Reltio | Reltio Team | Not Started | Disable Match Strategy in Tenant Physical Configuration | Sumit | 2 | 2022-03-29 08:00 | 2022-03-29 10:00
| Pre-load | Reltio | MDM Team | Not Started | Remove all the match rules from L3 configuration | Prabhat Ghosh | 4 | 2022-03-29 08:00 | 2022-03-29 12:00
| Pre-load | Snowflake | DI Team | Not Started | Confirm CSS data loaded into CSS_CDP schema in Snowflake | Kiranmai | 2 | 2022-03-29 08:00 | 2022-03-29 10:00
| Pre-load | Snowflake | MDM Team | Not Started | Validate CSS data available | Prabhat Ghosh | 2 | 2022-03-29 08:00 | 2022-03-29 10:00
| Pre-load | Snowflake | DI Team | Not Started | Confirm CRIS data loaded into CRIS_CDP schema in Snowflake | Kiranmai | 2 | 2022-03-29 08:00 | 2022-03-29 10:00
| Pre-load | Snowflake | MDM Team | Not Started | Validate CRIS data available | Varsha Gore | 2 | 2022-03-29 08:00 | 2022-03-29 10:00
| Data Prep and data load | Matillion/Snowflake/Reltio | MDM Team | Not Started | Execute JOB_MDM_CSS_Data_Load Matillion job | Prabhat Ghosh | 45 | 2022-03-29 08:00 | 2022-03-30 05:00
| Data Prep and data load | Matillion/Snowflake/Reltio | MDM Team | Not Started | Execute JOB_MDM_CRIS_Data_Load Matillion job | Varsha Gore | 25 | 2022-03-29 08:00 | 2022-03-29 09:00
| Data Prep and data load | Matillion/Snowflake/Reltio | MDM Team | Not Started | Validate CSS data load failures and try to process them if possible | Prabhat Ghosh | 6 | 2022-03-29 08:00 | 2022-03-29 14:00
| Data Prep and data load | Matillion/Snowflake/Reltio | MDM Team | Not Started | Validate CRIS data load failures and process them if possible | Varsha Gore | 6 | 2022-03-29 08:00 | 2022-03-29 14:00
| Post Data Load | Matillion/Snowflake/Reltio | MDM Team | Not Started | Schedule Jobs in Matillion for CSS and CRIS data load | Prabhat Ghosh | 6 | 2022-03-29 08:00 | 2022-03-29 14:00
| Post Data Load | Reltio | MDM Team | Not Started | Run the reindexing job in Reltio Prod - Set Update Entity = False, Streaming = OFF, Distributed Task Count = 8, Enable Separate Indexing = True | Prabhat Ghosh | 9 | 2022-03-29 08:00 | 2022-03-29 17:00
| Post Data Load | Reltio | MDM Team | Not Started | Once the reindexing job is completed reconsolidate the records counts | Prabhat Ghosh | 2 | 2022-03-29 08:00 | 2022-03-29 10:00
| Post Data Load | Snowflake | MDM Team | Not Started | Once job complete, validate record counts in Snowflake and Reltio | Prabhat Ghosh | 2 | 2022-03-29 08:00 | 2022-03-29 10:00
| Post Data Load | Snowflake | Snowflake Team | Not Started | Drop "Contact" tables and View from MDM Schema | Abhinav , Ranjith | 4 | 2022-03-29 08:00 | 2022-03-29 12:00
| Post Data Load | Snowflake | Snowflake Team | Not Started | Truncate all PROD tables from MDM Schema | Abhinav , Ranjith | 4 | 2022-03-29 08:00 | 2022-03-29 12:00
| Post Data Load | Reltio | MDM Team | Not Started | Once indexing is completed(CSS and CRIS) add the match rules back and apply the L3 configuration | Prabhat Ghosh | 4 | 2022-03-29 08:00 | 2022-03-29 12:00
| Post Data Load | Reltio | Reltio Team | Not Started | Enable Match Strategy in physical configuration | Sumit | 2 | 2022-03-29 08:00 | 2022-03-29 10:00
| Post Data Load | Reltio | MDM Team | Not Started | Run Rebuild match table job - Set Streaming = OFF, Distributed Task Count = 8 | Prabhat Ghosh | 91 | 2022-03-29 08:00 | 2022-03-30 03:00
| Post Data Load | Reltio | MDM Team | Not Started | Update Pipeline to include all Customer Individual, Customer Organization, Account, and relationship entities | Nishit Ajwaliya | 5 | 2022-03-29 08:00 | 2022-03-29 13:00
| Post Data Load | Reltio | MDM Team | Not Started | Create Incremental Snowflake Connector Job for every 4 hours | Nishit Ajwaliya | 5 | 2022-03-29 08:00 | 2022-03-29 13:00
| Post Data Load | Reltio | MDM Team | Not Started | Once Job complete, validate record count in Snowflake | Prabhat Ghosh | 2 | 2022-03-29 08:00 | 2022-03-29 10:00
| Post Data Load | Snowflake | Snowflake Team | Not Started | Create MDM_CDP schema in PROD_CDP_DB | Abhinav , Ranjith | 4 | 2022-03-29 08:00 | 2022-03-29 12:00
| Post Data Load | Snowflake | Snowflake Team | Not Started | Create Views in MDM_CDP schema | Abhinav , Ranjith | 4 | 2022-03-29 08:00 | 2022-03-29 12:00
| Post Data Load | Reltio | MDM Team | Not Started | Validate and confirm all data load | Prabhat Ghosh | 5 | 2022-03-29 08:00 | 2022-03-29 13:00
| Post Data Load | Reltio | MDM Team | Not Started | Make sure User has Access | Prabhat Ghosh | 5 | 2022-03-29 08:00 | 2022-03-29 13:00
| Post Data Load | Reltio | Business Team | Not Started | Hand it over to Business for the quick check | Vishal P/Mike D |  | 2022-03-29 08:00 | 2022-03-29 08:00
| Post Data Load | Reltio | Business Team | Not Started | Receive confirmation from Business | Vishal P/Mike D |  | 2022-03-29 08:00 | 2022-03-29 08:00
Milestone 3 - MDM Data Load Ends
Send out Go Live announcement to NG
| Post PROD |  |  |  | Matching Tuning in PROD
Formulas:
Planned End Date & Time = [Planned Start Date & Time] + TIME([Time to complete (Hours)],0,0)
Planned End Date & Time = [Planned Start Date & Time]+TIME([Time to complete (Hours)],0,0)

## Record Counts
| Count | Process Time | [5 empty] | Final Total
Matillion Data Prep | 33M records | 5 hours | 2min | 250 | 8min | 1m | 33M | 6
Individual/Organization Customer | 7M | 4 hours | 41min | 110 | 370min | 1M | 7M | 43
Account | 13M | 26 hours | 8min | 136 | 1h | 1M | 13M | 13
Acct-Cust Relationship | 13M |  | 16 min | 136 | 2h | 1M | 7M | 14
Reindexing | 20M |  | 7min | 250 | 28 | 1M | 20M | 9
Rebuild Match | 7M |  | 90min | 110 | 13 | 1M | 7M | 91
176
[9 empty] | 1 hours | 400K
[9 empty] | 2.5 | a