## Project Costs
Activity | Resource | Days | Start | End | Cost | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20
Data Operating Model
Establish "As-Is" & "To-Be" HR Data operating model |  |  | 2021-05-03 | 2021-06-04
Implement target operating model for priority use cases & the rest of HR |  |  | 2021-06-07 | 2021-07-30
Expand workforce target operating model to align to high value intersectional areas |  |  | 2021-08-02 | 2021-08-28
Iterate data roles & resonsibilities |  |  | 2021-08-30 | 2021-09-25
Define HR Data Vision |  |  | 2021-05-03 | 2021-06-04
Build HR Data Roadmap |  |  | 2021-06-07 | 2021-07-10
Data Governance
Roles & Forums starting to function upskilling in place |  |  | 2021-05-03 | 2021-06-25
Data Process and Standards |  |  | 2021-05-03 | 2021-07-10
Data assurance and controls |  |  | 2002-06-21 | 2021-11-06
Data Culture |  |  | 2021-05-17 | 2021-08-07
Data Integration & Data Model Insight
Establish common data model
Self Service Foundation
Self Service BI POC
Establish Self Service
Identify detailed integration issues and establish tailored design for HR Data integration
Key Improvements
Extend DQ Dashboards
Improve overall data Quality
Data Quality Improvement Update
Data Integration & Data Model Insight
Start up & Sanction |  |  | 2021-05-03 | 2021-05-29
Requirements |  |  | 2021-06-07 | 2021-07-31
Design |  |  | 2021-06-07 | 2021-08-27
SAP Interfaces Build |  |  | 2021-07-05 | 2021-10-01
MDM Build |  |  | 2021-07-05 | 2021-12-03
EDP Build |  |  | 2021-07-05 | 2021-12-03
SITS & Integration Testing |  |  | 2021-12-06 | 2021-12-28
UAT |  |  | 2022-01-31 | 2022-02-25
Production |  |  | 2022-03-07 | 2022-03-25
Early Life Support |  |  | 2022-04-04 | 2022-05-30
Role | Name | Days | Day Rate | Skill Set ID | Cost | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23
IT Programme
Programme Manager | Andy Noton | 60 | 610 |  | 36600 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Project Manager | Gavin Farrell | 180 | 420 |  | 75600 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Business Partner | Rohan Kapoor | 60 | 0 |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PSO Lead | Kelly Britton | 60 | 422 |  | 25320 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PMO | PMO | 8 | 2000 |  | 16000 | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1
SAP Tower
PMO Lead | Ellen Hunt | 8 | 333 |  | 2664 | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1
Lead Solution Architect | Vijaya Nayar | 5 | 610 |  | 3050 | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 1
Solution Engineering SEDirector | Debbie Turner | 8 | 1036 |  | 8288 | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1
Solution Engineering Lead | Sujata Goyal | 80 | 428 |  | 34240 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
Integration Solution Architect | Masood Khan | 18 | 410 |  | 7380 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Solution Architect | Shalini Saxena | 78 | 280 |  | 21840 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1
SF Functional Consultant | Anand V | 12 | 430 |  | 5160 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Tech Arch Team | Andy Earnshaw | 2 | 420 |  | 840 | 0.25 |  |  |  | 0.25 |  |  |  | 0.25 |  |  |  | 0.25 |  |  |  | 0.25 |  |  |  | 0.25 |  |  |  | 0.25 |  |  |  | 0.25
QES | Gagandeep Singh | 6 | 430 |  | 2580 | [13 empty] | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1
Release/Cutover Manager |  | 8 | 420 |  | 3360 | [22 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Total Costs |  |  |  |  | 242922
Data Operating Model
NG IT
Data Governance Manager | Kam | 14 | 0 |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Business
Data Domain Lead | David Smith | 45 | 0 |  | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
Business Analyst | Richard Walker | 30 | 525 |  | 15750 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Data Governance Lead | TBC | 54 | 0 |  | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
3rd Party
Capgemini
Consultant - Data Strategy, vision, engagement and workshop | TBC | 85 | 1087 |  | 92395 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Data Analyst | TBC | 53 | 450 |  | 23850 | 3.5 | 3.5 | 3.5 | 3.5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Total Cost |  |  |  |  | 116245
Total Cost |  |  |  |  | 131995
Data Governance
NG IT
Product Owner | Dan Senter | 11 | 0 |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Lead - Data Governance Manager | Kam Bharj | 27.5 | 0 |  | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
3rd Party - Capgemini
Data Analyst |  | 150 | 450 |  | 67500 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Data Analyst |  | 150 | 450 |  | 67500 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Data Consultant |  | 150 | 1087 |  | 163050 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Total Cost |  |  |  |  | 298050
Data Integration & Data Model Insight
NG IT
Lead - Enterprise Architect | Nishit Ajwaliya | 72 | 610 |  | 43920 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Solution Engineering SR Director | Bharat Tripathi | 54 | 0 |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Solution Engineering SR Manager | Sean Mcauley | 100 | 429 |  | 42900 |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
EC Solution Architect
Security Architect | Gerard R - Need to confirm No Days with Basav, will require Tech Scope | 21.7 | 600 |  | 13020 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
Infrastructure and Operations | TBC - Need to confirm if they charge for this - Bharat | 5 | 429 |  | 2145 | [34 empty] | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Interface Data SME UK & US | David Smith | 58 | 0 |  | 0 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Service Tranisition | TBC | 16 | 428 |  | 6848 | [38 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Lead Data Architect | Harsh Mundel | 62 | 428 |  | 26536 |  |  |  |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Enterprise Architect | Mandera Sen - Nishit to confirm if 1 day per month? | 13.5 | 0 |  | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Total Cost |  |  |  |  | 135369
3rd Party
TCS
QES Test Lead | TBC | 203.5 | 390 |  | 79365 | [13 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3.5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
QES Tester | TBC | 135 | 500 |  | 67500 | [13 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
QES Tester Offshore | TBC | 90 | 175 |  | 15750 | [22 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
QES Tester Offshore | TBC | 90 | 175 |  | 15750 | [22 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
QES Tester Offshore | TBC | 90 | 175 |  | 15750 | [22 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
TCS Total Cost |  |  |  |  | 194115
Capgemini
Senior Data Architect | TBC | 185 | 777 |  | 143745 |  |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Data Modeler India | TBC | 55 | 200 |  | 11000 | [6 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Data Models & Insight Analyst | TBC | 80 | 715 |  | 57200 |  |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2.5 | 2.5 | 2.5 | 2.5
Data Engineer | TBC | 165 | 777 |  | 128205 | [8 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Offshore - Analyst | TBC | 145 | 175 |  | 25375 | [12 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Offshore - Analyst | TBC | 145 | 175 |  | 25375 | [12 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Offshore - Consultant | TBC | 100 | 230 |  | 23000 | [21 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Offshore - Consultant | TBC | 100 | 230 |  | 23000 | [21 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Scrum Master | TBC | 185 | 715 |  | 132275 |  |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Lead Integration Architect | TBC | 128.5 | 715 |  | 91877.5 |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2.5
Data Integration Consultant | TBC | 45 | 777 |  | 34965 | [22 empty] | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
Data Integration Consultant | TBC | 73 | 777 |  | 56721 | [8 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
Data Integration Analyst | TBC | 160 | 715 |  | 114400 | [8 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Data Integration Analyst | TBC | 160 | 175 |  | 28000 | [8 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Offshore - Analyst | TBC | 95 | 175 |  | 16625 | [22 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Offshore - Analyst | TBC | 95 | 175 |  | 16625 | [22 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Capgemini Total Cost |  |  |  |  | 928388.5
Wipro
Integration Tech Support |  | 52 | 425.18 |  | 22109.36 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Fieldglass (FC) |  | 44 | 500 |  | 22000 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
ABAPer |  | 100 | 160.61 |  | 16061 |  |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Integration Resource 1 |  | 160 | 186 |  | 29760 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Integration Resource 2 |  | 92 | 142 |  | 13064 |  |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Integration Resource 3 |  | 76 | 142 |  | 10792 |  |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Wipro Total Costs |  |  |  |  | 113786.36
Supplier Total Cost |  |  |  |  | 1236289.86
Business
Product Owner | Glenn Mallinson | 7.8 | 0 |  | 0 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
Product Owner | Stacey Martson | 7.8 | 0 |  | 0 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
Product Owner | Paul Mason | 7.8 | 0 |  | 0 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
Product Owner | Dan Salter | 7.8 | 0 |  | 0 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
Customer Insight Process Lead | TBC
UAT SME - UK | Emma Mesey | 21.1 | 0 |  | 0 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UAT SME - US | Michelle Ericson | 21.1 | 0 |  | 0 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Total Cost |  |  |  |  | 0
Env Cost
US Env Costs |  |  |  | 59230.7692 | 90000
UK Env Costs |  |  |  |  | 9700
Firewall Changes |  |  |  |  | 10000
Total Cost |  |  |  |  | 109700
Licences
Infrastructure and year 1 licences | NG Azure VM and Infrastructure Charges |  |  |  | 25000
ER Studio Licences | ER/Studio Data Architect licence cost (2 licences for first 2 years then 1 licence) |  |  |  | 20000
Informatica CDQ | Informatica CDQ usage charges |  |  |  | 50000
Integration & Orchestration | Licence and usage cost for Mulesoft (£50k) and Matillion (£20k) |  |  |  | 70000
Data Catalog | Licence and usage costs (first 3 year cost is covered by IT4IT) |  |  |  | 0
Master Data Management | Licence, Usage,storage and support cost of Reltio MDM |  |  |  | 98000
Cloud Data Platform- Snowflake | Snowflake Compute and Storage Cost |  |  |  | 50000
Total Cost |  |  |  |  | 313000
Project Costs |  |  |  |  | 2316206.86

## Plan
Ref | Activity | Workstream | Resource Lead | Start | End | Status | Milestones | Dependencies | Successors | time axis 2021-05-03 to 2022-05-30
Pre-Requisite
1 | Sanction Paper created | IT Team | Rohan/Gavin | 2021-03-01 | 2021-04-23 | In Progress
2 | Environment Confirmed | IT Team | Gavin | 2021-03-01 | 2021-04-16 | In Progress
3 | Solution Vision Document Created and Signed off | IT Team | Mandira Sen | 2021-03-01 | 2021-04-02 | Complete
4 | Capgemini Resource Confirmed | IT Team | Bharat | 2021-03-01 | 2021-04-16 | In Progress
5 | TCS Resource Confirmed | IT Team | Bharat | 2021-03-01 | 2021-04-16 | In Progress
6 | Wipro Resource Confirmed | IT Team | Sujata | 2021-03-01 | 2021-04-02 | Complete
Requirements & Planning
7 | Establish "As-Is" and "To-Be" HR Operating Data Model | Data Operating Model | Capgemini Analyst | 2021-05-03 | 2021-06-04 | Not Started |  |  | 8 | bar: 2021-05-03 to 2021-05-31
8 | As Is and To Be Operating Data Model documented | Data Operating Model |  | 2002-06-04 | 2021-06-04 |  | Y | 7 | 11,13
9 | Clarify data roles and responsibilities | Data Operating Model | Capgemini Analyst | 2021-06-07 | 2021-07-30 | Not Started |  | 7 | 10 | bar: 2021-06-07 to 2021-07-26
10 | Roles and Responsibilities Documented | Data Operating Model |  | 2021-07-30 | 2021-07-30 |  | Y | 9 | 11,13
11 | Review existing Data Governance Structures, Interactions and roles in other domains to best fit HR and create key interaction models | Data Governance | Capgemini Consultant | 2021-08-02 | 2021-08-27 | Not Started |  | 8,10 | 12 | bar: 2021-08-02 to 2021-08-23
12 | Key Interaction Model Documented | Data Governance |  | 2021-08-27 | 2021-08-27 |  | Y | 11
13 | Key roles identified and responsibilities trained | Data Governance | Capgemini Consultant | 2021-08-30 | 2021-10-02 | Not Started |  | 8,10 | 14 | bar: 2021-08-30 to 2021-09-27
14 | Key Roles Trained | Data Governance |  | 2021-10-02 | 2021-10-02 |  | Y
15 | Carry out assessment of fields in myhub that are not currently being fed by reference data lists & assess suitability of this | Data Governance | Capgemini Analyst | 2021-07-19 | 2021-08-13 | Not Started | bar: 2021-07-19 to 2021-08-09
16 | Assess the compatibility of reference data sets with SAP ECC | Data Governance | Capgemini Analyst | 2021-07-19 | 2021-08-13 | Not Started | bar: 2021-07-19 to 2021-08-09
17 | Reference Data Sets including Data Definitions and Quality requirements where required | Data Governance | Capgemini Consultant | 2021-07-19 | 2021-08-20 | Not Started |  |  | 18 | bar: 2021-07-19 to 2021-08-16
18 | Document Data Definitions and Quality requirements |  |  | 2021-08-20 | 2021-08-20 |  | Y | 17
19 | Agree a regular review & maintenance process | Data Governance | Capgemini Consultant | 2021-08-16 | 2021-09-03 | Not Started |  |  | 20 | bar: 2021-08-16 to 2021-08-30
20 | Regular Review and Maintenance Process in place |  |  | 2021-09-03 | 2021-09-03 |  | Y | 19
21 | Evaluate required steps to incorporate stricter data controls within 3rd party systems | Data Governance | Capgemini Consultant | 2021-09-13 | 2021-10-22 | Not Started | bar: 2021-09-13 to 2021-10-18
22 | Data Model and Integration Requirements Documented and signed off | Data Model & Integration |  | 2021-05-31 | 2021-06-13 | Not Started |  | 23 | bar: 2021-05-31 to 2021-07-26
23 | Data Model Integration Requirements signed off | Data Model & Integration |  | 2021-06-13 | 2021-06-13 |  | Y |  | 22
Design & Processes
24 | Define HR Data Vision | Data Operating Model | Capgemini Consultant | 2021-05-03 | 2021-06-04 | Not Started |  | 7 | 26 | bar: 2021-05-03 to 2021-05-31
25 | Build HR Data Roadmap | Data Operating Model | Capgemini Consultant | 2021-06-07 | 2021-07-10 | Not Started |  | 24 | 26 | bar: 2021-06-07 to 2021-07-05
26 | HR Data Vision and Roadmap documented |  |  | 2021-07-10 | 2021-07-10 |  | Y | 24,25
27 | Update CRUD afor HR/IT changes and BAU Processes | Data Governance | Capgemini Analyst | 2021-05-03 | 2021-05-22 | Not Started | bar: 2021-05-03 to 2021-05-17
28 | Socialise data principles and standards within HR | Data Governance | Capgemini Analyst | 2021-05-10 | 2021-06-05 | Not Started |  |  | 29 | bar: 2021-05-10 to 2021-05-31
29 | Communicate out Data Principles and Standards in HR | Data Governance |  | 2021-06-05 | 2021-06-05 |  | Y | 28
30 | Update to data maturity and focus in with wider selction of data consumers/users across the business | Data Governance | Capgemini Consultant | 2021-05-17 | 2021-06-11 | Not Started | bar: 2021-05-17 to 2021-06-07
31 | Highlight common themes and cross validate with other overlapping domains e,g Finance | Data Governance | Capgemini Consultant | 2021-06-07 | 2021-06-18 | Not Started | bar: 2021-06-07 to 2021-06-14
32 | Develop key themes to target along with supporting actions | Data Governance | Capgemini Consultant | 2021-05-24 | 2021-06-04 | Not Started | bar: 2021-05-24 to 2021-05-31
33 | Identification & mobilisation of change culture champions | Data Governance | Capgemini Analyst | 2021-05-31 | 2021-06-25 | Not Started | bar: 2021-05-31 to 2021-06-21
34 | Establish target maturity updates/surveys to track progress | Data Governance | Capgemini Analyst | 2021-06-14 | 2021-06-25 | Not Started |  |  | 35 | bar: 2021-06-14 to 2021-06-21
35 | Target Maturity Updates/Surveys in place |  |  | 2021-06-25 | 2021-06-25 |  | Y | 34
36 | Initial Design Complete | Data Model & Integration |  | 2021-06-14 | 2021-06-27 | Not Started | bar: 2021-06-14 to 2021-06-21
37 | CSA Complete and Reviewed | Data Model & Integration |  | 2021-07-12 | 2021-07-25 | Not Started | bar: 2021-07-12 to 2021-07-19
38 | Data Modelling Signed off | Data Model & Integration |  | 2021-07-26 | 2021-08-08 | Not Started |  |  | 39 | bar: 2021-07-26 to 2021-08-02
39 | Data Modelling Complete | Data Model & Integration |  | 2021-08-08 | 2021-08-08 |  | Y | 38
40 | MDM Configuration | Data Model & Integration |  | 2021-08-09 | 2021-08-22 | Not Started |  |  | 41 | bar: 2021-08-09 to 2021-08-16
41 | MDM Configuration complete |  |  | 2021-08-22 | 2021-08-22 |  | Y | 40
Build
42 | Implement target data operating model for priority uses cases and the rest of HR | Data Operating Model | Capgemini Consultant | 2021-06-07 | 2021-07-30 | Not Started |  | 8 | 43,46,50 | bar: 2021-06-07 to 2021-07-26
43 | Target Data Operating Model Implemented | Data Operating Model |  | 2021-07-30 | 2021-07-30 |  | Y | 42 | 44
44 | Expand Workforce target operating model to align to high value intersectional areas | Data Operating Model | Capgemini Consultant | 2021-08-02 | 2021-08-28 | Not Started |  | 42,43 | 50 | bar: 2021-08-02 to 2021-08-23
45 | SAP Interfaces Built | Data Model & Integration |  | 2021-08-23 | 2021-09-19 | Not Started | bar: 2021-08-23 to 2021-09-13
46 | Release 1 | Data Model & Integration |  |  |  | Not Started
47 | MDM Integration for 1st Release complete | Data Model & Integration |  | 2021-09-20 | 2021-10-03 | Not Started |  |  | 49 | bar: 2021-09-20 to 2021-09-27
48 | EDP Populated for 1st Release | Data Model & Integration |  | 2021-10-04 | 2021-10-31 | Not Started |  |  | 49 | bar: 2021-10-04 to 2021-10-25
49 | Release 1 Complete | Data Model & Integration |  | 2021-10-31 | 2021-10-31 |  | Y | 47,48 | 51
50 | Release 2 | Data Model & Integration |  |  |  | Not Started | bar: 2021-11-01 to 2021-11-08
51 | MDM Integration for 2nd Release complete | Data Model & Integration |  | 2021-11-01 | 2021-11-14 | Not Started |  | 49 | 53 | bar: 2021-11-15 to 2021-11-22
52 | EDP Populated for 2nd Release | Data Model & Integration |  | 2021-11-15 | 2021-11-28 | Not Started |  |  | 53 | bar: 2021-11-15 to 2021-11-22
53 | Release 2 Complete | Data Model & Integration |  | 2021-11-28 | 2021-11-28 |  | Y | 51,52
54 | Outbound API Set Up | Data Model & Integration |  | 2021-11-29 | 2021-12-12 | Not Started | bar: 2021-11-29 to 2021-12-06
55 | Oubound API Complete |  |  | 2021-12-12 | 2021-12-12 |  | Y
55 | Self Service Set Up | Data Model & Integration |  | 2021-12-13 | 2022-01-09 | Not Started | bar: 2021-12-13 to 2022-01-03
56 | Self Service Complete | Data Model & Integration |  | 2022-01-09 | 2022-01-09 |  | Y
Training & Communications
57 | Set up series of DM training | Data Governance | Capgemini Analyst | 2021-06-21 | 2021-07-16 | Not Started | bar: 2021-06-21 to 2021-07-12
58 | DM Training Delivered | Data Governance |  | 2021-07-16 | 2021-07-17 |  | Y | 57
58 | Communication Campaigns | Data Governance | Capgemini Analyst | 2021-07-12 | 2021-08-06 | Not Started | bar: 2021-07-12 to 2021-08-02
Testing
59 | Testing desired behaviours via high value use cases | Data Governance | Capgemini Analyst | 2021-06-21 | 2021-07-02
60 | SIT & Integration Testing | Data Model & Integration | QES Lead | 2021-12-06 | 2022-01-28 | Not Started |  |  | 61 | bar: 2021-12-06 to 2022-01-24
61 | UAT | Data Model & Integration | QES Lead | 2022-02-01 | 2022-02-26 | Not Started | Y |  | 62 | bar: 2022-01-31 to 2022-02-28
62 | Testing Complete | Data Model & Integration |  | 2022-02-26 | 2022-02-26 |  | Y | 60,61
| Go Live |  |  | 2022-03-01 | 2022-03-31
63 | HR Data Forums in place and embeded into existing governance | Data Governance | Capgemini Consultant | 2021-05-31 | 2021-06-25 | Not Started | bar: 2021-05-31 to 2021-06-21
64 | Roll out data principles/stamdard with appropriate use cases across HR | Data Governance | Capgemini Analyst | 2021-05-31 | 2021-07-10 | Not Started | bar: 2021-05-31 to 2021-07-05
65 | Implement quick process fixes based on assessments | Data Governance | Capgemini Analyst | 2021-08-02 | 2021-09-24 | Not Started |  |  | 67 | bar: 2021-08-02 to 2021-09-20
66 | Implement priority reference data lists in myhub | Data Governance | Capgemini Analyst | 2021-09-06 | 2021-09-24 | Not Started | Y |  | 67 | bar: 2021-09-06 to 2021-09-20
67 | Fixes and Priority reference data lists implemented to Live | Data Governance |  | 2021-09-24 | 2021-09-24 |  |  | 65,66
68 | Mobilise data quality measurement and DQ best practise within 3rd party systems | Data Governance | Capgemini Analyst | 2021-10-11 | 2021-11-12 | Not Started | bar: 2021-10-11 to 2021-11-08
69 | Cutover to Production | Data Model & Integration |  | 2022-03-01 | 2022-03-31 | Not Started | bar: 2022-03-07 to 2022-03-28
70 | Go Live | Data Model & Integration |  | 2022-03-31 | 2022-03-31 |  | Y | 69

## Scope & Deliverables
Workstream | Scope | Deliverables
Data Operating Model | Organises teams to own and manage data | Workforce Domain Data Strategy, Roadmap & Vision
As-Is Assessment & To-Be creation of Data Operating Model playbook
RACI and capabilities of workforce data team outline and agreed
Operational Roles & Responsibilities set up and communicated
Data Operating Model luanched across workforce domain
Target Data Operating Model fully implemented
Automated Data Management processes set up
Data Governance | Deliver Change Management and Crystallising Data Models, Insights and Integratio into BAU “Stand-up an executive sponsored data governance model, which operates to defined data standards, manages data stewardship and outlines quality assurances & controls for the use of data across the Workforce Domain” | Increase data governance use-case adoption
Data Management best practises defined
Addressed processes & control gaps
Roles & forums fully functional - supported by enterprise tooling
Improve data management best practice delivery
Further preventiative data assurance and controls in place
Cross-domain governance interaction model in place and running alongside OP Model
Delivery and tracking of training across the workforce domain
Data Management best preactises reconfigured
Data assrance and controls reconfigured
Data Models, Insight and Integration | Delivers Data Trust in Workfore Data, and Data Centricity by mastering Workforce Data and establishing a Workforce Data platform (EDP) to ensure consistency and accuracy of data consumed by downstream systems | Identify key DQ issue mgmt and define a max of 10 issues of medium complexity
Data Integration mitigation plan and design
Key integration issue identified
Key integrations improvements prioritized
Implement new integration key features, including a single source of truth
Enterprise unique persistent ID for the worker
Integration with MDM
MDM Centralized data repository for the Workforce Master Data
Replace IAM Tactical MDM Solution with enterprise strategic MDM
EDP Centralized data repository for all workforce
Implement up to 10 new data quality dashboards
Finalise all build and implementation effort
Consolidation of new assests with changes driven by MyHub
Key attributes, KPIs and metrics documented
Logical Business Glossary created
Workforce Physical data model defined
Full serve service capability, sourcing data from trustworthy sources, supported by an operating model and a complete business glossary business
Self Service operating model embedded in the organisation.
users fully independent to create self-serve reports and dashboards

## RTB Costs 1
| Description | 2022 | 2023 | 2024 | 2025 | 2026
Licences
Data Modelling ER Studio | ER/Studio Data Architect Licence Cost (2 Licences for first 2 years and then 1 Licence) | 20000 | 20000 | 10000 | 10000 | 10000
Data Quality - Informatica CDQ | Informaitca CDQ useage Charges | 50000 | 50000 | 50000 | 50000 | 50000
Data Integration & Orchestration - Mulesoft,Matillion | Licence and Usage cost for Mulesoft (£50k) and Martilion (£20k) | 70000 | 70000 | 70000 | 70000 | 70000
Data Catalog and Governance - Informatica | Licence and Usage cost (First 3 years cost is covered by IT4IT) | 0 | 0 | 0 | 19000 | 19000
Master Data Management - Relito | Licence, Usage,Storage and support cost of Relito MDM | 98000 | 98000 | 98000 | 98000 | 98000
Cloud Data Platform -Snowflake | Snowflake Compute and Storage Cost | 50000 | 50000 | 50000 | 50000 | 50000
Env |  | 6000 | 6000 | 6000 | 6000 | 6000
Infrastructure | NG Azure VM and Infrastructure Charges | 25000 | 25000 | 25000 | 25000 | 25000
Resource
Data Engineering Analyst | Support cost for all data tools and workforce code | 45000 | 45000 | 45000 | 45000 | 45000
Total RTB |  | 364000 | 364000 | 354000 | 373000 | 373000

## Env
Application | Scope | Provisioned by | Confirmed Dates
SF | Global | Barbara
SAP ECC USS | US | Barbara
Fieldglass | Global | Barbara
SAP CPI | Global | Barbara
SAP PO | UK | Ian
SAP PI | US | Barbara
Mulesoft | US | Barbara
SAP ECC UK | Not required
MDM | In clound not included in costing