## Slide 1
Data Capability Enablement as of 01/2021
Capability available
Tool(s) Selected
Research Initiated
GA timeline uncertain
2021
JAN
FEB
Q2
Q3
Q4
MAR
Data Analytics & Reporting – Power BI
Data Modeling - ER/Studio
Actively Deployed
Informatica - Data Quality, Data Catalog, Data Governance
Enterprise Data Analytics Platform - Snowflake
Master Data Management – Finalists: Reltio, Informatica
Data Integration & Orchestration
Advanced Analytics, Machine Learning & AI
Q4
Q1
Q3
Q2
2020
ITGC
Approved
ITGC
Approved
Achievements since last Communication
  Master Data Management “bake off” of final two vendors have been completed. Next up is commercial and security components. Target End of February for final decision
  We have progressed and fine-tuned our research on Data Integration & Orchestration with focus concentrated on Matillion and LogicApps at this time. Gaps will still exist, such as Data Replication and will need to be addressed in future
  Snowflake continues to march towards general availability. Architecture and critical initial setup around account structure, security and network configuration continue to move forward. Target for initial early (limited) adoption is April.
  Data Catalog/Governance capability is on target to be enables by end of February. A proof of concept is being developed with goal to have completed in the April timeline. Scoring is being tabulated and
  Multiple sessions with the Microsoft /Azure Data Architecture group have been held to help us determine our approach to Machine Learning and Artificial Intelligence (ML/AI). We have additional sessions scheduled thru January with goal of end of Q1 for recommendation and general framework.

## Slide 2
10/05-10/19 – Consolidate MDM Use cases/Capabilities - Completed on 10/16
10/05-10/19 – Identify NG team (IT + Business) for demo - Completed on 10/19
10/19 – Share MDM Use cases/Capabilities with vendors - Completed on 10/16
10/19-10/30 – Vendor to prepare demo to show use uses - Completed on 11/9
11/02-11/10 – Vendor Demo with NG and follow-up with vendor - Completed on 11/9
11/13 – Finalize top 2 tools - Completed 11/12
11/12-11/20 – Create Specific use cases for 2nd round of demo and share with Informatica and Reltio (Riversand withdraw 12/3) - Completed 11/19
11/12-12/08 – Create a business case for standing up MDM tool for funding prior to April 2021 - Completed 12/4
12/07 – Present business case to stand up MDM tool for funding to Steve Olive - Approved by Steve 12/7
11/20-1/7 – Both vendors to prepare final round of demos – Completed 1/14
11/30-1/15 – Vendor Demo presentation with 2 vendors – Completed 1/14
1/19 – ITGC group presentation – Approved 1/19
11/13-1/30 – Security Assessment of both Informatica and Reltio MDM platforms – In progress
11/13-1/30 – Initial procurement discussion with both Informatica and Reltio MDM platforms – In progress
1/30 – Finalize MDM tool score on security, procurement, and demos and select the Final Tool
12/25-2/22 – Complete Security, legal, funding, and procurement process
2/22 – Sign Contract
2/22- 3/30 – Stand-up DEV and QA MDM environments (prod after 3/15)
Master Data Management Platform Selection Plan