## Slide 1: Executive Steering Group
  05th March 2021

## Slide 2
Purpose & Ask
1
MyHR2.0 Overview
3
Progress and Next Steps
2
Workforce Data Domain Overview
4
Agenda
Global Workforce Tracking Overview
5
Appendix
6
To be updated

## Slide 3
Session Purpose & Ask
What is the purpose of the session and the ask of the SteerCo?
The Ask of the Session
MyHR 2.0
  Approval to move to sanction for recommended scope
  Approval to start project re-mobilisation in Sep with Oct'21 start date for delivery
2. Workforce Data Domain
  Approval to move to sanction for recommended scope
3. Global Workforce Tracking
  Approval to move to sanction for recommended scope, subject to completion of outstanding business actions
4. Request for feedback on current activities and direction of travel.
  Feedback
  Changes Requested
  Recommendations/Alterations
Purpose
MyHR 2.0
  Share revised delivery approach, timelines, cost and associated benefits
Workforce Data Domain
  Share revised scope, timeline and cost
Global Workforce Tracking
Share progress
Programme to escalate/highlight key Steerco Feedback items
  Risks, dependency which directly impact planning & execution scope and achievability.
  Bandwidth & Capacity concerns (Business & IT SMEs)
Notes: Who is involved in the EC Workshops? Controls, HRPS (Chris Ly)
Who is involved in the DCB? Share the TORs before next steerco
Are we doing a controls impact assesement?
Who are the participants of the DCB? Functions & Roles.

## Slide 4
MyHR2.0 Transformation Vision
Current State
MyHR 2.0 Target
Managers
Employees
HR & Bus Serv.
Self-service system for end-to-end recruitment Inc. contractors
Single source of truth on workforce, including MSPs
Accountability & control over managing headcount & hierarchy
Self-service tool for all HR Requirements, learning, performance etc.
One-Stop-Shop for system owners req. workforce data
A unique identifier, which follows them around the company
Single source of truth on workforce, including MSPs
Efficient global processes & clear accountability across teams
Single point of entry for workforce data
Increased control over critical data
Lack of Self-Service
Regional ways of working & regional system configuration
Out of system disjointed manual processes in Business Services
Increased operational costs
Customised integrations between Employee Central and On Premise SAP causing integration errors & reporting compliance challenges.
Poor data quality across critical HR data fields with a lack of clear HR data governance & ownership framework
Inadequate end to end metrics
Lack of visibility into performance challenges & accountability in processes
Functionality operating as expected
Operating with some issues
Major Issues / Significant functionality not available
Improvement driven by MyHR 2.0
MyHub module
Addressing existing major issues in MyHR 2.0
Making supporting improvements in My HR 2.0
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
Sales | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2
1
1, 2, 3
& 6
1
1 & 3
3
2
Core scope for each iteration
Number indicates iteration where impacts occur
1
9
9

## Slide 5
MyHR2.0 Transformation Vision
MyHR 2.0 Target
Managers
Employees
HR & Bus Serv.
Self-service system for end-to-end recruitment Inc. contractors
Single source of truth on workforce, including MSPs
Accountability & control over managing headcount & hierarchy
Self-service tool for all HR Requirements, learning, performance etc.
One-Stop-Shop for system owners req. workforce data
A unique identifier, which follows them around the company
Single source of truth on workforce, including MSPs
Efficient global processes & clear accountability across teams
Single point of entry for workforce data
Increased control over critical data
Lack of Self-Service
Regional ways of working & regional system configuration
Out of system disjointed manual processes in Business Services
Increased operational costs
Customised integrations between Employee Central and On Premise SAP causing integration errors & reporting compliance challenges.
Poor data quality across critical HR data fields with a lack of clear HR data governance & ownership framework
Inadequate end to end metrics
Lack of visibility into performance challenges & accountability in processes
Functionality operating as expected
Operating with some issues
Major Issues / Significant functionality not available
Improvement driven by MyHR 2.0
MyHub module
Addressing existing major issues in MyHR 2.0
Making supporting improvements in My HR 2.0
Current State
Pre-Read

## Slide 6
To-Be Business Process Maps
SAP “Recommendation Report” for all SuccessFactors modules
Completed Technical, Integration & Business Change Impact Assessments
To-Be requirements for Global Workforce Mgmt. & Tracking (All worker types permanent + non-perm)
To-Be Employee Central Configuration Workbooks
Updated & Validated Business Case
Defined Logical Workforce Data Domain Model & Golden Record
As-Is Workforce Data Maturity Assessment
To-Be workforce Data Governance Model defined
Proposed remediation plan with associated Investment Paper
MyHR2.0
Design Outputs
What have we achieved and what is next?
Overall Programme Outcomes
Workforce Data Domain
Build SuccessFactors updated Configuration in multiple iterations
Fix Integrations into on premise UK&US SAP Downstream systems.
Build FieldGlass integration for global workforce tracking
Comprehensive Testing throughout iterations
Comprehensive Business Change & Process Engineering & Training
Build Activities
Leaders will have clarity on processes and contact points
Improved resolution times and operational efficiency by 1.5x
Access rights will be correctly managed effectively reducing the risk of data leakage due to unintended access by 10-15%
Data will be seamlessly integrated across the HR landscape, allowing colleagues to proactively address data gaps via Data Quality dashboards.
Improved resolution times & 20-25% reduction in manual data handling.
Linkage
Workforce Data Domain will build a foundational platform and single source of truth for all consumers of workforce data
MyHR 2.0 will ensure this platform is as standard & simple as possible. Reducing complexity & associated cost of downstream consumers, such as MyFinance, IAM”
Increased SAP Standardisation in our system config
FTE reduction​ through improved efficiency in our supporting Op Model
Addressed control issues through simplifying integrations
Increased Automation
Simplified End-to-End HR processes
Enabled Global Workforce Tracking (All worker types permanent + non-permanent)
Addressed workforce data inconsistencies between systems​
Define enduring WDD Operating Model
Mobilise & Embed Governance Model
Culture & Training Activities
Implement Workforce Data Model Platform
Drive downstream connectivity to new EDP, enable iPaaS, deploy new MDM platform and deploy new DQ platform
We will maintain our operationally expensive custom configuration, increasing costs for downstream consumers.
We will maintain regional and disjointed operational processes with greater headcount
We will not be able to offer self-service HR processes and improved employee experience
We will maintain our poor data quality, control over workforce analytics, governance and maturity score
What if
we don’t invest?
Feasibility analysis complete to assess technology and process to manage non-employee workforce
As-is process documented and pain points identified
Proposed solution to manage non-emp workforce
Detailed requirements and design
To-be process mapping and documentation
Configuration of CWP and WPM aligned to business requirements
Build Fieldglass integration to downstream apps
Single source of truth, Non-Employees mastered in one single system irrespective of Category or region
Mitigate Audit and Security Risks related to non-employees
Addressed workforce data inconsistencies between systems​
Increased automation
GWT
Pre-Read

## Slide 7: ~£4.5M of proposed J2L value reliant on MyHR2.0, WDD, & GWT
MyHR2.0, WDD, GWT
~£4.5M value dependent on foundational IT programmes due to automation opportunities, process changes, and data quality improvements
0.3 L&D sprint
0.9 Mng. data & trans. sprint
0.1 ARO dashboard
1. Apply, recruit, onboard
Note: Values represent midpoint targets and are approximate; numbers may not foot due to rounding
Source: BCG analysis
2.1 ARO1 sprint
0.7 Strategy sprint
0.2 Union back-end simplif.
0.2 Reporting sprint
(Values shown in £M)
Self-service improvements (e.g., role-based permissions) allow for reduction in resourcing
Self-service for routine reports allows for consolidation of reporting resources
MSP / contractor data provide insight into optimal outsourcing model
Data quality and self-service improvements (e.g., role-based permissions) reduce volume of manual data entries
Reduction in manual activities (e.g., faxes) drives productivity improvements
Automation of admin. and manual activities (e.g., offer letter creation, etc.) drives consolidation
Automation of nudges (e.g., follow-ups) and improved planning enables consolidation

## Slide 8: Overall Cost & Benefit Case – Executive Summary
MyHR 2.0
WDDO
GWT
CAPEX
OPEX
TOTEX
£10.5 M
£1.35 M
£1.70 M
£1.20 M
£1.23 M
£0.40 M
£11.8 M
£2.58M
£2.10 M
MyHR 2.0
WDDO
GWT
Single Source of Data
Controls Issues and Simplification of Integrations
Support Op Model Efficiency
Process Simplification and User Experience
Standard Reporting and WFA Capability
Cost of integration reduced
IAM enabler
Strategic architecture built (EDP,MDM,DQ,APIs)
Data assurance, standards, procedures and controls built
Golden record and data models, data capability matured
Data quality is continuously measured and managed for 33k workers
Single Source of Data
Mitigate Audit and Security Risks
Enabler to strategic workforce planning
Make the right buying decisions
Enable Facilities Planning and site demand management
MyHR 2.0
WDDO
GWT
Tangible Benefit
£568 K
Building capability
Insourcing Capability
Intangible Benefit
Forecast Costs
At this stage project is asking for approval of first 3 iterations which will be delivered over a period of 30 weeks. The cost to deliver this scope is £xx M and tangible value that will be delivered is xx£ M
The project contains 3 workstreams – 1) Governance £700k, 2) Operating Model £130k are enablers for the key workstream 3) Data Models, Insights and Integration £1750k. The entire project runs for 9 months with 1 and 3 agile, and 2 waterfall.
With do-nothing option, Total Cost of Ownership (TCO) for NG over 5 years will be £4.6 M, as license and maintenance cost will be paid in-directly via Contingent Provider (currently Pontoon). Going with the recommendation of NG owned platform TCO over 5 years will be £4.9 M. Additional £300k spend over 5 years would mitigate outstanding Audit & Security risks and enable seamless management of entire workforce (employee and non-employee)
Ask – Approval to progress |  |  | 
myHR | WDDO | GWT | Total Cost
*£2.10 M | £2.58 M | £2.10 M | £6.78 M
*MyHR cost for first 3 iterations
Notes: EDP is the enterprise data platform or SnowFlake cloud DB, a unifying store for data mastered in many operational data stores
MDM is the master data management solution that delivers a unique worker id and supports IAM and contractor to perm conversions
DQ is data quality or Informatica Cloud Data Quality, we feed in data, measure its quality and report and manage defects
APIs are application programming interfaces, the modern way to get data from source and import it into a target system

## Slide 9
MyHR 2.0

## Slide 10: MyHR2.0 Implementation Phasing – Justin
Dependency
Phases for Sanctioning |  |  | Phases for Future Sanctioning |  |  |  |  |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 (N) - Intergration
“Quick Wins & Moving to Standard” | “Introducing Self Serve Hierarchy Functionality & Removing Custom Fields” | “Introducing Business Hierarchy and Temporary Assignment’’ | “Releasing Transition Period Functionality” | “Moving to Standard on Pay Related Information” | “Releasing Leave of Absence & Right to Return Functionality” | “Moving to Standard on Contract Type Fields” | “Moving to Standard for Contingent Workers” | “Improving Role Based Permissions” | “Integration to SAP on Premise”
Removal of link between JC & JPB HR Manager Matrix Relationship Hide user name when adding new employee Proof of concept for transition periods LMS Data Services Onboarding Admin Reports & Reporting Use Bus X Audit Func. | Position to Job Information Sync Removal of Custom Fields Position Creation & Delimiting | Temporary Assignment Data aspect of Temporary Assignments Enable Job Info Pay Group Enabling of Business Unit, Division, Department | Transition Periods integration for Employees Transition Periods for Managers | Replacing Location Group with Geozone Enable Job Info Pay Group Removal of country specific fields Reverting to standard pay ranges and Job Classification | Introduce the leave of absence and right to return functionality Improving performance of compensation module | Removing Custom Field Person ID Job information Contract Type Introducing role based learning | Mandatory fields for contingent workers Mass Positions Using LMS for Contingent workers | Making objects mandatory Role Based Permissions (RBP) Learning Improvements (Reduce Admin Access Roles) | Downstream Config Integration to SAP for BU, Division Department Chief Position Automation of transition periods for managers (integration to SAP) Introduce System Identifier to SAP ECC Redesign field values for Employee Class & Employment Type Integration for ‘Managers’ Transition Periods etc… Person ID External DOA
*To Be Validated
Title
Core Employee Central Scope
*Foundational work, Value delivered in later phase
Value
*SuccessFactors Non-EC scope
JUSTIN & ALAN CONTENT

## Slide 11: MyHR2.0 Iteration Cost Forecasts - Andy
 | Phase – “Iteration” |  |  |  |  |  |  |  |  | 
Title | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 (N)
 | “Quick Wins & Moving to Standard” | “Introducing New Functionality & Removing Custom Fields” | “Introducing Business Hierarchy & Temp Assign” | “Releasing Transition Period Functionality” | “Moving to Standard on Pay Related Info” | “Releasing Leave of Absence & Right to Return Func” | “Moving to Standard on Contract Type Fields” | “Moving to Standard for Contingent Workers” | “Improving Role Based Permissions” | “Improving Role Based Permissions”
Timeline | 7 Weeks | 12 Weeks | 11 Weeks | TBC | TBC | TBC | TBC | TBC | TBC | TBC
NG IT Cost | £56K | £90K | £81K |  |  |  |  |  |  | 
Wipro Cost | £247K +£250K ROM | £424K | £339K |  |  |  |  |  |  | 
Business Cost | £145K | £250K | £229K |  |  |  |  |  |  | 
Total Iteration Cost | £698K* | £764K* | £649K* |  |  |  |  |  |  | £6M
Cumulative Cost |  | £1.45M | £2.1M |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  | £11M
*Based on initial ROM’s and draft proposals, further discussion required, if the approach is agreed.
**Ball Park figure – significant dependencies on timing and other inflight initiatives.
JUSTIN & ALAN CONTENT

## Slide 12: MyHR2.0 Implementation Phasing
 |  |  | Phase – “Iteration” |  |  |  |  | 
Title |  |  | 1 |  | 2 |  | 3 | 
 |  |  | “Quick Wins & Moving to Standard” |  | “Introducing New Functionality & Removing Custom Fields” |  | “Introducing Business Hierarchy and Temporary Assignment” | 
Timeline |  |  |  |  |  |  |  | 
Technical Scope |  |  | Enhancement of critical HR data relationships, improving controls and insight |  | Systemisation of position creation and simplification of supporting data model |  | Workflow reduction and improvement and systemised temporary assignment* process | 
ROM Cost |  |  | £448K |  | £764K |  | £649K | 
Benefit | Tangible Benefit | UK | N/A |  | $11 - $17k (Position Creation) |  | N/A | 
 |  | US | N/A |  | $52 - $78k (Position Creation) |  | $9 - $14k (Union workflow enhancement) | 
 |  | Total |  |  | $63 – 95k |  | $9 - $14k | 
 | Intangible Benefit |  | Improvement in HR to employee data alignment Reducing controls Issues Improving HRBP visibility and insight Enabling further enhancements in reporting |  | Providing Managers accountability for their own hierarchy Increasing self serve for Managers Simplifying our positional data model Reducing the volume of offline requests into Business Services |  | Reduction in workflow volume and simplification of workflows across EC Enhanced workflows, reducing the need for Business Services to contact Managers outside of the system Improved event derivation, driving clearer reporting | 
Change Impact | High |  | 0 |  | 3 |  | 0 | 
 | Medium |  | 0 |  | 9 |  | 2 | 
 | Low |  | 7 |  | 26 |  | 2 | 
 | # of Personas Impacted (highest impacted) |  | 3 | Process Executor HRBP Individual Contributor | 8 | Process Executor Manager Supervisor | 4 | Process Executor Manager Supervisor
 | # of People Impacted |  | ~14,000 |  | ~4,300 |  | ~4,200 | 
1 | 2 | 3 | 4 | 5 | 6 | 7
CL | B&UT |  |  | QAB | UAT | Dep
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
CL | B&UT |  |  |  |  | QAB |  | UAT |  | Dep | ELS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
CL | B&UT |  |  |  | QAB |  | UAT |  | Dep | ELS
* Slide does not include impacts / tangible benefits relating to Temporary Assignments as final technical proposal is being validated

## Slide 13: MyHR2.0 Implementation Phasing
 |  |  | Phase – “Iteration” |  |  |  |  |  |  |  |  |  |  | 
Title |  |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 | 
 |  |  | “Releasing Transition Period Functionality” |  | “Moving to Standard on Pay Related Info” |  | “Releasing Leave of Absence & Right to Return Function” |  | “Moving to Standard on Contract Type Fields” |  | “Moving to Standard for Contingent Workers” |  | “Improving Role Based Permissions” | 
Timeline |  |  | ~10 Weeks |  | ~10 Weeks |  | ~10 Weeks |  | ~10 Weeks |  | ~10 Weeks |  | ~10 Weeks | 
Technical Scope |  |  | Simplification of position management, accelerating processes |  | Simplification of Job Architecture, improved recruitment geographic reporting |  | Systemised LoA process and simplified position management |  | Simplified HR data model and processes, improved controls and access |  | Reduced position requests, accelerated recruitment, streamlines MSP/MSA approach in MyHub |  | Improved control and security, simplified reporting and automated data flows | 
ROM Bus. Change Cost |  |  | £254k |  | £254k |  | £254k |  | £254k |  | £254k |  | £254k | 
Benefit | Tangible Benefit | UK | $7 – 11k |  | N/a |  | $11k - 17k |  | No |  | $0.5-1k |  | 63k-94k (Global WFA) | 
 |  | US | $29 – 43k |  | N/a |  | $9 – 13k |  | No |  | $8-12k |  |  | 
 |  | Total | $36 – 54k |  | N/a |  | $20 – 30k |  | No |  | $8.5 – 13k |  | 63k-94k (WFA) | 
 | Intangible Benefit |  | Simplified & standard position management Reduce Business Services workload, and accelerate processes Simplified & standard headcount reporting |  | Job Architecture simplification (dependant on future clarification)* Improve recruitment geographic reporting Simplified data maintenance for Business Services Simplified pay range management for reward team (particularly UK) |  | Systemise LoA request process Reduce Business Services workload, and accelerate processes and SLAs Improved employee experience and autonomy Simplified & standard position management Simplified & standard headcount reporting |  | Simplified HR data model Reduced data maintenance Simplified processes for Managers of Contingent Workers Improved controls and access |  | Reduction in need for new position requests Accelerate recruitment on high volume roles i.e. new talent Reduction in data maintenance requirements Streamlined approach to MSP/MSA positions within MyHub |  | Improved control and security using a simplified role based permissions structure Unlock standard and simple reporting and dashboards within MyHub Automation of company structured data flows to other modules i.e. R&O | 
Change Impact | High |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 
 | Medium |  | 5 |  | 0 |  | 4 |  | 0 |  | 3 |  | 3 | 
 | Low |  | 13 |  | 5 |  | 14 |  | 6 |  | 7 |  | 25 | 
 | To be discussed |  | 0 |  | 0 |  | 1 |  | 0 |  | 1 |  | 1 | 
 | # of Personas Impacted (highest impacted) |  | 7 | Manager Process Executor Supervisor | 3 | Process Executor Manager Supervisor | 6 | Manager Individual Contributor Process Executor | 4 | Manager Process Executor Individual Contributor | 4 | Process Executor Manager Supervisor | 8 | Process Executor Manager Supervisor
 | # of People Impacted |  | ~9,800 |  | ~3,600 |  | ~9,800 |  | ~9,600 |  | ~4,000 |  | ~4,000 | 
Slide only includes EC scope
Bus Change estimates to be refined for each module

## Slide 14: MyHR2.0 Implementation Phasing
 |  |  | Phase – “Iteration” |  |  |  | 
Title |  |  | 10 (N) – Integration Waterfall |  |  |  | 
 |  |  | “Integration to SAP on Premise” |  |  |  | 
Timeline |  |  | ~6 Months |  |  |  | 
Technical Scope |  |  | UK HR payroll system streamlined, improved position creation & controls & security. Simplified data model within HR systems |  |  |  | 
ROM Bus. Change Cost |  |  | ~£816k |  |  |  | 
Benefit | Tangible Benefit | UK | $1-1.5k (Company Structure) |  | To be defined then |  | 
 |  | US | $136-204k (Company Structure) 5-7k (Cost Center Standardisation) |  | To be defined then |  | 
 |  | Total | $142-212.5k |  | To be defined then |  | 
 | Intangible Benefit |  | SuccessFactors Impacts Improved controls and security for global assignees and rehires with alignment across key systems Simplified data model within HR systems Simplified cost distribution process in the UK and removal of redundant fields in US Simplified and standard integrations to downstream systems with reduced replication errors |  | Downstream Impacts High: UK HR payroll system streamlined to support Legal Entity and payroll area realignment simplification. Improved position creation and systemised approvals in UK GRC. Medium: Significant changes to company structure, as custom structures replaced in MyHub & SAP with standard. Low: Increase in data quality leading to reduction in data alignment and tickets/queries. Note: Low / Medium / High impact = < 25% / < 50% / > 50% change to role of process, respectively. |  | 
Change Impact | High |  | 1 |  | Impacted Systems | High | 2
 | Medium |  | 4 |  |  | Medium | 17
 | Low |  | 1 |  |  | Low | 41
 |  |  |  |  |  | Low | 41
 | To be discussed |  | 2 |  |  | None | 12
 |  |  |  |  |  | None | 12
 | # of Personas Impacted |  | 3 | Process Executor Manager Reporting Team |  | None | 12
 | # of People Impacted |  | ~9,600 |  |  |  | 
Bus Change estimates to be refined for each module

## Slide 15: myHR 2.0 Cost Comparison Cost Breakdowns**
Total WIP Cost |  |  |  |  |  |  | 
Previous TOTAL: |  |  |  |  | Vs. | £24M | Revised estimate based on Iterative delivery
myHR 2.0 Based on Original Plan Estimates |  |  | Waterfall |  | Iterative |  | Commentary
 | myHR2.0 | NGIT | £2.5M | £17M** |  | £11.8M** | Inc. Leadership, Solution Engineering, Architecture, Assurance (Security, Controls etc.)
 |  | NGBiz | £3.8M |  |  |  | TBC - Business Resource costs allocation to project. Current assumption - Leadership & Product owners roles remain BAU
 |  | NG Infrastructure | £1.9M |  |  |  | Significant cost due to current capacity constraints. Opportunity to reduce £ with delay
 |  | MSP Business Change | £2.5M |  |  |  | ROM Cost from Accenture BC Team– Mini Tender to be issued subject to sanction.
 |  | Wipro | £3.7M |  |  |  | Technical Delivery SF & Downstream ADAM Framework
 |  | Miscellaneous | £0.2M |  |  |  | Staff Travel, Plug-In, Walkme, Audit cost allowance etc.
 |  | Risk | £2.1M |  |  |  | TBC 3rd Party Downstream Development Costs + Overrun cost risk.
GWT Based on Original Plan Estimates |  |  | Breakdown |  |  | TOTAL | 
 | GWT | NGIT | £0.26M | £2M | £0.26M | £2M | Inc. Leadership, Solution Engineering, Architecture, Assurance (Security, Controls etc.)
 |  | NGBiz | £0.14M |  | £0.14M |  | TBC - Business Resource costs allocation to project.
 |  | NG Infrastructure | £0.1M |  | £0.1M |  | Environment Costs for connected delivery landscape.
 |  | Wipro | £1M |  | £1M |  | Technical Delivery ADAM Framework
 |  | Risk | £0.2M |  | £0.2M |  | Overrun cost risk + CR risk (E.g. additional integration requirements).
Workforce Data Domain Based on Original Plan Estimates |  |  |  | Breakdown |  |  | TOTAL | 
 | Workforce Data Domain | IT | Data Culture Workstream | £0 | £4.6M |  | £2.6M | Inc. Leadership, Solution Engineering, Architecture, Assurance (Security, Controls etc.)
 |  |  | Data Governance Workstream | £0 |  |  |  | 
 |  |  | Data Integration Workstream | £0.13M |  |  |  | 
 |  |  | Data Models & Insight Workstream | £0.04M |  |  |  | 
 |  |  | Data Operating Model Workstream | £0 |  |  |  | 
 |  | MSP Delivery Partner | Data Culture Workstream | £1M |  |  |  | Cost proposal from Accenture Workforce Team following current Phase.
 |  |  | Data Governance Workstream | £0.7M |  |  |  | 
 |  |  | Data Integration Workstream | £1.2M |  |  |  | 
 |  |  | Data Models & Insight Workstream | £1M |  |  |  | 
 |  |  | Data Operating Model Workstream | £0.6M |  |  |  | 
* Note: Breakdowns for each project provided in subsequent slides
**Estimated 10-20% additional cost forecast to deliver through Option 3 – Phased Approach recommended. Additional scoping, planning & dependency assessment efforts required to refine.
 | Internal NG Costs
 | External 3rd Party Costs
 | Mixed Cost

## Slide 16: MyHR2.0 Implementation Phasing - Justin
 |  |  | Phase – “Iteration” |  |  |  |  | 
Title |  |  | 4 | 5 | 6 | 7 | 8 | 9
 |  |  | “Releasing Transition Period Functionality” | “Moving to Standard on Pay Related Info” | “Releasing Leave of Absence & Right to Return Func” | “Moving to Standard on Contract Type Fields” | “Moving to Standard for Contingent Workers” | “Improving Role Based Permissions”
Timeline |  |  |  |  |  |  |  | 
Technical Scope |  |  |  |  |  |  |  | 
ROM Cost |  |  |  |  |  |  |  | 
Benefit | Tangible Benefit | UK |  |  |  |  |  | 
 |  | US |  |  |  |  |  | 
 |  | Total |  |  |  |  |  | 
 | Intangible Benefit |  |  |  |  |  |  | 
Change Impact | High |  |  |  |  |  |  | 
 | Medium |  |  |  |  |  |  | 
 | Low |  |  |  |  |  |  | 
 | # of Personas Impacted (highest impacted) |  |  |  |  |  |  | 
 | # of People Impacted |  |  |  |  |  |  | 
* Slide does not include impacts / tangible benefits relating to Temporary Assignments as final technical proposal is being validated
JUSTIN & ALAN CONTENT

## Slide 17: MyHR2.0 Implementation Phasing - Justin
 |  |  | Phase – “Iteration”
Title |  |  | 10 (N) – Integration Waterfall
 |  |  | “Integration to SAP on Premise”
Timeline |  |  | 
Technical Scope |  |  | 
ROM Cost |  |  | 
Benefit | Tangible Benefit | UK | 
 |  | US | 
 |  | Total | 
 | Intangible Benefit |  | 
Change Impact | High |  | 
 | Medium |  | 
 | Low |  | 
 | # of Personas Impacted (highest impacted) |  | 
 | # of People Impacted |  | 
* Slide does not include impacts / tangible benefits relating to Temporary Assignments as final technical proposal is being validated
JUSTIN & ALAN CONTENT

## Slide 18: myHR 2.0 Programme RAID
#Ref | Issue Classification | ISSUE Status | Description | Mitigating Action | Target Resolution | Owner
I-21 | Concern | Critical | The overall costs exceeded initial estimate at last sanction | Scope of what can be delivered and approach being reviewed to help reduce Project costs | 05/03/21 | Andy Noton
OPEN | Critical | High | Med | Low | Negligible | Closed | TOTAL
14 | 3 | 3 | 1 | 4 | 3 | 57 | 71
1 | -1 | 1 | - | - | - | 3 | 4
OPEN | Critical | High | Med | Low | Negligible | Closed | TOTAL
2 | 1 | 1 | 0 | 0 | 0 | 21 | 23
-1 | - | -3 | - | - | - | - | 1
ISSUES
RISKS
#Ref | Risk Type | RISK Status | Description | Mitigating Action | Target Resolution | Owner
R-59 | Resource | Critical | There is a risk that the combined Change Portfolio for HR & Business Services from Jan 2021 onwards will result in significant capacity constraints & gaps across several key resources and associated teams. Resulting in schedule, cost and quality impacts to key decisions, activity progress/pace and outputs across several key engagement areas. | Requires wider alignment through the Change portfolio. Query on current assessments being done across inflight and known demand… e.g. other IT Programmes, Project Evolution, T2 Readiness & BAU operational efforts in an ongoing remote working environment. Once revised Scope work is complete and grouping/bunding exercise will identify what Business Resource will be required and when and any resource constraints | 19/03/2021 | Andy/Justin
R-62 | Sanction | Critical | There is a risk that we do not secure funding for Data Domain Phase 2 in FY21 | Project Sponsors raising upwards to Andi K, Andy D. | 12/03/2021 | Gary Dione
R-53 | Design | Critical | There is a risk that we will need to proceed planning & delivery with current assumption that Job Grading & Architecture will remain "As Is“ – due to unknowns & potential reworking/impacts of inflight change. | There is currently activity underway to Impact Assess the Job Grading. | 05/03/2021 | Justin
R-17 | Design | Med | There is a risk that Architectural landscape and data flow mapping is not yet fully complete ahead of the design work | Review and validation of the existing landscape lead by NG Solution Architecture team - This work is not 100% complete due to missing few TS/FS documents. Wipro have been asked to help get the final few done and will then be an evolving doc | 01/04/2021 | Debbie
ISSUES
RISKS

## Slide 19
Workforce Data Domain Owner (WDDO)

## Slide 20: Deliverables, value & benefit
Dependency
Key Deliverables
Key Value*
Data Operating Model
Data Owners will have a target state to work towards and monitor whilst employees will have better clarity on processes and contact points for all data operational processes . This will reduce data re-work, tickets, and use of fire fighter access to fix data.
Set the Workforce data vision and strategic roadmap with an approach to measure its implementation
Communicate & implement the Workforce data operating model to ensure that roles and responsibilities support the data lifecycle (Create, Read, Update, Delete)
Data Governance
Access rights will be correctly managed effectively reducing the risk of data leakage due to unintended access by 10-15% e.g. employees being paid after they have left National Grid
Assign ownership via the newly proposed Data Governance framework and support by forums and interactions
Embed best practice for BAU processes and change requests to improve our data integrity
Data Integration
Data will be seamlessly integrated across the HR landscape, there will be no more manual interventions and colleagues can proactively address data gaps, improving resolution times and This will reduce manual data handling by 20-25%.
Identify gaps with data and its integration between systems
Integration improvements driven from MDM golden record
Rectify gaps and automate integration where feasible aligning to a MDM/EDP solution
Data Model & Insight
This will help towards building a uniform view of all workforce related information and reduce ambiguity in operational reporting by 10-20%
Implement a central workforce data model supported by business terminology and build on the key set of attributes identified for different types of workers (employees, contractors, service providers).
Create enduring tooling capability via self-serve insights into workforce data
*All figures provided are based on Accenture 3rd party research
SPOKE
HUB
Lead - David Smith
Spend - £130k
Duration – 117 days
Man days – 198 days
Benefits location
HR Business Services
Workforce data stakeholders – integrated systems, workers, managers
All across National Grid
Business Areas to manage, adapt & implement via their DDO
Workforce centric-benefit for integrity & use of Workforce data.
Entire of National Grid will be enabled delivery of IT target-state architecture
IT Domain as we lead on the DQ analysis of key ID platforms
Workforce centric-benefit for integrity & use of Workforce Data.
Entire of National Grid will be enabled delivering IT vision of leveraging digitalisation
WDD Program will implement new data management and monitoring tools and technology coupled with a strong operating model to drive data ownership and accountability and enduring capability to monitor data quality which enables Process and Data Owners to sustain the quality of data in their stewardship
‘Hub’ workstreams will deliver value and benefit across the entire Group – ‘Spoke’ across Workforce Data Domain
Data Culture
WS data points
Lead – Dan Senter
Spend - £700k
Duration – 120 days
Man days – 725 days
Lead – Bharat Tripathi
Spend - £1,750k
Duration – 271 days
Man days – 4,000 days
Workstream Descoped – Key outputs absorbed by other workstreams where possible

## Slide 21
Global Workforce Tracking
(GWT - Fieldglass)

## Slide 22: GWT Status and Timeline
Background
Our global non-employee workforce consists of approximately 9611 workers
Contingent workers are tracked through SAP Fieldglass, which is currently provided by Pontoon
Statement of Work (SoW) workers are somewhat tracked across multiple systems when system or site access is required
Two recent audit findings relate to the tracking of our non-employees
  Background checking: No single repository with a complete and accurate list of all non-employees, which reduces the effectiveness of monitoring the background check process
  Starters, Movers & Leavers: Lack of controls on the starters, movers, leavers process of non-employees
The Identity and Access Management (IAM) programme have also identified concerns and risks with how we track and manage non-employees
Recommendation
To address the audit and IAM concerns, National Grid require a single source of truth for tracking all non-employees. Such a system should enable:
  Management of non-employees from a joiner to leaver perspective
  Simplified integrations to allow flow of workforce information between applications
  Process automation and self-serve capabilities
SAP Fieldglass is the recommended software solution as it is a market leader and allows for simpler integrations with National Grid’s existing SAP architecture
It’s recommended that we bring two SAP Fieldglass modules in-house:
  Contingent Worker Module (CWM): Module currently provided through Pontoon
  Worker Profile Module (WPM): New module to provide basic tracking of non-employees not captured by CWM, i.e. SoW workers
Next Steps
IT Sanction is required to proceed to the implementation phase
The ongoing contingent labour tender requires a decision so that the contingent labour software solution can be factored into supplier bids (supplier shortlisting ongoing, contract award due early April ‘21)
Wipro’s suggested implementation timeline is 36 weeks (incl. 6 weeks of post-go live support

## Slide 23: Appendix Approach Re-Cap

## Slide 24
MyHR 2.0 Costs & Benefits Case- Executive Summary
MyHR2.0 Benefits
1
Direct benefits resulting from Process based time savings from EC decisions in MyHR2.0
Indirect time savings as a result of EC decisions in MyHR2.0.
Intangible Benefits expected as a result of wider HR2.0 Programme activity
2
3
Min | Stretch
213k | 320k
25k | 38k
47k | 70k
284k | 427k
284k – 427k
94k – 141k
Reduced transaction time for business services to action transactions / updates reduced due to enhanced self-service & data sync
Reduced maintenance effort required due to reduction in replication errors between MyHub and SAP ECC
Intangible
Single source of data, control Issue simplification & efficiency, process simplification, reporting & user experience
Tangible savings achieved through operational headcount & contractor reduction
US Business Services
UK Business Services
Global Workforce Analytics
Min | Stretch
71k | 107k
23k | 34k
94k | 141k
Total
MyHR2.0 Costs
Y1 | Y2
7.40 M | 3.15 M
1.00 M | 0.25 M
8.40 M | 3.40 M
Cost to deliver proposed MyHR 2.0 changes
Cost includes both US and UK
£11.8 M
$
CAPEX
OPEX
TOTEX
Single Source of Data
Working towards MyHub existing as a single source of trusted workforce data
Syncing of key data fields (e.g. position, cost center) and removal of custom fields will remove unnecessary data maintenance
Centralizing processes (e.g. leave of absence) and removing complexity in the data model will deliver clean and consistent data across the ecosystem
Controls Issues and Simplification of Integrations
Address control issues through simplifying integrations and addressing workforce data inconsistencies
Offline forms and processes are automated, enabling efficient workflow vs manual intervention
Support Op Model Efficiency
Improve the efficiency in our supporting Operating Model and enable FTE reduction
Greater autonomy and self-service for managers (e.g. position and org hierarchy changes)
Process Simplification and User Experience
Remove Joiners to Leavers complexity, improve user experience, process efficiency and overall employee engagement and enablement
The business will have valuable real-time reporting and dashboards to drive strategic decision making
Standard Reporting and WFA Capability
Unlock standard reporting and full workforce analytics capability
Further tangible benefits to be qualified throughout the build phase

## Slide 25
GWT Costs & Benefits Case- Executive Summary
GWT Benefits
1
Tangible benefits resulting from implementation of NG owned FG
Intangible Benefits expected as a result of GWT
2
10k – 70k
Intangible
Single source of truth, Mitigate open audit actions and security risks, enabler to strategic workforce planning, authoritative source to IAM for access management
Business Services
ACG
SW/HW
Total
GWT Costs
Y1 | Y2
1.70 | 00
0.40 | 00
2.10 M | 00
Blurb about how costs were calculated
Total cost for design, build for both UK and US. Cost includes 1st year license and support cost, which is $0.93 M
£2.10 M
$
CAPEX
OPEX
TOTEX
Single Source of Truth
Non-Employees mastered in one single system irrespective of Category or region.
Provisions a National Grid owned single source of truth for tracking and managing all non-employees.
Address the open Audit actions by setting up a single system so that non-employee SML process could be better tracked, controlled and reported on including BGV status.
Mitigate Audit and Security Risks
Address Open Audit Actions related to non-employees.
Manage workforce Architecture mix to consider internal as well Contingent/ SOW Workers. Provide better Insights to base resourcing decisions on.
Enabler to strategic workforce planning
Group HR doesn’t have complete visibility of non-employee resources and their skillsets
Enable procurement to make the correct buying decisions based on visibility of our non-employee workforce and buy the correct resources
Make the right buying decisions
Make correct buying decisions based on visibility of non-employee workforce.
Provide non-employee insights to Corporate Property for forward facilities planning and site demand management
Enable Facilities Planning and site demand management
Ensure sites can cope with demand and sites demand is maintained in accordance with HSE requirements
Further tangible benefits to be qualified throughout the build phase
Min | Stretch
TBC | TBC
10k | 70k
TBC | TBC
10k | 70k
With do-nothing option, Total Cost of Ownership (TCO) for NG over 5 years will be $6 M, as license and maintenance cost will be paid in-directly via Contingent Provider (currently Pontoon). Going with the recommendation of NG owned platform TCO over 5 years will be $6.4 M. Additional $400k spend would allow NG to mitigate outstanding Audit & Security risks and enable seamless management of entire workforce (employee and non-employee)

## Slide 26
WDDO Phase 2 Costs & Benefits Case- Executive Summary
WDDO Benefits
1
Direct benefits resulting from implementation
Intangible Benefits expected as a result of WDDO
3
£tbck
Enterprise data platform stood up and sharing data with downstream systems via API layer, we avoid new point to point integrations, reduce the cost of maintaining integrations as we migrate away from existing point to point integrations. Also supports future myHub changes requiring integration change.
Intangible
Worker data accurate, shared, able to support the agile/digital ambition
Tangible savings achieved through vendor costs reduction
WIPRO
WDDO Costs
Y1 £ | Y2 £
1.35m | 0 M
1.13m | 0.24m
2.58m | 0.24M
Cost to deliver 3 workstreams, globally
Y1 Spend is combination of platform implementation, and business process and governance development and implementation. The project will implement a number of high value use cases and provide a foundation for future build out. Y2 is licences and some people resource to support the change in BAU
£2.58m
£
CAPEX
OPEX
TOTEX
Data maturity improved
Improving our digital capability for the workforce domain
We move from a maturity score of 1.45 out of 5 to 3.3 which puts us ‘in the pack’ to ‘ahead of the pack’
Platform consumers of worker data use API and fetch data – we reduce expensive custom integrations. Other consumers pull from Snowflake on demand, securely
Strategic architecture built
Reduces the TCO of our platforms and processes.
Accountability for the entire data lifecycle deployed to data owners and stewards. Playbooks deployed to provide one way to master, update and delete data. We govern our data better\easier
Data assurance, standards, procedures and controls built
We have one way of managing and governing data
Update the conceptual and logical data models, ensure integration improvements to Downstream systems are driven from a Golden Record
Golden record and data models
Core documentation and data facts documented
We make data quality measurement simple by leveraging the strategic architecture, the enterprise data platform and DQ tooling, published and consumed by data SMEs using PowerBI
Data quality is continuously measured and managed
Critical worker identity data is accurate to support consumers
Further tangible benefits to be qualified throughout the build phase
£k | Details of saving
tbc | Reduce cost of new integrations, cost of maintaining existing integrations and one off reduce costs incurred by myHR2.0 when it changes integrations
DRAFT NOT AGREED NOT FOR SHARING

## Slide 27
myHR2.0 Transformation Vision
Current State
MyHR 2.0 Target
Managers
Employees
HR & Bus Serv.
Self-service system for end-to-end recruitment Inc. contractors
Single source of truth on workforce, including MSPs
Accountability & control over managing headcount & hierarchy
Self-service tool for all HR Requirements, learning, performance etc.
One-Stop-Shop for system owners req. workforce data
A unique identifier, which follows them around the company
Single source of truth on workforce, including MSPs
Efficient global processes & clear accountability across teams
Single point of entry for workforce data
Increased control over critical data
Lack of Self-Service
Regional ways of working & regional system configuration
Out of system disjointed manual processes in Business Services
Increased operational costs
Customised integrations between Employee Central and On Premise SAP causing integration errors & reporting compliance challenges.
Poor data quality across critical HR data fields with a lack of clear HR data governance & ownership framework
Inadequate end to end metrics
Lack of visibility into performance challenges & accountability in processes
Functionality operating as expected
Operating with some issues
Major Issues / Significant functionality not available
Improvement driven by MyHR 2.0
MyHub module
Addressing existing major issues in MyHR 2.0
Making supporting improvements in My HR 2.0

## Slide 28
myHR Implementation Options Intro
Option | Option Overview | Exec Summary |  | Implementation Analysis |  |  | 
 | Scope | Pro’s | Cons | Cost | Time | Risk | Ben
Do Nothing | Stand Down Programme & leave the System in it’s current state – making any improvements through the BAU CR Funding route only. | No additional Cost or resource efforts No complexity/dependency considerations | Enduring As-Is Architecture & associated pain points (Slide 2) |  |  |  | 
 “Big Bang” | Full Scope* Inc. Global Workforce Tracking– Delivered through 1 integrated programme starting as soon as possible in line with original aspirations. Start ~March 2021 with Full delivery across EC & Other modules, “Big-Bang” implementation, Go-live ~May 2022 Workforce Data Domain, full scope of MDM / EDP with supporting culture, operating model and governance | Delivering the full Scope, overall deliverables & value* as quickly as possible. Best case support for strategic dependencies of IAM, MyFinance Etc. Economies of scale supporting full delivery – efficient sequencing MDM & EDP Foundation Built as quickly as possible Workforce Data Domain full maturity reached earliest. | Congested Change Landscape - Business Capacity Constraints to deliver Evolution etc. Job Grading & Evolution activities & outputs risk – unknown timelines & impacts to the inflight programme. Lower cost certainty due to unknowns. IT Environment Capacity constraints driving increased Costs to mitigate. Outstanding Detailed Design activities. |  |  |  | 
 “Big Bang-Delay” | Full Scope* – Delivered through 1 integrated programme with a delayed kick for myHR2.0 off to accommodate wider change landscape & capacity concerns/constraints. Global Workforce Tracking kick-started & delivered independently with implementation starting asap ~Feb 2021 Start ~Aug 2021 with full delivery across EC & Other modules, “big-bang” implementation, go-live ~October 2022 Workforce Data Domain, full scope of MDM / EDP with supporting culture, operating model and governance spread over a longer period | Economies of scale supporting full delivery – efficient sequencing. Enables wider linkages such as grading / org transition to be delivered ahead of full team mobilisation. Accounts for business capacity constraints Allows additional dependencies and impacts to be considered. E.g. Lessons learned from IAM & myFinance. & Evolution. | Delay to tangible business benefits Desired workforce data domain maturity level is reached at later date Potential loss of key project resources during stand down period (External) Potential risk of further delays to programme mobilisation & delivery due to yet unknown risks |  |  |  | 
 “Phased Acceleration” | Full Scope* – Delivered through a phased delivery. An iterative “agile” Phase I delivering “resource-light”, “No-Regret”, quick-win improvements before Phase II delivering the ‘big-bang’ large scale improvements’ mobilising later to account for constraints Global Workforce Tracking kick-started & delivered independently with implementation starting asap ~Feb 2021 Phase I Start ~Feb 2021 Phase II Start ~Aug 2021 with go-live in October 2022 Workforce Data Domain, full scope of MDM / EDP with supporting culture, operating model and governance | Accelerated delivery of benefits to the end user Enables wider linkages such as grading / org transition to be delivered in advance Allows an agile approach to delivery of value, in parallel with organisational change Greater cost certainty possible for Phase II. Secures core subset key resources throughout constraint period. MDM & EDP Foundation Built & Workforce Data Domain full maturity reached earliest | Delay to overall tangible business benefits. Potential risk rework required in some areas (Low). Potential additional total cost to deliver elements separately. Loss of shared efficiencies (to be fully costed). Estimated ~10-20% |  |  |  | 
RECOMMENDATION
Significant Issues – - Best Case 

## Slide 29
Implementation Options POAP Estimates
Option | Description | 2021 |  |  |  | 2022 |  |  |  | 2023
 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | 
 “Big Bang” | Global Workforce Tracking – Global Workforce Tracking (Fieldglass) Implementation |  |  |  |  |  |  |  |  | 
 | Additional Value “Non Core Module Improvements) |  |  |  |  |  |  |  |  | 
 | Core myHR 2.0 Scope |  |  |  |  |  |  |  |  | 
 | Workforce Data Domain – Workforce Data Domain Delivery |  |  |  |  |  |  |  |  | 
 “Big Bang-Delay” | Global Workforce Tracking – Global Workforce Tracking (Fieldglass) Implementation |  |  |  |  |  |  |  |  | 
 | Additional Value “Non Core Module Improvements) |  |  |  |  |  |  |  |  | 
 | Core myHR 2.0 Scope |  |  |  |  |  |  |  |  | 
 | Workforce Data Domain – Workforce Data Domain Delivery |  |  |  |  |  |  |  |  | 
 “Phased Acceleration” | Global Workforce Tracking – Global Workforce Tracking (Fieldglass) Implementation |  |  |  |  |  |  |  |  | 
 | Additional Value “Non Core Module Improvements” |  |  |  |  |  |  |  |  | 
 | Core myHR 2.0 Scope |  |  |  |  |  |  |  |  | 
 | Workforce Data Domain – Workforce Data Domain Delivery |  |  |  |  |  |  |  |  | 
Mobilisation
myHR Full Implementation Go Live
~ Approx May 22
Workforce Data Domain Phase 1
Phase 2
Phase 3
Release 1
Release 2
Release 3
GWT Go Live
MDM /EDP
Design
Mobilisation
Core SuccessFactors & Downstream Build
myHR Full Implementation Go Live
~ Approx Oct 22
Workforce Data Domain Phase 1
Phase 2
Phase 3
MDM Release 1
MDM Release 2
MDM Release 3
Global Workforce Tracking Fieldglass Implementation
GWT Go Live
MDM Design
Phase I – Current Instance & Quick Win
myHR Full Implementation Go Live
~ Approx Oct 22
Workforce Data Domain Phase 1
Phase 2
Phase 3
Non Core Module Improvements
Phase II – Core SF & Downstream Build & Test
Mobilisation
Global Workforce Tracking Fieldglass Implementation
GWT Go Live
Global Workforce Tracking Fieldglass Implementation
Core SuccessFactors & Downstream Build
Testing
Job Grading – Independent Delivery
Mobilisation II
BAU CRs
Non Core Module Improvements
Non Core Module Improvements
*Job Grading Design Decisions & Implementation will have significant impacts to the current myHR2.0 Plan Estimates
Release 1
Release 2
Release 3
MDM /EDP
Design
RECOMMENDATION
Re-Plan
Cutover Simulation & Build
Testing
Cutover Simulation & Build
Job Grading Implementation
April ‘22
Job Grading – Independent Delivery
Job Grading Implementation
April ‘22
Job Grading – Independent Delivery
Job Grading Implementation
April ‘22
Re-Plan
Cutover Simulation & Build
Job Grading Impact Assessment
Jan ‘21
Job Grading Impact Assessment
Jan ‘21
Job Grading Impact Assessment
Jan ‘21
Re-Plan
- Stand Down -

## Slide 30
Option | Description | 2021 |  |  |  | 2022 |  |  |  | 2023
 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | 
 “Phased Acceleration” | Core myHR 2.0 Scope |  |  |  |  |  |  |  |  | 
 | Additional Value “Non Core Module Improvements) |  |  |  |  |  |  |  |  | 
 | Global Workforce Tracking – Global Workforce Tracking (Fieldglass) Implementation |  |  |  |  |  |  |  |  | 
 | Workforce Data Domain – Workforce Data Domain Delivery |  |  |  |  |  |  |  |  | 
Phase I – Current Instance & Quick Win
myHR Full Implementation Go Live
~ Approx Oct 22
Workforce Data Domain Phase 1
Phase 2
Phase 3
Non Core Module Improvements
Phase II – Core SuccessFactors & Downstream Build & Test
Mobilisation
GWT Go Live
Global Workforce Tracking Fieldglass Implementation
Mobilisation II
TBC*
BAU CRs
Release 1
Release 2
Release 3
MDM /EDP
Design
RECOMMENDATION
Job Grading – Independent Delivery
Re-Plan
Recommendation: Option 3 Scope Summary
Phase II – New Instance & Big Bang | Value / Benefit
Organization Structure (II) | Enable standard structure in MyHub and hierarchy integrations to SAP ECC
Position Management (II) | Implementation of transition periods, temp assignments, mass positions and right to return removes shadow positions, simplifies and standardizes config
Foundation Data (II) – employee data, contract data, location | Removal of custom fields across position and employee records with enhanced data sync
Job Structure | Simplifying job architecture
Grading Structure | Simplifying grading structure globally
Legal Entity and Cost Center Alignment | Reduce the reliance on cost distribution within MyHub in the UK
Platform - RBP Rebuild & Home Page Redesign | Dynamic access management with MyHub and rebrand to Grid People
Rebuild Integrations | Improved accuracy of hierarchy and critical data points do downstream systems
Leave of Absence (UK) | Remove offline process to request LoA, building visibility of leave in MyHub
DOA Decommission | Removal of non-HR data out of MyHub
Non Employee Central Modules (e.g. Learning, Compensation, Recruitment Onboarding) | Implement remaining SAP SF recommendations outstanding from phase I
Phase I – Iterative Delivery | Value / Benefit
Organization Structure - BU (I) | Implementing BU will allow BU data in dashboarding, search functionality & recruitment
Position Management (I) | Allow managers to create / remove positions in their hierarchies
Foundation Data (I) – job classification, person ID, employee data | Removes custom config and avoids extra maintenance
Contingent Workforce | Contingent Worker UI will hide data points not tracked
Leave of Absence (US) | Avoids manual entry directly on job data and non standard
Compensation | 20 SAP recommendations built into early CRs (e.g. comp forms)
Learning | 3 SAP recommendations built into early CRs (e.g. data services)
Recruitment | 9 SAP recommendations built into early CRs (e.g. employee referral)
Onboarding | 9 SAP recommendations built into early CRs (e.g. audit trail)
Performance | 5 SAP recommendations built into early CRs
Succession & Career Development Planning | 13 SAP recommendations built into early CRs (e.g. employee profile redesign)
Reporting & Analytics | Enable report center for all leaders
Platform | Improving home page and RBPs
Option 3 offers a more agile approach, with a smaller portion of value delivered early within our current instance, with the larger items requiring a new instance being pushed out in line with Resource Constraints highlighted by SteerCo leaders
74 of 155 total recommendations are being considered for implementation in Phase 1.
In addition, some have already been implemented as part of BAU and some rejected due to conflict with strategy.
- Final phasing under review

## Slide 31: MyHR2.0 Implementation Phasing – Full SOW
Dependency
Phases for Sanctioning |  |  | Phases for Future Sanctioning |  |  |  |  |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
“Quick Wins & Moving to Standard” | “Introducing Self Serve Hierarchy Functionality & Removing Custom Fields” | “Introducing Business Hierarchy and Temporary Assignment’’ | “Releasing Transition Period Functionality” | “Moving to Standard on Pay Related Information” | “Releasing Leave of Absence & Right to Return Functionality” | “Moving to Standard on Contract Type Fields” | “Moving to Standard for Contingent Workers” | “Improving Role Based Permissions” | “Integration to SAP on Premise”
Removal of link between JC & JPB HR Manager Matrix Relationship Hide user name when adding new employee Proof of concept for transition periods LMS Data Services Onboarding Admin Reports & Reporting Use Bus X Audit Func. | Position to Job Information Sync Removal of Custom Fields Position Creation & Delimiting | Temporary Assignment Data aspect of Temporary Assignments Enable Job Info Pay Group Enabling of Business Unit, Division, Department | Transition Periods integration for Employees Transition Periods for Managers | Replacing Location Group with Geozone Enable Job Info Pay Group Removal of country specific fields Reverting to standard pay ranges and Job Classification | Introduce the leave of absence and right to return functionality Improving performance of compensation module | Removing Custom Field Person ID Job information Contract Type Introducing role based learning | Mandatory fields for contingent workers Mass Positions Using LMS for Contingent workers | Making objects mandatory Role Based Permissions (RBP) Learning Improvements (Reduce Admin Access Roles) | Downstream Config Integration to SAP for BU, Division Department Chief Position Automation of transition periods for managers (integration to SAP) Introduce System Identifier to SAP ECC Redesign field values for Employee Class & Employment Type Integration for ‘Managers’ Transition Periods etc… Person ID External DOA
 |  |  |  | Evolution | IAM |  | Global Workforce Tracking | IAM, GRC | IAM, New Instance & supporting env, myFinance release 2, SAP release pack alignment
*To Be Validated
Title
Core Employee Central Scope
*Foundational work, Value delivered in later phase
Value
Dependency
*SuccessFactors Non-EC scope

## Slide 32: myHR 2.0 Original Approach Build Phase Cost Breakdowns**
Total WIP Cost |  |  |  |  |  | 
Next Phase TOTAL: |  |  |  |  | £24M | Combined total of all 3x initiatives.
myHR 2.0 Based on Original Plan Estimates |  |  | Breakdown | Sub-Total | TOTAL | Commentary
 | myHR2.0 | NGIT | £2.5M | £6.3M | £17M** | Inc. Leadership, Solution Engineering, Architecture, Assurance (Security, Controls etc.)
 |  | NGBiz | £3.8M |  |  | TBC - Business Resource costs allocation to project. Current assumption - Leadership & Product owners roles remain BAU
 |  | NG Infrastructure | £1.9M | £1.9M |  | Significant cost due to current capacity constraints. Opportunity to reduce £ with delay
 |  | MSP Business Change | £2.5M | £6.2M |  | ROM Cost from Accenture BC Team– Mini Tender to be issued subject to sanction.
 |  | Wipro | £3.7M |  |  | Technical Delivery SF & Downstream ADAM Framework
 |  | Miscellaneous | £0.2M | £2.2M |  | Staff Travel, Plug-In, Walkme, Audit cost allowance etc.
 |  | Risk | £2.1M |  |  | TBC 3rd Party Downstream Development Costs + Overrun cost risk.
GWT Based on Original Plan Estimates |  |  | Breakdown | Sub-Total | TOTAL | 
 | GWT | NGIT | £0.26M | £0.4M | £2M | Inc. Leadership, Solution Engineering, Architecture, Assurance (Security, Controls etc.)
 |  | NGBiz | £0.14M |  |  | TBC - Business Resource costs allocation to project.
 |  | NG Infrastructure | £0.1M | £0.1M |  | Environment Costs for connected delivery landscape.
 |  | Wipro | £1M | £1.0M |  | Technical Delivery ADAM Framework
 |  | Risk | £0.2M | £0.2M |  | Overrun cost risk + CR risk (E.g. additional integration requirements).
Workforce Data Domain Based on Original Plan Estimates |  |  |  | Breakdown | Sub-Total | TOTAL | 
 | Workforce Data Domain | IT | Data Culture Workstream | £0 | £0.17M | £4.6M | Inc. Leadership, Solution Engineering, Architecture, Assurance (Security, Controls etc.)
 |  |  | Data Governance Workstream | £0 |  |  | 
 |  |  | Data Integration Workstream | £0.13M |  |  | 
 |  |  | Data Models & Insight Workstream | £0.04M |  |  | 
 |  |  | Data Operating Model Workstream | £0 |  |  | 
 |  | MSP Delivery Partner | Data Culture Workstream | £1M | £4.45M |  | Cost proposal from Accenture Workforce Team following current Phase.
 |  |  | Data Governance Workstream | £0.7M |  |  | 
 |  |  | Data Integration Workstream | £1.2M |  |  | 
 |  |  | Data Models & Insight Workstream | £1M |  |  | 
 |  |  | Data Operating Model Workstream | £0.6M |  |  | 
* Note: Breakdowns for each project provided in subsequent slides
**Estimated 10-20% additional cost forecast to deliver through Option 3 – Phased Approach recommended. Additional scoping, planning & dependency assessment efforts required to refine.
 | Internal NG Costs
 | External 3rd Party Costs
 | Mixed Cost

## Slide 33: myHR 2.0 + Global Workforce Tracking Original Approach Build Phase Cost Breakdowns
Total WIP Cost |  |  |  |  |  |  | 
Next Phase TOTAL: |  |  |  |  | £19M | Delivery of myHR with Global Workforce Tracking | 
myHR 2.0 Based on Original Plan Estimates |  |  | SuccessFactors | Downstream | TOTAL |  | Comments
 |  |  | £8.0M | £8.7M | £17M |  | Source/split estimates
 | NG IT | Leadership, Governance, PMO | £380K | £380K | £2.5M | £8.2M | 50/50 – End to end
 |  | Solution Engineering & Architecture | £500K | £690K |  |  | 40/60 – SAP Downstream drives additional complexities & efforts
 |  | Testing (QES) | £76K | £110K |  |  | 30/70 - SAP Downstream drives additional complexities & efforts
 |  | Assurance – Security, Tech Risk, Controls, Assurance) | £150K | £211K |  |  | 40/60 – SAP Downstream drives additional complexities & efforts
 |  | UK Environments Resources | £10K | £285K | £1.9M* |  | UK & US costs broken down per environment.
 |  |  |  |  |  |  | UK & US Environment estimates broken down per application instance
 |  | UK Environment & Infrastructure (Azure, DXC etc.) | £30K | £208K |  |  | UK & US Environment estimates broken down per application instance
 |  | US Environments Resources (Syntax etc.) | £10K | £1,067K |  |  | Significant cost due to considerable capacity constraints.
 |  | US Environment & Infrastructure | £30K | £264K |  |  | Significant cost due to considerable capacity constraints.
 | NG Biz: | Leadership & Programme | £100K | £100K | £3.8M |  | 50/50 – End to end
 |  | Solution Design (SME Backfill) | £547K | £400K |  |  | 60/40 – Greater redesign efforts in SF – Downstream Technical Focus
 |  | Data Workstream (Extract, Transform, Load etc) | £1,686K | £40 K |  |  | 80/20 – Considerable focus on SuccessFactors (SF)
 |  | Testing (UAT, Payroll etc.) | £145K | £145K |  |  | 50/50 – End to end
 |  | Reporting | £104K | £104K |  |  | 50/50 – End to end
 |  | Reporting Strategy (WFA, Tiles etc.) | TBC |  | TBC |  | Gary D assessing revised Reporting Strategy. SteerCo Decision TBC
 | MSP Business Change Support | Change, Process & Training Augmentation | £1,250K | £1,250K | £2.5M | £6.2M | This cost cannot really be split as the work focuses on E2E Processes. 50/50 used to reflect this and the reduction in effort if SF only.
 | Wipro | Wipro myHR Core Build – SuccessFactors | £774K | - | £3.7M |  | Wipro provided Specific Tech Breakdown efforts on current scope.
 |  | Wipro myHR Core Build – Downstream | - | £970K |  |  | Wipro provided Specific Tech Breakdown efforts on current scope.
 |  | Wipro myHR Core Build – Data | £405K | £45K |  |  | Wipro provided Specific Tech Breakdown efforts on current scope.
 |  | Wipro myHR Wider Scope Build (Non-EC, RBP etc.) | £332K | £89K |  |  | Wipro provided Specific Tech Breakdown efforts on current scope.
 |  | Wipro Testing & Cutover | £247K | £247K |  |  | Wipro provided Specific Tech Breakdown efforts on current scope.
 |  | Wipro Delivery & Leadership UK & US Coordination. | £260K | £260K |  |  | Wipro provided Specific Tech Breakdown efforts on current scope.
 | Miscellaneous | Travel, Plug-In, Walkme, Audit etc. | £115K | £115K | £0.23M | £2.3M | 50/50 – End to end – Applies evenly
 | Risk | 3rd Party Downstream Development Costs ROM | £100K | £400K | £2.1M |  | 20/80 Split on potential Downstream Development costs
 |  | Risk (Overruns + Additional Resource Concerns) | £800K | £1,313K |  |  | 40/60 – SAP Downstream drives additional Risk
GWT Based on Original Plan Estimates |  |  |  |  | TOTAL: £2M |  | Comments
 | GWT | GWT Project Workstream |  |  | £2.0M | £2.0M | Combined cost of IT, Business & Wipro.
 | Internal NG Costs
 | External 3rd Party Costs
 | Mixed Cost
*Majority of US Environment costs are with outsourced partner Syntax.
Recommended Pre-Read Context

## Slide 34: DATA DOMAIN Original Approach Build Phase Cost Breakdowns
Data Domain |  | High-level Deliverables Across all Phases | Totals* |  |  | 
 |  |  | Team Size | MSP | IT | Totals per WS*
HUB | Data Culture | Data comms + signposting delivered – owners assigned. Data mgmt. library for Workforce domain created Data Culture behaviour defined and strategy created Creation of training for high-value use cases with new tooling & processes Training delivered and tracked across workforce domain | 4-6 | £966K | £0 | £966K
 | Data Governance | Increased data governance use-case adoption of Workforce Data Domain Governance Model Data management best practises defined. Process & control gaps documented Improve data management best practice & preventative data assurance and controls implemented Cross-domain governance interaction model in place and running alongside Op Model Data mgmt. best practises & Data assurance & controls reconfigured for MyHub 2.0 configuration changes | 4-6 | £725K | £0 | £725K
 | Data Integration | Analysis of Workforce data landscape documented Forecasted Data Catalogue is complete & MDM/EDP roadmap is finalised DQ dashboards built and implemented Systems Exchanging Workforce Data from SAP ECC/UK & US, MyHub, Inc. Fieldglass, integrated into MDM / EDP | 6-8 | £1,153K | £129K | £1.28M
 | Data Models & Insight | Logical Business Glossary created & workforce physical data model defined Single enterprise definitions published for data entities via Business Glossary Physical data model implemented Self-service Business reports are created & published aligned to data defined in the Data Integration workstream Business glossary & data dictionary reconfigured for MyHub 2.0 configuration changes | 6-8 | £1,008K | £39K | £1M
SPOKE | Data Operating Model | Workforce Domain Data Strategy, Roadmap & Vision As-Is assessment & To-Be creation of Data Domain Operating Model Operational roles, responsibilities, processes set up & communicated Operating model fully implemented, aligned with automated data management processes & tooling | 4-6 | £598K | £0 | £598K
 |  |  | Total | £4.45M | £168K | £4.6M
*The programme has PMO, BAU and NG support incorporated as well as a transitional cost to retain part of project team to upskill new/existing colleagues. Business costs that do not require a backfill have been discounted. Middle values of cost mitigation displayed, however -/+20% for Data Operating Mode, Culture and Governance included with -/+50% mitigation included for Integration, Models & Insight in the financials section
Total WIP Cost |  | 
Next Phase TOTAL: | £4.6M | Full scope delivered as quickly as possible to drive value ASAP.
Recommended Pre-Read Context

## Slide 35
MyHR2.0 Iteration 1-3 Cost Estimates* - Andy N
 | Iteration ROMs |  |  | Extrapolated ROMS***
Title | 1 | 2 | 3 | 4-9
 | “Quick Wins & Moving to Standard” | “Introducing New Functionality & Removing Custom Fields” | “Introducing Business Hierarchy and Temporary Assignment” | Extrapolated Sprints 4-9
Timeline |  |  |  | 
NG IT Cost | £56K | £90K | £81K | ~75K pi x 6 = £450K
Wipro Cost | £247K | £424K | £339K | ~£350K pi x 6 = £2.1M
Business Change Cost | £145K | £250K | £229K | ~£230K x 6 = £1.4M
Total Cost | £448K* | £764K* | £649K* | £4M*
Cumulative Total |  | £1.2M | £1.9M | £5.9M
1 | 2 | 3 | 4 | 5 | 6 | 7
CL | B&UT |  |  | QAB | UAT | Dep
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
CL | B&UT |  |  |  |  | QAB |  | UAT |  | Dep | ELS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
CL | B&UT |  |  |  | QAB |  | UAT |  | Dep | ELS
*Based on initial ROM’s and draft proposals, further discussion required, if the approach is agreed.
 | Iteration 10 (N)
Waterfall Integration Iteration | £6M**
 | £11.9M
**Ball Park figure – significant dependencies on timing and other inflight initiatives.

## Slide 36
GWT: Current Activity - Rohan
Overview of the GWT teams current efforts
Challenge
Activity
Next Steps, Goals & Considerations
Business Lead – Challenge in confirming the business lead for the delivery phase
Product Owner – Decision pending on product owner, who will support during the delivery and maintain the platform going forward.
Timelines - There is a dependency on ongoing Pontoon Replacement RFP, this means NG owned allication has to be implemented before end-sep'21
Project team working on Investment paper documentation
Refining the business benefits case focusing on:
Platform Savings:
  Efficiency Savings at ACG
  Cost Avoidance - ACG DB Running costs.
  Cost Avoidance - Hanging Assets/ Licenses.
Completed:
Partner Delivery Approach & Timelines
Business Resource Effort & Costing
Testing Strategy Sign-Off with QES team
Update the Sanction paper with revised costs & Business owner.
Sanction submission – both US/UK (weekly)
Delivering the Fieldglass solution in line with current RFP Timelines. Reducing dependencies on myHR.
Notes: Who is involved in the EC Workshops? Controls, HRPS (Chris Ly)
Who is involved in the DCB? Share the TORs before next steerco
Are we doing a controls impact assesement?
Who are the participants of the DCB? Functions & Roles.