## Slide 1: US Customer Business Capabilities Proposed Roadmap (Draft)
Business Capabilities Support
MDM/DQ/DG
Persistent ID (leverage UDM) , Key Customer Profile fields, Product, Account
CDP
Customer Contact,
Preference, Premise, Meter
Customer Data model, Data Catalog, Data Governance, Data Quality Profiling, CDC, Business Rules/Requirement
Customer, Segments,
Customer Programs/Plans
Customer Segments,
Customer Program/Plan, Campaign, Campaign Response
Jun
May
2021
Aug
Jul
Dec
Nov
Jan
MVP R1
2022
Feb
Mar
May
Apr
MVP R2
MVP R3
Oct
Sep
Nov
Dec
Oct
Data Management Foundational
Customer Dara Foundational
Customer Data Integration Services
Releases:
Delivery / Value Streams:
C9 – Usage Analysis
Customer Interaction,
Messages, Addition Customer Data
Jun
Aug
Jul
Sep
Persistent ID, Key Customer Profile fields, Product, Account
Usage, Bill/Credit/Payment, Customer Contact, Preference, Premise, Meter
C14 – Usage Prediction
Data Quality Profiling, CDC, Business Rules/Requirement
MVP R4
C1 – Segmentation Campaign Metrics
C7 – Product Catalog
C3 – Personalized Messages
C2 – Utilization Recommendation
C5 – Comprehensive Profile
C4 – Customer Interactions
C13 – Consolidated Profile
C8 – Customer Programs
C8 – Customer Programs
C10 – EE Recommendations
C12 – Energy Usage Insights
C17 – EE Ratings
C15 –Campaign Performance Metrics
C16 – Loyalty Program
C18 – Personalized Product Guidance
C19 – Energy Savings and Incentives
C20 – Usage History
C21 – Enrollment Offers
C22 – Proactive Usage Feedback
C23 – Outage Status
C25 – Customer Balance
C11 – Energy Self Service
CRIS and CSS CDC
Informatica Catalog, Governance and Quality Tools available
Reltio MDM and Matillion Tools available
Notes: Bottom-up view of enabling Data Capabilities in support of prioritized business capabilities
  - Iterative approach to building out capabilities incrementally though data enablement – Clean data available and under management - Master Data managed under MDM and both Master and Transaction Data Available within the Data Hub
Business Capabilities sequencing and timelines are still subject to Top-Down Analysis under the Program Governance & Alignment and Technology Solutioning Towers (taking place over the next 3-4 months, but subject to funding)
- Programs need to re-align priorities and release plan, cross-program gaps and dependencies need to be revisited and programs must be funded and resourced accordingly. This is especially impacted by program gaps in CRM and Automated
Marketing capabilities
- Note: CRM and Marketing Automation Completes in Dec 2022
Timelines for many of the required business capabilities extend beyond May-2022 which are being driving by process and tech changes
Some Capabilities that the Blueprint suggests will be dependent on a step change in platform can begin to be enabled by a Step change in data (e.g. Billing Insights). Other such as (New Service Connect) will obviously be clearly be dependent on AMI service

## Slide 2: US Customer High Level Plan for MVP 1
Business Capabilities Support
MDM/DQ/DG
Persistent ID (leverage UDM) , Key Customer Profile fields, Product, Account
CDP
Customer Contact,
Preference, Premise, Meter
Customer Data model, Data Catalog, Data Governance, Data Quality Profiling, CDC, Business Rules/Requirement
Customer, Segments,
Customer Programs/Plans
Customer Segments,
Customer Program/Plan, Campaign, Campaign Response
Jun
May
2021
Aug
Jul
Dec
Nov
MVP R1
MVP R2
MVP R3
Oct
Sep
Data Management Foundational
Customer Dara Foundational
Customer Data Integration Services
Releases:
Delivery / Value Streams:
C9 – Usage Analysis
Customer Interaction,
Messages, Addition Customer Data
Persistent ID, Key Customer Profile fields, Product, Account
Usage, Bill/Credit/Payment, Customer Contact, Preference, Premise, Meter
C14 – Usage Prediction
Data Quality Profiling, CDC, Business Rules/Requirement
MVP R4
C1 – Segmentation Campaign Metrics
C7 – Product Catalog
C3 – Personalized Messages
C2 – Utilization Recommendation
C5 – Comprehensive Profile
C4 – Customer Interactions
C13 – Consolidated Profile
C8 – Customer Programs
C8 – Customer Programs
C10 – EE Recommendations
C12 – Energy Usage Insights
C17 – EE Ratings
C15 –Campaign Performance Metrics
C16 – Loyalty Program
C18 – Personalized Product Guidance
C19 – Energy Savings and Incentives
C20 – Usage History
C21 – Enrollment Offers
C22 – Proactive Usage Feedback
C23 – Outage Status
C25 – Customer Balance
C11 – Energy Self Service
CRIS and CSS CDC
Informatica Catalog, Governance and Quality Tools available
Reltio MDM and Matillion Tools available
Notes: Bottom-up view of enabling Data Capabilities in support of prioritized business capabilities
  - Iterative approach to building out capabilities incrementally though data enablement – Clean data available and under management - Master Data managed under MDM and both Master and Transaction Data Available within the Data Hub
Business Capabilities sequencing and timelines are still subject to Top-Down Analysis under the Program Governance & Alignment and Technology Solutioning Towers (taking place over the next 3-4 months, but subject to funding)
- Programs need to re-align priorities and release plan, cross-program gaps and dependencies need to be revisited and programs must be funded and resourced accordingly. This is especially impacted by program gaps in CRM and Automated
Marketing capabilities
- Note: CRM and Marketing Automation Completes in Dec 2022
Timelines for many of the required business capabilities extend beyond May-2022 which are being driving by process and tech changes
Some Capabilities that the Blueprint suggests will be dependent on a step change in platform can begin to be enabled by a Step change in data (e.g. Billing Insights). Other such as (New Service Connect) will obviously be clearly be dependent on AMI service